## All
This tab only lists the projects for which we have complete data in terms of costs and lenghts on both the estimate (PAD) and the actual (ICR). From there we provide the explanations from the ICR in terms of why the project component witnessed a major overrun/underrun in terms of lenght and/or unit costs (USD per km)-- if applicable
Country | Region | Project ID | Component | Section | Code | Cost Type | Year | Work Type | Duration | Length (km) | Cost (M) | CCY | Cost (M; USD) | Unit costs (M USD per KM) | Check_lenght_under | Check_cost_under | Check_cost_over | Check_cost_over | Agg check | Outlier Categories | Outlier explanation
Afghanistan | South Asia | P078284 | C1 |  | P078284C1 | Estimate | 2003 | Strengthening |  | 346.8 | 69.9 | USD | 69.9 | 0.20156
Afghanistan | South Asia | P078284 | C1 |  | P078284C1 | Actual | 2008 | Strengthening |  | 345 | 98.51 | USD | 98.51 | 0.28554
Afghanistan | South Asia | P078284 | C1 |  | P078284C1 | Ratio | 2003 / 2008 | Strengthening |  | 99.48% | 140.9% |  | 140.9% | 141.7%
Afghanistan | South Asia | P078284 | C1 | S1 | P078284C1S1 | Estimate | 2003 | Strengthening | 6 | 175 | 44.9 | USD | 44.9 | 0.25657
Afghanistan | South Asia | P078284 | C1 | S1 | P078284C1S1 | Actual | 2008 | Strengthening | 30 | 175 | 67.34 | USD | 67.34 | 0.3848
Afghanistan | South Asia | P078284 | C1 |  | P078284C1S1 | Ratio | 2003 / 2008 | Strengthening | 500% | 100% | 150% |  | 150% | 150%
Afghanistan | South Asia | P078284 | C1 | S2 | P078284C1S2 | Estimate | 2003 | Strengthening | 21 | 171.8 | 25 | USD | 25 | 0.14552
Afghanistan | South Asia | P078284 | C1 | S2 | P078284C1S2 | Actual | 2008 | Strengthening | 33 | 170 | 31.17 | USD | 31.17 | 0.18335
Afghanistan | South Asia | P078284 | C1 |  | P078284C1S2 | Ratio | 2003 / 2008 | Strengthening | 157.1% | 98.95% | 124.7% |  | 124.7% | 126%
Afghanistan | South Asia | P078284 | C2 |  | P078284C2 | Estimate | 2003 | Upgrading |  | 250 | 38.3 | USD | 38.3 | 0.1532 | x |  |  | x | x
Afghanistan | South Asia | P078284 | C2 |  | P078284C2 | Actual | 2008 | Upgrading |  | 61 | 28.03 | USD | 28.03 | 0.45951 | x |  |  | x | x
Afghanistan | South Asia | P078284 | C1 |  | P078284C2 | Ratio | 2003 / 2008 | Upgrading |  | 24.4% | 73.19% |  | 73.19% | 299.9% | x |  |  | x | x | Political events; Competition; Change of project scope | security-related expenses resulting from the fragile security situation in the country; weak governance; insufficient competition and security premium pushed up bid prices for the civil works and consultant services; the availabilty of funds determined the actual length of the roads that were rehabilitated
Afghanistan | South Asia | P082472 | C1 |  | P082472C1 | Estimate | 2008 | Reconstruction |  | 2000 | 34.2 | USD | 34.2 | 0.0171
Afghanistan | South Asia | P082472 | C1 |  | P082472C1 | Actual | 2008 | Reconstruction |  | 1516.7 | 37.61 | USD | 37.61 | 0.024797
Afghanistan | South Asia | P082472 | C1 |  | P082472C1 | Ratio | 2008 / 2008 | Reconstruction |  | 75.83% | 110% |  | 110% | 145%
Afghanistan | South Asia | P107101 | C1 | S1 | P107101C1S1 | Estimate | 2010 | Strengthening | 4 | 3.14 | 3.32 | USD | 3.32 | 1.0573
Afghanistan | South Asia | P107101 | C1 | S1 | P107101C1S1 | Actual | 2012 | Strengthening | 33 | 3.14 | 3.313 | USD | 3.313 | 1.0551
Afghanistan | South Asia | P107101 | C1 |  | P107101C1S1 | Ratio | 2010 / 2012 | Strengthening | 825% | 100% | 99.79% |  | 99.79% | 99.79%
Afghanistan | South Asia | P107101 | C1 | S2 | P107101C1S2 | Estimate | 2010 | Strengthening | 4 | 3.28 | 3.85 | USD | 3.85 | 1.1738
Afghanistan | South Asia | P107101 | C1 | S2 | P107101C1S2 | Actual | 2012 | Strengthening | 33 | 3.28 | 3.796 | USD | 3.796 | 1.1573
Afghanistan | South Asia | P107101 | C1 |  | P107101C1S2 | Ratio | 2010 / 2012 | Strengthening | 825% | 100% | 98.6% |  | 98.6% | 98.6%
Afghanistan | South Asia | P107101 | C1 | S3 | P107101C1S3 | Estimate | 2010 | Strengthening | 4 | 2.22 | 2.86 | USD | 2.86 | 1.2883
Afghanistan | South Asia | P107101 | C1 | S3 | P107101C1S3 | Actual | 2012 | Strengthening | 30 | 2.22 | 2.12 | USD | 2.12 | 0.95495
Afghanistan | South Asia | P107101 | C1 |  | P107101C1S3 | Ratio | 2010 / 2012 | Strengthening | 750% | 100% | 74.13% |  | 74.13% | 74.13%
Afghanistan | South Asia | P107101 | C1 | S4 | P107101C1S4 | Estimate | 2010 | Strengthening | 4 | 3.27 | 4.3 | USD | 4.3 | 1.315
Afghanistan | South Asia | P107101 | C1 | S4 | P107101C1S4 | Actual | 2012 | Strengthening | 30 | 3.27 | 2.85 | USD | 2.85 | 0.87156
Afghanistan | South Asia | P107101 | C1 |  | P107101C1S4 | Ratio | 2010 / 2012 | Strengthening | 750% | 100% | 66.28% |  | 66.28% | 66.28%
Albania | Europe and Central Asia | P068853 | C1 | S1 | P068853C1S1 | Estimate | 1999 | Bituminous Pavement Preventive Treatment | 15 | 22 | 0.73 | USD | 0.73 | 0.033182 |  |  |  | x | x
Albania | Europe and Central Asia | P068853 | C1 | S1 | P068853C1S1 | Actual | 2004 | Routine Maintenance |  | 12.3 | 0.9999 | USD | 0.9999 | 0.081293 |  |  |  | x | x
Albania | Europe and Central Asia | P068853 | C1 |  | P068853C1S1 | Ratio | 1999 / 2004 | Routine Maintenance |  | 55.91% | 137% |  | 137% | 245% |  |  |  | x | x | Capacity of counterpart ; Weather shocks; Macroeconomic conditions | the problem of power cuts that occurred at the end of September 2000 and worsened in late October 2000 hindered the activities of Contractors and Engineers thus resulting in higher costs sustained by the Contractors ; prolonged winter season ; initially unfavourable exchange rate between the SDR and US Dollar; towards the end of the project, the US Dollar began to weaken and this reversed the losses; however, the works’ contracts were paid to the Contractors in Albanian LEK, which strengthened against the US Dollar and thus offset the gains made against the SDR
Albania | Europe and Central Asia | P068853 | C1 | S2 | P068853C1S2 | Estimate | 1999 | Bituminous Pavement Preventive Treatment | 15 | 26 | 0.87 | USD | 0.87 | 0.033462 |  |  |  | x | x
Albania | Europe and Central Asia | P068853 | C1 | S2 | P068853C1S2 | Actual | 2004 | Routine Maintenance |  | 14.9 | 1.098 | USD | 1.098 | 0.073691 |  |  |  | x | x
Albania | Europe and Central Asia | P068853 | C1 |  | P068853C1S2 | Ratio | 1999 / 2004 | Routine Maintenance |  | 57.31% | 126.2% |  | 126.2% | 220.2% |  |  |  | x | x | Capacity of counterpart ; Weather shocks; Macroeconomic conditions | the problem of power cuts that occurred at the end of September 2000 and worsened in late October 2000 hindered the activities of Contractors and Engineers and thus resulted in higher costs sustained by the Contractors ; prolonged winter season; initially unfavourable exchange rate between the SDR and US Dollar; towards the end of the project, the US Dollar began to weaken and this reversed the losses; however, the works’ contracts were paid to the Contractors in Albanian LEK, which strengthened against the US Dollar and thus offset the gains made against the SDR
Albania | Europe and Central Asia | P068853 | C1 | S3 | P068853C1S3 | Estimate | 1999 | Asphalt Mix Resurfacing | 15 | 30 | 1.9 | USD | 1.9 | 0.063333 |  |  | x |  | x
Albania | Europe and Central Asia | P068853 | C1 | S3 | P068853C1S3 | Actual | 2004 | Asphalt Mix Resurfacing | 4 | 29 | 0.188 | USD | 0.188 | 0.0064828 |  |  | x |  | x
Albania | Europe and Central Asia | P068853 | C1 |  | P068853C1S3 | Ratio | 1999 / 2004 | Asphalt Mix Resurfacing | 26.67% | 96.67% | 9.895% |  | 9.895% | 10.24% |  |  | x |  | x | Capacity of counterpart ; Weather shocks; Macroeconomic conditions | the problem of power cuts that occurred at the end of September 2000 and worsened in late October 2000 hindered the activities of Contractors and Engineers thus resulting in higher costs sustained by the Contractors ; prolonged winter season; initially unfavourable exchange rate between the SDR and US Dollar; towards the end of the project, the US Dollar began to weaken and this reversed the losses; however, the works’ contracts were paid to the Contractors in Albanian LEK, which strengthened against the US Dollar and thus offset the gains made against the SDR
Albania | Europe and Central Asia | P068853 | C1 | S4 | P068853C1S4 | Estimate | 1999 | Routine Maintenance | 15 | 49 | 1.43 | USD | 1.43 | 0.029184
Albania | Europe and Central Asia | P068853 | C1 | S4 | P068853C1S4 | Actual | 2004 | Routine Maintenance | 8 | 42.7 | 1.591 | USD | 1.591 | 0.03726
Albania | Europe and Central Asia | P068853 | C1 |  | P068853C1S4 | Ratio | 1999 / 2004 | Routine Maintenance | 53.33% | 87.14% | 111.3% |  | 111.3% | 127.7%
Albania | Europe and Central Asia | P068853 | C1 | S5 | P068853C1S5 | Estimate | 1999 | Asphalt Mix Resurfacing | 15 | 70 | 5.4 | USD | 5.4 | 0.077143
Albania | Europe and Central Asia | P068853 | C1 | S5 | P068853C1S5 | Actual | 2004 | Asphalt Mix Resurfacing | 44 | 55.3 | 6.37 | USD | 6.37 | 0.11519
Albania | Europe and Central Asia | P068853 | C1 |  | P068853C1S5 | Ratio | 1999 / 2004 | Asphalt Mix Resurfacing | 293.3% | 79% | 118% |  | 118% | 149.3%
Albania | Europe and Central Asia | P068853 | C1 | S6 | P068853C1S6 | Estimate | 1999 | Surface Treatment Resurfacing | 15 | 24 | 1.2 | USD | 1.2 | 0.05 | x |  |  | x | x
Albania | Europe and Central Asia | P068853 | C1 | S6 | P068853C1S6 | Actual | 2004 | Routine Maintenance | 4 | 1.5 | 0.146 | USD | 0.146 | 0.097333 | x |  |  | x | x
Albania | Europe and Central Asia | P068853 | C1 |  | P068853C1S6 | Ratio | 1999 / 2004 | Routine Maintenance | 26.67% | 6.25% | 12.17% |  | 12.17% | 194.7% | x |  |  | x | x | Capacity of counterpart ; Capacity of counterpart ; Macroeconomic conditions | due to the limited availability of funds, the initially planned to be repaired 24km had to be drastically reduced to only the very worst section for a total length of 1.5km; the problem of power cuts that occurred at the end of September 2000 and worsened in late October 2000 hindered the activities of Contractors and Engineers thus resulting in higher costs sustained by the Contractors ; initially unfavourable exchange rate between the SDR and US Dollar; towards the end of the project, the US Dollar began to weaken and this reversed the losses; however, the works’ contracts were paid to the Contractors in Albanian LEK, which strengthened against the US Dollar and thus offset the gains made against the SDR
Albania | Europe and Central Asia | P078949 | C1 | S1 | P078949C1S1 | Estimate | 2007 | New 2L Highway | 22 | 9 | 12.32 | USD | 12.32 | 1.3689
Albania | Europe and Central Asia | P078949 | C1 | S1 | P078949C1S1 | Actual | 2011 | New 4L Expressway | 49 | 9 | 14.48 | USD | 14.48 | 1.6089
Albania | Europe and Central Asia | P078949 | C1 |  | P078949C1S1 | Ratio | 2007 / 2011 | New 4L Expressway | 222.7% | 100% | 117.5% |  | 117.5% | 117.5%
Albania | Europe and Central Asia | P078949 | C1 | S2 | P078949C1S2 | Estimate | 2007 | New 2L Highway | 11 | 9 | 10.68 | USD | 10.68 | 1.1867
Albania | Europe and Central Asia | P078949 | C1 | S2 | P078949C1S2 | Actual | 2011 | New 4L Expressway | 41 | 9 | 10.32 | USD | 10.32 | 1.1467
Albania | Europe and Central Asia | P078949 | C1 |  | P078949C1S2 | Ratio | 2007 / 2011 | New 4L Expressway | 372.7% | 100% | 96.63% |  | 96.63% | 96.63%
Albania | Europe and Central Asia | P078949 | C1 | S3 | P078949C1S3 | Estimate | 2007 | New 2L Highway | 16 | 8 | 13.2 | USD | 13.2 | 1.65
Albania | Europe and Central Asia | P078949 | C1 | S3 | P078949C1S3 | Actual | 2011 | New 4L Expressway | 35 | 8 | 13.64 | USD | 13.64 | 1.705
Albania | Europe and Central Asia | P078949 | C1 |  | P078949C1S3 | Ratio | 2007 / 2011 | New 4L Expressway | 218.8% | 100% | 103.3% |  | 103.3% | 103.3%
Albania | Europe and Central Asia | P107833 | C1 | S1 | P107833C1S1 | Estimate | 2008 | Reconstruction | 5 | 10.9 | 2.42 | USD | 2.42 | 0.22202
Albania | Europe and Central Asia | P107833 | C1 | S1 | P107833C1S1 | Actual | 2013 | Reconstruction | 12 | 10.9 | 1.79 | USD | 1.79 | 0.16422
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C1S1 | Ratio | 2008 / 2013 | Reconstruction | 240% | 100% | 73.97% |  | 73.97% | 73.97%
Albania | Europe and Central Asia | P107833 | C1 | S2 | P107833C1S2 | Estimate | 2008 | Reconstruction | 8 | 6.6 | 2.06 | USD | 2.06 | 0.31212
Albania | Europe and Central Asia | P107833 | C1 | S2 | P107833C1S2 | Actual | 2013 | Reconstruction | 12 | 6.6 | 2.01 | USD | 2.01 | 0.30455
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C1S2 | Ratio | 2008 / 2013 | Reconstruction | 150% | 100% | 97.57% |  | 97.57% | 97.57%
Albania | Europe and Central Asia | P107833 | C1 | S3 | P107833C1S3 | Estimate | 2008 | Reconstruction | 10 | 10.5 | 2.57 | USD | 2.57 | 0.24476
Albania | Europe and Central Asia | P107833 | C1 | S3 | P107833C1S3 | Actual | 2013 | Reconstruction | 12 | 10.5 | 2.14 | USD | 2.14 | 0.20381
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C1S3 | Ratio | 2008 / 2013 | Reconstruction | 120% | 100% | 83.27% |  | 83.27% | 83.27%
Albania | Europe and Central Asia | P107833 | C2 | S1 | P107833C2S1 | Estimate | 2008 | Reconstruction | 11 | 12.6 | 2.47 | USD | 2.47 | 0.19603
Albania | Europe and Central Asia | P107833 | C2 | S1 | P107833C2S1 | Actual | 2013 | Reconstruction | 12 | 12.6 | 1.45 | USD | 1.45 | 0.11508
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S1 | Ratio | 2008 / 2013 | Reconstruction | 109.1% | 100% | 58.7% |  | 58.7% | 58.7%
Albania | Europe and Central Asia | P107833 | C2 | S2 | P107833C2S2 | Estimate | 2008 | Reconstruction | 12 | 9.8 | 2.19 | USD | 2.19 | 0.22347
Albania | Europe and Central Asia | P107833 | C2 | S2 | P107833C2S2 | Actual | 2013 | Reconstruction | 24 | 9.8 | 1.93 | USD | 1.93 | 0.19694
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S2 | Ratio | 2008 / 2013 | Reconstruction | 200% | 100% | 88.13% |  | 88.13% | 88.13%
Albania | Europe and Central Asia | P107833 | C2 | S3 | P107833C2S3 | Estimate | 2008 | Reconstruction | 13 | 12.8 | 3.15 | USD | 3.15 | 0.24609
Albania | Europe and Central Asia | P107833 | C2 | S3 | P107833C2S3 | Actual | 2013 | Reconstruction | 12 | 12.8 | 2.81 | USD | 2.81 | 0.21953
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S3 | Ratio | 2008 / 2013 | Reconstruction | 92.31% | 100% | 89.21% |  | 89.21% | 89.21%
Albania | Europe and Central Asia | P107833 | C2 | S4 | P107833C2S4 | Estimate | 2008 | Reconstruction | 21 | 11.5 | 2.09 | USD | 2.09 | 0.18174
Albania | Europe and Central Asia | P107833 | C2 | S4 | P107833C2S4 | Actual | 2013 | Reconstruction | 36 | 11.5 | 2.92 | USD | 2.92 | 0.25391
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S4 | Ratio | 2008 / 2013 | Reconstruction | 171.4% | 100% | 139.7% |  | 139.7% | 139.7%
Albania | Europe and Central Asia | P107833 | C2 | S5 | P107833C2S5 | Estimate | 2008 | Reconstruction | 12 | 11.8 | 2.01 | USD | 2.01 | 0.17034
Albania | Europe and Central Asia | P107833 | C2 | S5 | P107833C2S5 | Actual | 2013 | Reconstruction | 12 | 11.8 | 2.19 | USD | 2.19 | 0.18559
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S5 | Ratio | 2008 / 2013 | Reconstruction | 100% | 100% | 109% |  | 109% | 109%
Albania | Europe and Central Asia | P107833 | C2 | S6 | P107833C2S6 | Estimate | 2008 | Reconstruction | 10 | 9 | 2.55 | USD | 2.55 | 0.28333
Albania | Europe and Central Asia | P107833 | C2 | S6 | P107833C2S6 | Actual | 2013 | Reconstruction | 12 | 9 | 1.64 | USD | 1.64 | 0.18222
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S6 | Ratio | 2008 / 2013 | Reconstruction | 120% | 100% | 64.31% |  | 64.31% | 64.31%
Albania | Europe and Central Asia | P107833 | C2 | S7 | P107833C2S7 | Estimate | 2008 | Reconstruction | 8 | 7.8 | 2.06 | USD | 2.06 | 0.2641
Albania | Europe and Central Asia | P107833 | C2 | S7 | P107833C2S7 | Actual | 2013 | Reconstruction | 12 | 7.8 | 1.97 | USD | 1.97 | 0.25256
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S7 | Ratio | 2008 / 2013 | Reconstruction | 150% | 100% | 95.63% |  | 95.63% | 95.63%
Albania | Europe and Central Asia | P107833 | C2 | S8 | P107833C2S8 | Estimate | 2008 | Reconstruction | 6 | 5.4 | 1.24 | USD | 1.24 | 0.22963
Albania | Europe and Central Asia | P107833 | C2 | S8 | P107833C2S8 | Actual | 2013 | Reconstruction | 12 | 5.4 | 0.86 | USD | 0.86 | 0.15926
Albania | Europe and Central Asia | P107833 | C1 |  | P107833C2S8 | Ratio | 2008 / 2013 | Reconstruction | 200% | 100% | 69.35% |  | 69.35% | 69.35%
Angola | Sub-Saharan Africa | P095229 | C1 | S1 | P095229C1S1 | Estimate | 2014 | Reconstruction |  | 600 | 13 | USD | 13 | 0.021667 | x |  |  | x | x
Angola | Sub-Saharan Africa | P095229 | C1 | S1 | P095229C1S1 | Actual | 2014 | Reconstruction |  | 200 | 20 | USD | 20 | 0.1 | x |  |  | x | x
Angola | Sub-Saharan Africa | P095229 | C1 |  | P095229C1S1 | Ratio | 2014 / 2014 | Reconstruction |  | 33.33% | 153.8% |  | 153.8% | 461.5% | x |  |  | x | x | Political events; Administrative processes; | Initially, the PMIU, as well as contractors and consultants, faced extensive logistical difficulties when visiting the provinces due to inadequate transport infrastructure, the presence of unmarked land mines, and the tense security situation in the country. ; (i) Board approval of the EMRP-2 was delayed by 14 months while the Bank reviewed non-concessional borrowing by the GoA. (ii) A number of factors under the control of the PMIU contributed to initial implementation delay but were remediated by the end of the project. These included: (a) logistics difficulty in coordination in the overall management of project activities, including preparation of work plans; (b) fragmented approach to the submission of procurement requests by the PMIU, which created confusion and delayed approvals; and (c) inadequate arrangements for the collection of project-related data needed for the agreed monitoring and evaluation procedures. ;
Argentina | Latin America and Caribbean | P099585 | C1 |  | P099585C1 | Estimate | 2006 | Strengthening |  | 174.26 | 42.21 | USD | 42.21 | 0.24222 |  |  |  | x | x
Argentina | Latin America and Caribbean | P099585 | C1 |  | P099585C1 | Actual | 2014 | Strengthening |  | 125 | 50.53 | USD | 50.53 | 0.40424 |  |  |  | x | x
Argentina | Latin America and Caribbean | P099585 | C1 |  | P099585C1 | Ratio | 2006 / 2014 | Strengthening |  | 71.73% | 119.7% |  | 119.7% | 166.9% |  |  |  | x | x | Quality of estimates; Macroeconomic conditions; | The actual prices of civil works far exceeded original estimates and the financing gap would require a reduction of the civil works targets.; A local inflation rate that far exceeded the rate of devaluation of the peso vis a vis the dollar.;
Argentina | Latin America and Caribbean | P099585 | C2 |  | P099585C2 | Estimate | 2006 | Strengthening |  | 424 | 34.5 | USD | 34.5 | 0.081368 | x |  |  | x | x
Argentina | Latin America and Caribbean | P099585 | C2 |  | P099585C2 | Actual | 2014 | Strengthening |  | 136.93 | 42.4 | USD | 42.4 | 0.30965 | x |  |  | x | x
Argentina | Latin America and Caribbean | P099585 | C1 |  | P099585C2 | Ratio | 2006 / 2014 | Strengthening |  | 32.29% | 122.9% |  | 122.9% | 380.6% | x |  |  | x | x | Quality of estimates; Macroeconomic conditions; Political events | The actual prices of civil works far exceeded original estimates and the financing gap would require a reduction of the civil works targets.; A local inflation rate that far exceeded the rate of devaluation of the peso vis a vis the dollar.; The Central government withdrew its support for the proposed additional financing and the civil works component could not be restored to its original size.
Argentina | Latin America and Caribbean | P088153 | C1 |  | P088153C1 | Estimate | 2004 | Strengthening | 72 | 21042 | 258.7 | USD | 258.7 | 0.012294 |  |  |  | x | x
Argentina | Latin America and Caribbean | P088153 | C1 |  | P088153C1 | Actual | 2011 | Strengthening |  | 12664 | 682 | USD | 682 | 0.053853 |  |  |  | x | x
Argentina | Latin America and Caribbean | P088153 | C1 |  | P088153C1 | Ratio | 2004 / 2011 | Strengthening |  | 60.18% | 263.6% |  | 263.6% | 438% |  |  |  | x | x | Macroeconomic conditions; Competition; Quality of estimates | Cost increase for road works due to changes in world markets and prices (particularly increase in the cost of petrol and associated byproducts such as asphalt and fuels) so that between Jan 2004 and Dec 2009 the cost of road works in Argentina had increased by about 90%); Limited competition due to the industry being strained as a result of an imbalance between its capacity (eroded after the 2001 economic crisis) and the high demand for road works following an upsurge of public investments in the sector; The first round of bidding involved 10 contracts and resulted in bidders’ proposals being much higher than expected with a limited price variation among the bids; the government decided to cancel the bidding process and postpone all subsequent biddings under the project until an in-depth analysis was carried out
Argentina | Latin America and Caribbean | P095569 | C1 |  | P095569C1 | Estimate | 2007 | Asphalt Mix Resurfacing |  | 3290 | 384.4 | USD | 384.4 | 0.11684
Argentina | Latin America and Caribbean | P095569 | C1 |  | P095569C1 | Actual | 2014 | Asphalt Mix Resurfacing |  | 3327 | 389.8 | USD | 389.8 | 0.11716
Argentina | Latin America and Caribbean | P095569 | C1 |  | P095569C1 | Ratio | 2007 / 2014 | Asphalt Mix Resurfacing |  | 101.1% | 101.4% |  | 101.4% | 100.3%
Armenia | Europe and Central Asia | P115486 | C1 |  | P115486C1 | Estimate | 2009 | Reconstruction | 7 | 99.8 | 27.1 | USD | 27.1 | 0.27154 |  | x |  |  | x
Armenia | Europe and Central Asia | P115486 | C1 |  | P115486C1 | Actual | 2014 | Reconstruction | 43 | 446 | 116.5982 | USD | 116.5982 | 0.26143 |  | x |  |  | x
Armenia | Europe and Central Asia | P115486 | C1 |  | P115486C1 | Ratio | 2009 / 2014 | Reconstruction | 614.3% | 446.9% | 430.3% |  | 430.3% | 96.28% |  | x |  |  | x | Capacity of contractors; Change of project scope; | Local designers and contractors successfully applied new technologies and appropriate and cost-effective design standards based on international practices; The project went through 2 additional financing to rehabilitate more km of road; the closing dates were extended to allow time to carry out that extra work; the deviation in length and duration seem to be due to the fact that the project was initially created to respond to “the emergency needs of creating temporary employment in the wake of global crisis;
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 350.7 | 26.8 | USD | 26.8 | 0.076419 |  |  |  | x | x
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1 | Actual | 2005 | Asphalt Mix Resurfacing |  | 227 | 33.3 | USD | 33.3 | 0.1467 |  |  |  | x | x
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 64.73% | 124.3% |  | 124.3% | 192% |  |  |  | x | x | Political events ; ; | Frequent changes at high levels of government, coupled with a bias towards short-term solutions, and lack of conviction vis-a-vis the reforms it supported, limited the institutional impact of the project; ;
Armenia | Europe and Central Asia | P044829 | C1 | S1 | P044829C1S1 | Estimate | 2000 | Surface Treatment Resurfacing | 15 | 18.7 | 1.19 | USD | 1.19 | 0.063636
Armenia | Europe and Central Asia | P044829 | C1 | S1 | P044829C1S1 | Actual | 2005 | Surface Treatment Resurfacing |  | 18.7 | 1.2 | USD | 1.2 | 0.064171
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1S1 | Ratio | 2000 / 2005 | Surface Treatment Resurfacing |  | 100% | 100.8% |  | 100.8% | 100.8%
Armenia | Europe and Central Asia | P044829 | C1 | S2 | P044829C1S2 | Estimate | 2000 | Asphalt Mix Resurfacing | 15 | 8.5 | 1.42 | USD | 1.42 | 0.16706
Armenia | Europe and Central Asia | P044829 | C1 | S2 | P044829C1S2 | Actual | 2005 | Asphalt Mix Resurfacing |  | 8.5 | 1.671 | USD | 1.671 | 0.19659
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1S2 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% | 117.7% |  | 117.7% | 117.7%
Armenia | Europe and Central Asia | P044829 | C1 | S3 | P044829C1S3 | Estimate | 2000 | Asphalt Mix Resurfacing | 15 | 11.6 | 1.03 | USD | 1.03 | 0.088793
Armenia | Europe and Central Asia | P044829 | C1 | S3 | P044829C1S3 | Actual | 2005 | Asphalt Mix Resurfacing |  | 11.6 | 1.17 | USD | 1.17 | 0.10086
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1S3 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% | 113.6% |  | 113.6% | 113.6%
Armenia | Europe and Central Asia | P044829 | C1 | S4 | P044829C1S4 | Estimate | 2000 | Asphalt Mix Resurfacing | 14 | 2.6 | 0.6 | USD | 0.6 | 0.23077
Armenia | Europe and Central Asia | P044829 | C1 | S4 | P044829C1S4 | Actual | 2005 | Asphalt Mix Resurfacing |  | 2.6 | 0.556 | USD | 0.556 | 0.21385
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1S4 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% | 92.67% |  | 92.67% | 92.67%
Armenia | Europe and Central Asia | P044829 | C1 | S5 | P044829C1S5 | Estimate | 2000 | Asphalt Mix Resurfacing | 14 | 16 | 1.75 | USD | 1.75 | 0.10938
Armenia | Europe and Central Asia | P044829 | C1 | S5 | P044829C1S5 | Actual | 2005 | Asphalt Mix Resurfacing |  | 16 | 1.902 | USD | 1.902 | 0.11888
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1S5 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% | 108.7% |  | 108.7% | 108.7%
Armenia | Europe and Central Asia | P044829 | C1 | S6 | P044829C1S6 | Estimate | 2000 | Asphalt Mix Resurfacing | 14 | 10.4 | 1.24 | USD | 1.24 | 0.11923
Armenia | Europe and Central Asia | P044829 | C1 | S6 | P044829C1S6 | Actual | 2005 | Asphalt Mix Resurfacing |  | 10.4 | 1.12 | USD | 1.12 | 0.10769
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1S6 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% | 90.32% |  | 90.32% | 90.32%
Azerbaijan | Europe and Central Asia | P040716 | C1 | S1 | P040716C1S1 | Estimate | 2001 | Reconstruction |  | 21.3 | 9.01 | USD | 9.01 | 0.423
Azerbaijan | Europe and Central Asia | P040716 | C1 | S1 | P040716C1S1 | Actual | 2009 | Reconstruction |  | 21.3 | 7.5 | USD | 7.5 | 0.35211
Azerbaijan | Europe and Central Asia | P040716 | C1 |  | P040716C1S1 | Ratio | 2001 / 2009 | Reconstruction |  | 100% | 83.24% |  | 83.24% | 83.24%
Azerbaijan | Europe and Central Asia | P040716 | C1 | S2 | P040716C1S2 | Estimate | 2001 | Reconstruction |  | 72.7 | 34.43 | USD | 34.43 | 0.47359
Azerbaijan | Europe and Central Asia | P040716 | C1 | S2 | P040716C1S2 | Actual | 2009 | Reconstruction |  | 72.7 | 30.8 | USD | 30.8 | 0.42366
Azerbaijan | Europe and Central Asia | P040716 | C1 |  | P040716C1S2 | Ratio | 2001 / 2009 | Reconstruction |  | 100% | 89.46% |  | 89.46% | 89.46%
Azerbaijan | Europe and Central Asia | P094488 | C1 | S1 | P094488C1S1 | Estimate | 2005 | Widening |  | 80 | 122.7 | USD | 122.7 | 1.5337 | x |  |  | x | x
Azerbaijan | Europe and Central Asia | P094488 | C1 | S1 | P094488C1S1 | Actual | 2005 | Widening |  | 31 | 85.3 | USD | 85.3 | 2.7516 | x |  |  | x | x
Azerbaijan | Europe and Central Asia | P094488 | C1 |  | P094488C1S1 | Ratio | 2005 / 2005 | Widening |  | 38.75% | 69.52% |  | 69.52% | 179.4% | x |  |  | x | x | Administrative processes; Macroeconomic conditions; Competition | The pace of implementation of the civil works suffered delays thorough the project due to land acquisition, procurement issues, in addition to the lack of experience of ARS on implementing large construction work.; The 2006-2008 economic boom brought about by the oil revenues, which overheated the economy and caused inflation and currency appreciation, and the world economic crisis of 2008-2009, which disturbed the contractor’s finances, influenced the project implementation. The project started to face a financing gap in 2009/2010. ; The pace of implementation of the civil works suffered delays thorough the project due availability of bitumen issues.
Azerbaijan | Europe and Central Asia | P094488 | C1 | S2 | P094488C1S2 | Estimate | 2005 | Reconstruction |  | 124 | 80 | USD | 80 | 0.64516 |  |  |  | x | x
Azerbaijan | Europe and Central Asia | P094488 | C1 | S2 | P094488C1S2 | Actual | 2005 | Reconstruction |  | 124 | 142.5 | USD | 142.5 | 1.1492 |  |  |  | x | x
Azerbaijan | Europe and Central Asia | P094488 | C1 |  | P094488C1S2 | Ratio | 2005 / 2005 | Reconstruction |  | 100% | 178.1% |  | 178.1% | 178.1% |  |  |  | x | x | Administrative processes; Macroeconomic conditions; Competition | The pace of implementation of the civil works suffered delays thorough the project due to land acquisition, procurement issues, in addition to the lack of experience of ARS on implementing large construction work.; The 2006-2008 economic boom brought about by the oil revenues, which overheated the economy and caused inflation and currency appreciation, and the world economic crisis of 2008-2009, which disturbed the contractor’s finances, influenced the project implementation. The project started to face a financing gap in 2009/2010. ; The pace of implementation of the civil works suffered delays thorough the project due availability of bitumen issues.
Bangladesh | South Asia | P071435 | C1 |  | P071435C1 | Estimate | 2003 | Partial Widening |  | 1100 | 6353.75 | BDT | 110.5 | 0.10045
Bangladesh | South Asia | P071435 | C1 |  | P071435C1 | Actual | 2013 | Partial Widening |  | 1115 | 8638.09 | BDT | 105.6389 | 0.094743
Bangladesh | South Asia | P071435 | C1 |  | P071435C1 | Ratio | 2003 / 2013 | Partial Widening |  | 101.4% | 136% |  | 95.6% | 94.31%
Bangladesh | South Asia | P071435 | C2 |  | P071435C2 | Estimate | 2003 | Upgrading |  | 500 | 1351.25 | BDT | 23.5 | 0.047
Bangladesh | South Asia | P071435 | C2 |  | P071435C2 | Actual | 2013 | Upgrading |  | 515 | 2085.78 | BDT | 25.5079 | 0.04953
Bangladesh | South Asia | P071435 | C1 |  | P071435C2 | Ratio | 2003 / 2013 | Upgrading |  | 103% | 154.4% |  | 108.5% | 105.4%
Bangladesh | South Asia | P071435 | C3 |  | P071435C3 | Estimate | 2003 | Asphalt Mix Resurfacing |  | 1500 | 2242.5 | BDT | 39 | 0.026
Bangladesh | South Asia | P071435 | C3 |  | P071435C3 | Actual | 2013 | Asphalt Mix Resurfacing |  | 2120 | 3425.22 | BDT | 41.8885 | 0.019759
Bangladesh | South Asia | P071435 | C1 |  | P071435C3 | Ratio | 2003 / 2013 | Asphalt Mix Resurfacing |  | 141.3% | 152.7% |  | 107.4% | 76%
Belarus | Europe and Central Asia | P118375 | C1 | S1 | P118375C1S1 | Estimate | 2010 | Widening and Reconstruction | 31 | 17.42 | 43.1 | USD | 43.1 | 2.4742
Belarus | Europe and Central Asia | P118375 | C1 | S1 | P118375C1S1 | Actual | 2016 | Widening and Reconstruction | 24 | 17.42 | 36.14 | USD | 36.14 | 2.0746
Belarus | Europe and Central Asia | P118375 | C1 |  | P118375C1S1 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% | 83.85% |  | 83.85% | 83.85%
Belarus | Europe and Central Asia | P118375 | C1 | S2 | P118375C1S2 | Estimate | 2010 | Widening and Reconstruction | 31 | 10.4 | 25.7 | USD | 25.7 | 2.4712
Belarus | Europe and Central Asia | P118375 | C1 | S2 | P118375C1S2 | Actual | 2016 | Widening and Reconstruction | 24 | 10.4 | 34.15 | USD | 34.15 | 3.2837
Belarus | Europe and Central Asia | P118375 | C1 |  | P118375C1S2 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% | 132.9% |  | 132.9% | 132.9%
Belarus | Europe and Central Asia | P118375 | C1 | S3 | P118375C1S3 | Estimate | 2010 | Widening and Reconstruction | 31 | 16.5 | 41 | USD | 41 | 2.4848
Belarus | Europe and Central Asia | P118375 | C1 | S3 | P118375C1S3 | Actual | 2016 | Widening and Reconstruction | 24 | 16.5 | 33.3 | USD | 33.3 | 2.0182
Belarus | Europe and Central Asia | P118375 | C1 |  | P118375C1S3 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% | 81.22% |  | 81.22% | 81.22%
Belarus | Europe and Central Asia | P118375 | C1 | S4 | P118375C1S4 | Estimate | 2010 | Widening and Reconstruction | 31 | 8.4 | 20.8 | USD | 20.8 | 2.4762
Belarus | Europe and Central Asia | P118375 | C1 | S4 | P118375C1S4 | Actual | 2016 | Widening and Reconstruction | 24 | 8.4 | 30.66 | USD | 30.66 | 3.65
Belarus | Europe and Central Asia | P118375 | C1 |  | P118375C1S4 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% | 147.4% |  | 147.4% | 147.4%
Belize | Latin America and Caribbean | P040150 | C1 | S1 | P040150C1S1 | Estimate | 2000 | Upgrading |  | 20 | 6.8 | USD | 6.8 | 0.34
Belize | Latin America and Caribbean | P040150 | C1 | S1 | P040150C1S1 | Actual | 2006 | Upgrading |  | 20 | 8.68 | USD | 8.68 | 0.434
Belize | Latin America and Caribbean | P040150 | C1 |  | P040150C1S1 | Ratio | 2000 / 2006 | Upgrading |  | 100% | 127.6% |  | 127.6% | 127.6%
Benin | Sub-Saharan Africa | AfDB-P-BJ-DB0-010 | C1 |  | AfDB-P-BJ-DB0-010 C1 | Estimate | 2002 | New 2L Highway |  | 125 | 18918.45 | CFAF | 27.1435 | 0.21715 | x |  | x | macroeconomic conditions | Depreciation of the UA (p.10 & 28)
Benin | Sub-Saharan Africa | AfDB-P-BJ-DB0-010 | C1 |  | AfDB-P-BJ-DB0-010 C1 | Actual | 2011 | New 2L Highway |  | 125 | 19978.47 | CFAF | 42.3398 | 0.33872 | x |  | x | macroeconomic conditions | The cost of works per kilometre rose to CFAF 155 million instead of the CFAF 145 million estimated at appraisal in 2003, owing to a surge in petroleum product prices in 2007 and 2008 (p.28)
Benin | Sub-Saharan Africa | AfDB-P-BJ-DB0-010 | C1 |  | AfDB-P-BJ-DB0-010 C1 | Ratio | 2002 / 2011 | New 2L Highway |  | 100% | 105.6% |  | 156% | 156% | x |  | x | change of project scope | line items were revised upwards due to construction of a new bridge and road alignment rectifications (p.28) | macroeconomic conditions; macroeconomic conditions; change of project scope | Depreciation of the UA (p.10 & 28); The cost of works per kilometre rose to CFAF 155 million instead of the CFAF 145 million estimated at appraisal in 2003, owing to a surge in petroleum product prices in 2007 and 2008 (p.28); line items were revised upwards due to construction of a new bridge and road alignment rectifications (p.28)
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C1 |  | AfDB loan number: F/BEN/ROD/92/27 C1 | Estimate | 1992 | New 2L Highway |  | 2.3 | 4662 | FCFA | 17.6131 | 7.6579
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C1 |  | AfDB loan number: F/BEN/ROD/92/27 C1 | Actual | 1999 | New 2L Highway |  | 2.3 | 6134 | FCFA | 9.9628 | 4.3317
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C1 |  | AfDB loan number: F/BEN/ROD/92/27 C1 | Ratio | 1992 / 1999 | New 2L Highway |  | 100% | 131.6% |  | 56.56% | 56.56%
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C2 |  | AfDB loan number: F/BEN/ROD/92/27 C2 | Estimate | 1992 | Partial Widening and Reconstruction |  | 4.5 | 1992 | FCFA | 7.5258 | 1.6724
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C2 |  | AfDB loan number: F/BEN/ROD/92/27 C2 | Actual | 1999 | Partial Widening and Reconstruction |  | 4.5 | 5602 | FCFA | 9.0987 | 2.0219
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C1 |  | AfDB loan number: F/BEN/ROD/92/27 C2 | Ratio | 1992 / 1999 | Partial Widening and Reconstruction |  | 100% | 281.2% |  | 120.9% | 120.9%
Bhutan | South Asia | P059481 | C1 |  | P059481C1 | Estimate | 1999 | New 1L Road | 60 | 122 | 12.5 | USD | 12.5 | 0.10246
Bhutan | South Asia | P059481 | C1 |  | P059481C1 | Actual | 2006 | New 1L Road | 74 | 128.76 | 12.6 | USD | 12.6 | 0.097856
Bhutan | South Asia | P059481 | C1 |  | P059481C1 | Ratio | 1999 / 2006 | New 1L Road | 123.3% | 105.5% | 100.8% |  | 100.8% | 95.51%
Bhutan | South Asia | P100332 | C1 |  | P100332C1 | Estimate | 2007 | New 1L Road |  | 89 | 8.7 | USD | 8.7 | 0.097753
Bhutan | South Asia | P100332 | C1 |  | P100332C1 | Actual | 2013 | New 1L Road |  | 90 | 10.84 | USD | 10.84 | 0.12044
Bhutan | South Asia | P100332 | C1 |  | P100332C1 | Ratio | 2007 / 2013 | New 1L Road |  | 101.1% | 124.6% |  | 124.6% | 123.2%
Bhutan | South Asia | P100332 | C1 | S1 | P100332C1S1 | Estimate | 2007 | New 1L Road | 10 | 13.7 | 2 | USD | 2 | 0.14599
Bhutan | South Asia | P100332 | C1 | S1 | P100332C1S1 | Actual | 2013 | New 1L Road |  | 11.83 | 1.66 | USD | 1.66 | 0.14032
Bhutan | South Asia | P100332 | C1 |  | P100332C1S1 | Ratio | 2007 / 2013 | New 1L Road |  | 86.35% | 83% |  | 83% | 96.12%
Bhutan | South Asia | P100332 | C1 | S2 | P100332C1S2 | Estimate | 2007 | New 1L Road | 10 | 22 | 2.5 | USD | 2.5 | 0.11364
Bhutan | South Asia | P100332 | C1 | S2 | P100332C1S2 | Actual | 2013 | New 1L Road |  | 26.1 | 3.19 | USD | 3.19 | 0.12222
Bhutan | South Asia | P100332 | C1 |  | P100332C1S2 | Ratio | 2007 / 2013 | New 1L Road |  | 118.6% | 127.6% |  | 127.6% | 107.6%
Bhutan | South Asia | P100332 | C1 | S3 | P100332C1S3 | Estimate | 2007 | New 1L Road | 16 | 29 | 3.3 | USD | 3.3 | 0.11379
Bhutan | South Asia | P100332 | C1 | S3 | P100332C1S3 | Actual | 2013 | New 1L Road |  | 29 | 4.04 | USD | 4.04 | 0.13931
Bhutan | South Asia | P100332 | C1 |  | P100332C1S3 | Ratio | 2007 / 2013 | New 1L Road |  | 100% | 122.4% |  | 122.4% | 122.4%
Bolivia | Latin America and Caribbean | P068968 | C1 |  | P068968C1 | Estimate | 2002 | Reconstruction |  | 353 | 36.39 | USD | 36.39 | 0.10309
Bolivia | Latin America and Caribbean | P068968 | C1 |  | P068968C1 | Actual | 2011 | Reconstruction |  | 353 | 42.5 | USD | 42.5 | 0.1204
Bolivia | Latin America and Caribbean | P068968 | C1 |  | P068968C1 | Ratio | 2002 / 2011 | Reconstruction |  | 100% | 116.8% |  | 116.8% | 116.8%
Bolivia | Latin America and Caribbean | P068968 | C2 |  | P068968C2 | Estimate | 2002 | Asphalt Mix Resurfacing |  | 3000 | 108 | USD | 108 | 0.036 | x |  |  |  | x
Bolivia | Latin America and Caribbean | P068968 | C2 |  | P068968C2 | Actual | 2011 | Asphalt Mix Resurfacing |  | 1330 | 61 | USD | 61 | 0.045865 | x |  |  |  | x
Bolivia | Latin America and Caribbean | P068968 | C1 |  | P068968C2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 44.33% | 56.48% |  | 56.48% | 127.4% | x |  |  |  | x | Macroeconomic conditions; Weather shocks ; Change of project scope | changes in world market and prices led to a dramatic increase in the costs of works items that use asphalt products ; unforseen weather conditions in the aftermath of El Nino phenomenon (2007) demanded the re-direction of the implementing agency’s efforts to attend, under emergency response, the most vulnerable roads; the scope and implementation of the periodic maintenance of the national highway system was severely affected by the lower-than-expected level of counterpart funds assigned to the Road Maintenance National Account
Brazil | Latin America and Caribbean | P055954 | C1 |  | P055954C1 | Estimate | 2001 | Surface Treatment Resurfacing |  | 1500 | 62.2 | USD | 62.2 | 0.041467
Brazil | Latin America and Caribbean | P055954 | C1 |  | P055954C1 | Actual | 2006 | Surface Treatment Resurfacing |  | 1250 | 77.2 | USD | 77.2 | 0.06176
Brazil | Latin America and Caribbean | P055954 | C1 |  | P055954C1 | Ratio | 2001 / 2006 | Surface Treatment Resurfacing |  | 83.33% | 124.1% |  | 124.1% | 148.9%
Brazil | Latin America and Caribbean | P055954 | C2 |  | P055954C2 | Estimate | 2001 | Asphalt Mix Resurfacing |  | 300 | 40.1 | USD | 40.1 | 0.13367
Brazil | Latin America and Caribbean | P055954 | C2 |  | P055954C2 | Actual | 2006 | Asphalt Mix Resurfacing |  | 270 | 37.6 | USD | 37.6 | 0.13926
Brazil | Latin America and Caribbean | P055954 | C1 |  | P055954C2 | Ratio | 2001 / 2006 | Asphalt Mix Resurfacing |  | 90% | 93.77% |  | 93.77% | 104.2%
Brazil | Latin America and Caribbean | P095460 | C1 |  | P095460C1 | Estimate | 2006 | Asphalt Mix Resurfacing |  | 2000 | 140.6 | USD | 140.6 | 0.0703 |  |  |  | x | x
Brazil | Latin America and Caribbean | P095460 | C1 |  | P095460C1 | Actual | 2014 | Asphalt Mix Resurfacing |  | 1196 | 194.07 | USD | 194.07 | 0.16227 |  |  |  | x | x
Brazil | Latin America and Caribbean | P095460 | C1 |  | P095460C1 | Ratio | 2006 / 2014 | Asphalt Mix Resurfacing |  | 59.8% | 138% |  | 138% | 230.8% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; Capacity of Counterpart | High inflation, the decreasing US Dollar vs. Brazilian Real further and the 2008 global crisis resulted, in Bahia, in a severe fiscal crisis.; Approximately four years elapsed between the initial road assessments (end of 2004), on which the initial road works cost estimates were based, and the actual works contracting. Road conditions had meanwhile substantially deteriorated, and final engineering designs required adjustments to those prepared at a conceptual level four years earlier in the Project Appraisal Document. Rehabilitation costs consequently increased.; Unfamiliarity with Bank international financing, the Government of Bahia decided to wait for the loan to become effective before bidding the works engineering designs. This decision increased by a year the Project initial delay. Engineering designs started in May 2008; once contracted, delays issues were again compounded by the poor quality of the designs, inducing back and forth exchanges between DERBA’s Project Coordination Unit and the consulting firms.
Brazil | Latin America and Caribbean | P106663 | C1 |  | P106663C1 | Estimate | 2009 | Reconstruction |  | 3100 | 477.04 | USD | 477.04 | 0.15388 |  | x |  |  | x
Brazil | Latin America and Caribbean | P106663 | C1 |  | P106663C1 | Actual | 2015 | Reconstruction |  | 6409 | 1010.25 | USD | 1010.25 | 0.15763 |  | x |  |  | x
Brazil | Latin America and Caribbean | P106663 | C1 |  | P106663C1 | Ratio | 2009 / 2015 | Reconstruction |  | 206.7% | 211.8% |  | 211.8% | 102.4% |  | x |  |  | x | ; Change of project scope; | ; Through an Additional Financing loan, civil works originally planned under other phases of the Program were executed under this Component;
Bulgaria | Europe and Central Asia | P094018 | C1 |  | P094018C1 | Estimate | 2007 | New 4L Expressway | 19 | 3.4 | 12.9 | USD | 12.9 | 3.7941
Bulgaria | Europe and Central Asia | P094018 | C1 |  | P094018C1 | Actual | 2014 | New 4L Expressway | 26 | 3.4 | 14.71 | USD | 14.71 | 4.3265
Bulgaria | Europe and Central Asia | P094018 | C1 |  | P094018C1 | Ratio | 2007 / 2014 | New 4L Expressway | 136.8% | 100% | 114% |  | 114% | 114%
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1 | Estimate | 2007 | Strengthening |  | 450 | 140.15 | EUR | 190.604 | 0.42356
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1 | Actual | 2013 | Strengthening |  | 307 | 94.6 | EUR | 129.589 | 0.42211
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1 | Ratio | 2007 / 2013 | Strengthening |  | 68.22% | 67.5% |  | 67.99% | 99.66%
Bulgaria | Europe and Central Asia | P099894 | C1 | S1 | P099894C1S1 | Estimate | 2007 | Strengthening | 15 | 37.14 | 7.4 | EUR | 10.064 | 0.27097
Bulgaria | Europe and Central Asia | P099894 | C1 | S1 | P099894C1S1 | Actual | 2013 | Strengthening |  | 36.6 | 11.9 | USD | 11.9 | 0.32514
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1S1 | Ratio | 2007 / 2013 | Strengthening |  | 98.55% | 160.8% |  | 118.2% | 120%
Bulgaria | Europe and Central Asia | P099894 | C1 | S2 | P099894C1S2 | Estimate | 2007 | Strengthening | 15 | 44.5 | 14.3 | EUR | 19.448 | 0.43703
Bulgaria | Europe and Central Asia | P099894 | C1 | S2 | P099894C1S2 | Actual | 2013 | Strengthening |  | 47.3 | 17.3 | USD | 17.3 | 0.36575
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1S2 | Ratio | 2007 / 2013 | Strengthening |  | 106.3% | 121% |  | 88.96% | 83.69%
Bulgaria | Europe and Central Asia | P099894 | C1 | S3 | P099894C1S3 | Estimate | 2007 | Strengthening | 19 | 61 | 18.3 | EUR | 24.888 | 0.408
Bulgaria | Europe and Central Asia | P099894 | C1 | S3 | P099894C1S3 | Actual | 2013 | Strengthening |  | 46.1 | 17.5 | USD | 17.5 | 0.37961
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1S3 | Ratio | 2007 / 2013 | Strengthening |  | 75.57% | 95.63% |  | 70.32% | 93.04%
Bulgaria | Europe and Central Asia | P099894 | C1 | S4 | P099894C1S4 | Estimate | 2007 | Strengthening | 26 | 55.9 | 23.4 | EUR | 31.824 | 0.5693
Bulgaria | Europe and Central Asia | P099894 | C1 | S4 | P099894C1S4 | Actual | 2013 | Strengthening |  | 55.4 | 18.7 | USD | 18.7 | 0.33755
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1S4 | Ratio | 2007 / 2013 | Strengthening |  | 99.11% | 79.91% |  | 58.76% | 59.29%
Bulgaria | Europe and Central Asia | P099894 | C1 | S5 | P099894C1S5 | Estimate | 2007 | Strengthening | 24 | 65 | 17.1 | EUR | 23.256 | 0.35778
Bulgaria | Europe and Central Asia | P099894 | C1 | S5 | P099894C1S5 | Actual | 2013 | Strengthening |  | 62.9 | 21.1 | USD | 21.1 | 0.33545
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1S5 | Ratio | 2007 / 2013 | Strengthening |  | 96.77% | 123.4% |  | 90.73% | 93.76%
Bulgaria | Europe and Central Asia | P099894 | C1 | S6 | P099894C1S6 | Estimate | 2007 | Strengthening | 25 | 65 | 24.9 | EUR | 33.864 | 0.52098
Bulgaria | Europe and Central Asia | P099894 | C1 | S6 | P099894C1S6 | Actual | 2013 | Strengthening |  | 61.8 | 22.1 | USD | 22.1 | 0.35761
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1S6 | Ratio | 2007 / 2013 | Strengthening |  | 95.08% | 88.76% |  | 65.26% | 68.64%
Burkina Faso | Sub-Saharan Africa | P074030 | C1 |  | P074030C1 | Estimate | 2003 | Reconstruction |  | 7057 | 129.26 | USD | 129.26 | 0.018317 | x |  |  | x | x
Burkina Faso | Sub-Saharan Africa | P074030 | C1 |  | P074030C1 | Actual | 2014 | Reconstruction |  | 2678 | 130.1 | USD | 130.1 | 0.048581 | x |  |  | x | x
Burkina Faso | Sub-Saharan Africa | P074030 | C1 |  | P074030C1 | Ratio | 2003 / 2014 | Reconstruction |  | 37.95% | 100.6% |  | 100.6% | 265.2% | x |  |  | x | x | Macroeconomic conditions; Weather shocks ; Change of project scope | increase in overall construction costs by about 30 percent between the launch of the project implementation and the 2006 restructuring; major drop of about 32 percent in the value of the US$ vis-àvis the FCFA from FCFA660 at appraisal (December 2002) to FCFA450 at the original project closing date (September 30, 2008); exchange rate fluctuations; steady increase of oil prices ; higher costs were incurred as a result of floodings ; the change in the length of the civil works led to the restructuring of the project which resulted from the financial constraints and overly optimistic budget planning
Burkina Faso | Sub-Saharan Africa | AfDB loan number: F/BUF/RTE/92/19 | C1 |  | AfDB loan number: F/BUF/RTE/92/19C1 | Estimate | 1990 | Upgrading | 20 | 76.4 | 3751 | CFAF | 13.7773 | 0.18033 | x | x | x
Burkina Faso | Sub-Saharan Africa | AfDB loan number: F/BUF/RTE/92/19 | C1 |  | AfDB loan number: F/BUF/RTE/92/19C1 | Actual | 1999 | Upgrading | 44 | 134.4 | 4502 | CFAF | 7.3121 | 0.054406 | x | x | x
Burkina Faso | Sub-Saharan Africa | AfDB loan number: F/BUF/RTE/92/19 | C1 |  | AfDB loan number: F/BUF/RTE/92/19C1 | Ratio | 1990 / 1999 | Upgrading | 220% | 175.9% | 120% |  | 53.07% | 30.17% | x | x | x | Quality of estimates |  | ; ; Quality of estimates
Burkina Faso | Sub-Saharan Africa | AfDB P-BF-DB0-012 | C1 |  | AfDB P-BF-DB0-012C1 | Estimate | 2004 | Strengthening |  | 975 | 8912.01 | CFAF | 16.8699 | 0.017302
Burkina Faso | Sub-Saharan Africa | AfDB P-BF-DB0-012 | C1 |  | AfDB P-BF-DB0-012C1 | Actual | 2011 | Strengthening |  | 919 | 8286.41 | CFAF | 17.5612 | 0.019109
Burkina Faso | Sub-Saharan Africa | AfDB P-BF-DB0-012 | C1 |  | AfDB P-BF-DB0-012C1 | Ratio | 2004 / 2011 | Strengthening |  | 94.26% | 92.98% |  | 104.1% | 110.4%
Burundi | Sub-Saharan Africa | P064876 | C1 |  | P064876C1 | Estimate | 2004 | Reconstruction | 9 | 161.8 | 29.167 | USD | 29.167 | 0.18027
Burundi | Sub-Saharan Africa | P064876 | C1 |  | P064876C1 | Actual | 2016 | Reconstruction |  | 161.8 | 42.388 | USD | 42.388 | 0.26198
Burundi | Sub-Saharan Africa | P064876 | C1 |  | P064876C1 | Ratio | 2004 / 2016 | Reconstruction |  | 100% | 145.3% |  | 145.3% | 145.3%
Burundi | Sub-Saharan Africa | P064876 | C2 |  | P064876C2 | Estimate | 2004 | Gravel Resurfacing | 5 | 350 | 9.523 | USD | 9.523 | 0.027209
Burundi | Sub-Saharan Africa | P064876 | C2 |  | P064876C2 | Actual | 2016 | Gravel Resurfacing |  | 355 | 8.119 | USD | 8.119 | 0.02287
Burundi | Sub-Saharan Africa | P064876 | C1 |  | P064876C2 | Ratio | 2004 / 2016 | Gravel Resurfacing |  | 101.4% | 85.26% |  | 85.26% | 84.06%
Cambodia | East Asia and Pacific | P071207 | C1 | S1 | P071207C1S1 | Estimate | 2003 | Upgrading | 12 | 21.8 | 1.78 | USD | 1.78 | 0.081651
Cambodia | East Asia and Pacific | P071207 | C1 | S1 | P071207C1S1 | Actual | 2012 | Upgrading |  | 19.8 | 1.61 | USD | 1.61 | 0.081313
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S1 | Ratio | 2003 / 2012 | Upgrading |  | 90.83% | 90.45% |  | 90.45% | 99.59%
Cambodia | East Asia and Pacific | P071207 | C1 | S10 | P071207C1S10 | Estimate | 2003 | Upgrading | 12 | 10.8 | 0.39 | USD | 0.39 | 0.036111
Cambodia | East Asia and Pacific | P071207 | C1 | S10 | P071207C1S10 | Actual | 2012 | Upgrading |  | 8 | 0.42 | USD | 0.42 | 0.0525
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S10 | Ratio | 2003 / 2012 | Upgrading |  | 74.07% | 107.7% |  | 107.7% | 145.4%
Cambodia | East Asia and Pacific | P071207 | C1 | S2 | P071207C1S2 | Estimate | 2003 | Upgrading | 12 | 11.8 | 0.92 | USD | 0.92 | 0.077966
Cambodia | East Asia and Pacific | P071207 | C1 | S2 | P071207C1S2 | Actual | 2012 | Upgrading |  | 12 | 1.29 | USD | 1.29 | 0.1075
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S2 | Ratio | 2003 / 2012 | Upgrading |  | 101.7% | 140.2% |  | 140.2% | 137.9%
Cambodia | East Asia and Pacific | P071207 | C1 | S3 | P071207C1S3 | Estimate | 2003 | Upgrading | 12 | 8.9 | 0.59 | USD | 0.59 | 0.066292 |  | x |  |  | x
Cambodia | East Asia and Pacific | P071207 | C1 | S3 | P071207C1S3 | Actual | 2012 | Upgrading |  | 13.5 | 0.95 | USD | 0.95 | 0.07037 |  | x |  |  | x
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S3 | Ratio | 2003 / 2012 | Upgrading |  | 151.7% | 161% |  | 161% | 106.2% |  | x |  |  | x | Change of project scope; Capacity of counterpart; | The project was designed with an implementation period of about four years, but with one suspension and three extensions, ended up lasting nearly eight years.; Implementing agency displayed renewed energy and follow-through during final stages of project;
Cambodia | East Asia and Pacific | P071207 | C1 | S4 | P071207C1S4 | Estimate | 2003 | Upgrading | 12 | 18.2 | 1.3 | USD | 1.3 | 0.071429
Cambodia | East Asia and Pacific | P071207 | C1 | S4 | P071207C1S4 | Actual | 2012 | Upgrading |  | 15.2 | 1.06 | USD | 1.06 | 0.069737
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S4 | Ratio | 2003 / 2012 | Upgrading |  | 83.52% | 81.54% |  | 81.54% | 97.63%
Cambodia | East Asia and Pacific | P071207 | C1 | S5 | P071207C1S5 | Estimate | 2003 | Upgrading | 12 | 15.3 | 1.23 | USD | 1.23 | 0.080392
Cambodia | East Asia and Pacific | P071207 | C1 | S5 | P071207C1S5 | Actual | 2012 | Upgrading |  | 15.5 | 1.31 | USD | 1.31 | 0.084516
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S5 | Ratio | 2003 / 2012 | Upgrading |  | 101.3% | 106.5% |  | 106.5% | 105.1%
Cambodia | East Asia and Pacific | P071207 | C1 | S6 | P071207C1S6 | Estimate | 2003 | Upgrading | 12 | 18.4 | 1.09 | USD | 1.09 | 0.059239
Cambodia | East Asia and Pacific | P071207 | C1 | S6 | P071207C1S6 | Actual | 2012 | Upgrading |  | 18.5 | 1.49 | USD | 1.49 | 0.080541
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S6 | Ratio | 2003 / 2012 | Upgrading |  | 100.5% | 136.7% |  | 136.7% | 136%
Cambodia | East Asia and Pacific | P071207 | C1 | S7 | P071207C1S7 | Estimate | 2003 | Upgrading | 12 | 17.8 | 0.58 | USD | 0.58 | 0.032584 |  | x |  |  | x
Cambodia | East Asia and Pacific | P071207 | C1 | S7 | P071207C1S7 | Actual | 2012 | Upgrading |  | 29 | 1.1 | USD | 1.1 | 0.037931 |  | x |  |  | x
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S7 | Ratio | 2003 / 2012 | Upgrading |  | 162.9% | 189.7% |  | 189.7% | 116.4% |  | x |  |  | x | Change of project scope; Capacity of counterpart; | The project was designed with an implementation period of about four years, but with one suspension and three extensions, ended up lasting nearly eight years.; Implementing agency displayed renewed energy and follow-through during final stages of project;
Cambodia | East Asia and Pacific | P071207 | C1 | S8 | P071207C1S8 | Estimate | 2003 | Upgrading | 12 | 12.7 | 0.42 | USD | 0.42 | 0.033071 |  |  |  | x | x
Cambodia | East Asia and Pacific | P071207 | C1 | S8 | P071207C1S8 | Actual | 2012 | Upgrading |  | 12.6 | 0.71 | USD | 0.71 | 0.056349 |  |  |  | x | x
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S8 | Ratio | 2003 / 2012 | Upgrading |  | 99.21% | 169% |  | 169% | 170.4% |  |  |  | x | x | Change of project scope; Procurement system; | The project was designed with an implementation period of about four years, but with one suspension and three extensions, ended up lasting nearly eight years.; Complaints of procurement irregularities led to an investigation by the Bank's INT, which found that Sub-standard designs were resulting in multiple variation orders and cost overruns. ;
Cambodia | East Asia and Pacific | P071207 | C1 | S9 | P071207C1S9 | Estimate | 2003 | Reconstruction | 12 | 16.7 | 0.36 | USD | 0.36 | 0.021557 |  |  |  | x | x
Cambodia | East Asia and Pacific | P071207 | C1 | S9 | P071207C1S9 | Actual | 2012 | Reconstruction |  | 17 | 0.63 | USD | 0.63 | 0.037059 |  |  |  | x | x
Cambodia | East Asia and Pacific | P071207 | C1 |  | P071207C1S9 | Ratio | 2003 / 2012 | Reconstruction |  | 101.8% | 175% |  | 175% | 171.9% |  |  |  | x | x | Change of project scope; Procurement system; | The project was designed with an implementation period of about four years, but with one suspension and three extensions, ended up lasting nearly eight years.; Complaints of procurement irregularities led to an investigation by the Bank's INT, which found that Sub-standard designs were resulting in multiple variation orders and cost overruns. ;
Cambodia | East Asia and Pacific | Project Number: 42358-013 | C1 |  | Project Number: 42358-013C1 | Estimate | 2009 | Upgrading |  | 113 | 23.78 | KHR | 0.0056647 | 5.013e-05 | x |  | x
Cambodia | East Asia and Pacific | Project Number: 42358-013 | C1 |  | Project Number: 42358-013C1 | Actual | 2014 | upgrading |  | 113 | 35.93 | KHR | 0.0088991 | 7.8753e-05 | x |  | x
Cambodia | East Asia and Pacific | Project Number: 42358-013 | C1 |  | Project Number: 42358-013C1 | Ratio | 2009 / 2014 | upgrading |  | 100% | 151.1% |  | 157.1% | 157.1% | x |  | x | macroeconomic conditions | The difference between total project costs at appraisal and completion is about $2.59 million, which was mainly due to the cost overruns of civil works, as a result of price increases beyond projections (PCR p. 5) | ; ; macroeconomic conditions | ; ; The difference between total project costs at appraisal and completion is about $2.59 million, which was mainly due to the cost overruns of civil works, as a result of price increases beyond projections (PCR p. 5)
Cameroon | Sub-Saharan Africa | P074490 | C1 |  | P074490C1 | Estimate | 2002 | Widening and Reconstruction |  | 23 | 58.13 | USD | 58.13 | 2.5274
Cameroon | Sub-Saharan Africa | P074490 | C1 |  | P074490C1 | Actual | 2010 | Widening and Reconstruction | 48 | 27 | 67.88 | USD | 67.88 | 2.5141
Cameroon | Sub-Saharan Africa | P074490 | C1 |  | P074490C1 | Ratio | 2002 / 2010 | Widening and Reconstruction |  | 117.4% | 116.8% |  | 116.8% | 99.47%
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 | S1 | AfDB loan number: B/CAM/RTE/89/16C1S1 | Estimate | 1988 | Upgrading | 22 | 15.8 | 2354.2 | CFAF | 7.9042 | 0.50027
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 | S1 | AfDB loan number: B/CAM/RTE/89/16C1S1 | Actual | 1998 | Upgrading | 44 | 15.8 | 2402.71 | CFAF | 4.0727 | 0.25777
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 |  | AfDB loan number: B/CAM/RTE/89/16C1S1 | Ratio | 1988 / 1998 | Upgrading | 200% | 100% | 102.1% |  | 51.53% | 51.53%
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 | S2 | AfDB loan number: B/CAM/RTE/89/16C1S2 | Estimate | 1988 | Strengthening | 22 | 49.6 | 3785.5 | CFAF | 12.7098 | 0.25625 | x |  | x
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 | S2 | AfDB loan number: B/CAM/RTE/89/16C1S2 | Actual | 1998 | Strengthening | 44 | 49.4 | 3565.01 | CFAF | 6.0429 | 0.12233 | x |  | x
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 |  | AfDB loan number: B/CAM/RTE/89/16C1S2 | Ratio | 1988 / 1998 | Strengthening | 200% | 99.6% | 94.18% |  | 47.55% | 47.74% | x |  | x | change of project scope | Modifications to the layout were made in some areas situated between Bafoussam and the Noun bridge reducing the lehght of the road by 155 meters. This made it possible to to reduce the cost of the expropriations. (annex 5 p. 1 of 2) | ; ; change of project scope | ; ; Modifications to the layout were made in some areas situated between Bafoussam and the Noun bridge reducing the lehght of the road by 155 meters. This made it possible to to reduce the cost of the expropriations. (annex 5 p. 1 of 2)
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S1 | P087004C1S1 | Estimate | 2005 | Upgrading |  | 3 | 0.62 | USD | 0.62 | 0.20667
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S1 | P087004C1S1 | Actual | 2014 | Upgrading |  | 3 | 0.75 | USD | 0.75 | 0.25
Cape Verde | Sub-Saharan Africa | P087004 | C1 |  | P087004C1S1 | Ratio | 2005 / 2014 | Upgrading |  | 100% | 121% |  | 121% | 121%
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S2 | P087004C1S2 | Estimate | 2005 | Upgrading |  | 11 | 3.62 | USD | 3.62 | 0.32909
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S2 | P087004C1S2 | Actual | 2014 | Upgrading |  | 11 | 4.18 | USD | 4.18 | 0.38
Cape Verde | Sub-Saharan Africa | P087004 | C1 |  | P087004C1S2 | Ratio | 2005 / 2014 | Upgrading |  | 100% | 115.5% |  | 115.5% | 115.5%
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S3 | P087004C1S3 | Estimate | 2005 | Upgrading |  | 27 | 8.13 | USD | 8.13 | 0.30111
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S3 | P087004C1S3 | Actual | 2014 | Upgrading |  | 27 | 12.06 | USD | 12.06 | 0.44667
Cape Verde | Sub-Saharan Africa | P087004 | C1 |  | P087004C1S3 | Ratio | 2005 / 2014 | Upgrading |  | 100% | 148.3% |  | 148.3% | 148.3%
Chad | Sub-Saharan Africa | P035672 | C1 | S1 | P035672C1S1 | Estimate | 2000 | Strengthening |  | 104 | 35.54 | USD | 35.54 | 0.34173
Chad | Sub-Saharan Africa | P035672 | C1 | S1 | P035672C1S1 | Actual | 2009 | Strengthening |  | 104 | 39 | USD | 39 | 0.375
Chad | Sub-Saharan Africa | P035672 | C1 |  | P035672C1S1 | Ratio | 2000 / 2009 | Strengthening |  | 100% | 109.7% |  | 109.7% | 109.7%
Chad | Sub-Saharan Africa | P035672 | C1 | S2 | P035672C1S2 | Estimate | 2000 | Upgrading |  | 286 | 25.36 | USD | 25.36 | 0.088671 |  |  |  | x | x
Chad | Sub-Saharan Africa | P035672 | C1 | S2 | P035672C1S2 | Actual | 2009 | Upgrading |  | 286 | 44 | USD | 44 | 0.15385 |  |  |  | x | x
Chad | Sub-Saharan Africa | P035672 | C1 |  | P035672C1S2 | Ratio | 2000 / 2009 | Upgrading |  | 100% | 173.5% |  | 173.5% | 173.5% |  |  |  | x | x | Change of project scope ; Capacity of contractors; Macroeconomic conditions | higher costs resulting from a catastrophic pavement failure which led to a complete redesign of the road works (major reconstruction as opposed to the originally planned minor rehabilitation) ; higher costs were incurred following the termination of the major civil works contract for the strenghtening of exisiting paved roads under Component 1 due to the incapability of the contractor to execute the contract (it is estimated that the default of the contractor may have generated a cost to the government of up to US$6.7 million, essentially due to the additional works required to remedy the accelerated physical deterioration of the road that continued until the works resumed); the significant depreciation of the SDR (in which the IDA credit was denominated) vis-à-vis the national currency FCFA (in which most contracts were signed) resulted in a shortfall of Bank financing (the exchange rate of SDR1.00 = CFA 950 at negotiations fell steadily by 41 percent to a low CFA 560 at project completion)
Chad | Sub-Saharan Africa | P035672 | C2 |  | P035672C2 | Estimate | 2000 | Routine Maintenance | 48 | 441 | 19.57 | USD | 19.57 | 0.044376
Chad | Sub-Saharan Africa | P035672 | C2 |  | P035672C2 | Actual | 2009 | Routine Maintenance | 57 | 441 | 28 | USD | 28 | 0.063492
Chad | Sub-Saharan Africa | P035672 | C1 |  | P035672C2 | Ratio | 2000 / 2009 | Routine Maintenance | 118.8% | 100% | 143.1% |  | 143.1% | 143.1%
Chad | Sub-Saharan Africa | AfDB project - P-TD-DB0-008 | C1 |  | AfDB project - P-TD-DB0-008C1 | Estimate | 2009 | Surface Treatment Resurfacing | 28 | 110 | 44.715 | UA | 30.4731 | 0.27703 | x |  | x
Chad | Sub-Saharan Africa | AfDB project - P-TD-DB0-008 | C1 |  | AfDB project - P-TD-DB0-008C1 | Actual | 2017 | Surface Treatment Resurfacing | 28 | 110 | 75.2566 | UA | 53.1691 | 0.48336 | x |  | x
Chad | Sub-Saharan Africa | AfDB project - P-TD-DB0-008 | C1 |  | AfDB project - P-TD-DB0-008C1 | Ratio | 2009 / 2017 | Surface Treatment Resurfacing | 100% | 100% | 168.3% |  | 174.5% | 174.5% | x |  | x | Change of project scope | The project cost differences are mainly explained by the additional costs of the modification of the roadway structure decided by the Government - The replacement of the two-layer surfacing course with 5 cm of bituminous concrete generated an additional cost of CFAF 11,055,332,234 or 30% of the total basic contract amount. | ; ; Change of project scope | ; ; The project cost differences are mainly explained by the additional costs of the modification of the roadway structure decided by the Government - The replacement of the two-layer surfacing course with 5 cm of bituminous concrete generated an additional cost of CFAF 11,055,332,234 or 30% of the total basic contract amount.
China | East Asia and Pacific | P045915 | C1 |  | P045915C1 | Estimate | 2000 | New 6L Expressway | 54 | 31.25 | 194.8 | USD | 194.8 | 6.2336
China | East Asia and Pacific | P045915 | C1 |  | P045915C1 | Actual | 2008 | New 6L Expressway | 54 | 31.25 | 216.4 | USD | 216.4 | 6.9248
China | East Asia and Pacific | P045915 | C1 |  | P045915C1 | Ratio | 2000 / 2008 | New 6L Expressway | 100% | 100% | 111.1% |  | 111.1% | 111.1%
China | East Asia and Pacific | P056596 | C1 |  | P056596 C1 | Estimate | 2001 | Widening |  | 32.9 | 170.3 | USD | 170.3 | 5.1763
China | East Asia and Pacific | P056596 | C1 |  | P056596 C1 | Actual | 2009 | Widening |  | 43.4 | 204.5 | USD | 204.5 | 4.712
China | East Asia and Pacific | P056596 | C1 |  | P056596 C1 | Ratio | 2001 / 2009 | Widening |  | 131.9% | 120.1% |  | 120.1% | 91.03%
China | East Asia and Pacific | P058843 | C1 |  | P058843C1 | Estimate | 2000 | Asphalt Mix Resurfacing | 48 | 236 | 56.72 | USD | 56.72 | 0.24034
China | East Asia and Pacific | P058843 | C1 |  | P058843C1 | Actual | 2007 | Asphalt Mix Resurfacing | 60 | 231.1 | 48.61 | USD | 48.61 | 0.21034
China | East Asia and Pacific | P058843 | C1 |  | P058843C1 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing | 125% | 97.92% | 85.7% |  | 85.7% | 87.52%
China | East Asia and Pacific | P058845 | C1 | S1 | P058845C1S1 | Estimate | 2001 | New 4L Expressway |  | 130 | 397 | USD | 397 | 3.0538
China | East Asia and Pacific | P058845 | C1 | S1 | P058845C1S1 | Actual | 2007 | New 4L Expressway | 25 | 128 | 271 | USD | 271 | 2.1172
China | East Asia and Pacific | P058845 | C1 |  | P058845C1S1 | Ratio | 2001 / 2007 | New 4L Expressway |  | 98.46% | 68.26% |  | 68.26% | 69.33%
China | East Asia and Pacific | P058845 | C2 |  | P058845C2 | Estimate | 2001 | Upgrading |  | 180 | 33.85 | USD | 33.85 | 0.18806
China | East Asia and Pacific | P058845 | C2 |  | P058845C2 | Actual | 2007 | Upgrading | 15 | 182 | 26.8 | USD | 26.8 | 0.14725
China | East Asia and Pacific | P058845 | C1 |  | P058845C2 | Ratio | 2001 / 2007 | Upgrading |  | 101.1% | 79.17% |  | 79.17% | 78.3%
China | East Asia and Pacific | P070519 | C1 | S1 | P070519C1S1 | Estimate | 2005 | New 6L Expressway |  | 11.6 | 158.57 | USD | 158.57 | 13.6698 |  |  |  | x | x
China | East Asia and Pacific | P070519 | C1 | S1 | P070519C1S1 | Actual | 2013 | New 6L Expressway | 39 | 11.6 | 326.25 | USD | 326.25 | 28.125 |  |  |  | x | x
China | East Asia and Pacific | P070519 | C1 |  | P070519C1S1 | Ratio | 2005 / 2013 | New 6L Expressway |  | 100% | 205.7% |  | 205.7% | 205.7% |  |  |  | x | x | Macroeconomic conditions ; Quality of estimates; | actual costs turned out to be higher than the estimated costs as a result of US dollar depreciation relative to the RMB (about 26 percent), increased construction material prices and inflation; increases in resettlements costs were incurred following a slow and difficult acquisition process ;
China | East Asia and Pacific | P070519 | C1 | S2 | P070519C1S2 | Estimate | 2005 | New 4L Expressway |  | 4.1 | 31.13 | USD | 31.13 | 7.5927
China | East Asia and Pacific | P070519 | C1 | S2 | P070519C1S2 | Actual | 2013 | New 4L Expressway |  | 4.1 | 32.68 | USD | 32.68 | 7.9707
China | East Asia and Pacific | P070519 | C1 |  | P070519C1S2 | Ratio | 2005 / 2013 | New 4L Expressway |  | 100% | 105% |  | 105% | 105%
China | East Asia and Pacific | P076714 | C1 |  | P076714C1 | Estimate | 2003 | New 4L Expressway | 42 | 116.15 | 4109 | RMB | 497.4576 | 4.2829
China | East Asia and Pacific | P076714 | C1 |  | P076714C1 | Actual | 2009 | New 4L Expressway | 39 | 116.12 | 3485 | RMB | 510.2489 | 4.3942
China | East Asia and Pacific | P076714 | C1 |  | P076714C1 | Ratio | 2003 / 2009 | New 4L Expressway | 92.86% | 99.97% | 84.81% |  | 102.6% | 102.6%
China | East Asia and Pacific | P076714 | C1 | S1 | P076714C1S1 | Estimate | 2003 | New 4L Expressway |  | 57.02 | 1426 | RMB | 172.6392 | 3.0277
China | East Asia and Pacific | P076714 | C1 | S1 | P076714C1S1 | Actual | 2009 | New 4L Expressway |  | 65.09 | 1618 | RMB | 236.896 | 3.6395
China | East Asia and Pacific | P076714 | C1 |  | P076714C1S1 | Ratio | 2003 / 2009 | New 4L Expressway |  | 114.2% | 113.5% |  | 137.2% | 120.2%
China | East Asia and Pacific | P076714 | C1 | S2 | P076714C1S2 | Estimate | 2003 | New 4L Expressway |  | 48.95 | 1371 | RMB | 165.9806 | 3.3908 |  |  |  | x | x
China | East Asia and Pacific | P076714 | C1 | S2 | P076714C1S2 | Actual | 2009 | New 4L Expressway |  | 41.3 | 1479 | RMB | 216.5447 | 5.2432 |  |  |  | x | x
China | East Asia and Pacific | P076714 | C1 |  | P076714C1S2 | Ratio | 2003 / 2009 | New 4L Expressway |  | 84.37% | 107.9% |  | 130.5% | 154.6% |  |  |  | x | x | Macroeconomic conditions ; Competition; | Dollar depreciation vis-à-vis the RMB.; At the bidding stage, the prices were lower than expected, due to strong competition for civil works contracts, ranging between 4-6 bids, depending on the package.;
China | East Asia and Pacific | P076714 | C1 | S3 | P076714C1S3 | Estimate | 2003 | New 4L Expressway |  | 10.18 | 1313 | RMB | 158.9588 | 15.6148 |  |  | x |  | x
China | East Asia and Pacific | P076714 | C1 | S3 | P076714C1S3 | Actual | 2009 | New 4L Expressway |  | 9.73 | 387 | RMB | 56.6618 | 5.8234 |  |  | x |  | x
China | East Asia and Pacific | P076714 | C1 |  | P076714C1S3 | Ratio | 2003 / 2009 | New 4L Expressway |  | 95.58% | 29.47% |  | 35.65% | 37.29% |  |  | x |  | x | Quality of estimates; ; | There is a typo in the ICR on p. 27. The actual Construction Cost (Million RMB) for Tanjiaqiao-Tongkou section should be 1,387 not 387. ; ;
China | East Asia and Pacific | P076714 | C2 |  | P076714C2 | Estimate | 2003 | Upgrading |  | 243 | 500 | RMB | 60.5327 | 0.24911
China | East Asia and Pacific | P076714 | C2 |  | P076714C2 | Actual | 2009 | Upgrading | 28 | 233.5 | 360.5 | RMB | 52.7818 | 0.22605
China | East Asia and Pacific | P076714 | C1 |  | P076714C2 | Ratio | 2003 / 2009 | Upgrading |  | 96.09% | 72.1% |  | 87.2% | 90.74%
China | East Asia and Pacific | P076714 | C2 | S1 | P076714C2S1 | Estimate | 2003 | Upgrading |  | 74 | 148 | RMB | 17.9177 | 0.24213
China | East Asia and Pacific | P076714 | C2 | S1 | P076714C2S1 | Actual | 2009 | Upgrading | 28 | 74.1 | 98.3 | RMB | 14.3924 | 0.19423
China | East Asia and Pacific | P076714 | C1 |  | P076714C2S1 | Ratio | 2003 / 2009 | Upgrading |  | 100.1% | 66.42% |  | 80.33% | 80.22%
China | East Asia and Pacific | P076714 | C2 | S2 | P076714C2S2 | Estimate | 2003 | Upgrading |  | 35 | 70 | RMB | 8.4746 | 0.24213
China | East Asia and Pacific | P076714 | C2 | S2 | P076714C2S2 | Actual | 2009 | Upgrading | 11 | 39 | 66.4 | RMB | 9.7218 | 0.24928
China | East Asia and Pacific | P076714 | C1 |  | P076714C2S2 | Ratio | 2003 / 2009 | Upgrading |  | 111.4% | 94.86% |  | 114.7% | 103%
China | East Asia and Pacific | P076714 | C2 | S3 | P076714C2S3 | Estimate | 2003 | Upgrading |  | 44 | 88 | RMB | 10.6538 | 0.24213
China | East Asia and Pacific | P076714 | C2 | S3 | P076714C2S3 | Actual | 2009 | Upgrading | 13 | 36.4 | 74.4 | RMB | 10.8931 | 0.29926
China | East Asia and Pacific | P076714 | C1 |  | P076714C2S3 | Ratio | 2003 / 2009 | Upgrading |  | 82.73% | 84.55% |  | 102.2% | 123.6%
China | East Asia and Pacific | P076714 | C2 | S4 | P076714C2S4 | Estimate | 2003 | Upgrading |  | 38 | 90 | RMB | 10.8959 | 0.28673
China | East Asia and Pacific | P076714 | C2 | S4 | P076714C2S4 | Actual | 2009 | Upgrading | 11 | 32.7 | 65.4 | RMB | 9.5754 | 0.29283
China | East Asia and Pacific | P076714 | C1 |  | P076714C2S4 | Ratio | 2003 / 2009 | Upgrading |  | 86.05% | 72.67% |  | 87.88% | 102.1%
China | East Asia and Pacific | P076714 | C2 | S5 | P076714C2S5 | Estimate | 2003 | Upgrading |  | 52 | 104 | RMB | 12.5908 | 0.24213
China | East Asia and Pacific | P076714 | C2 | S5 | P076714C2S5 | Actual | 2009 | Upgrading | 25 | 51.3 | 56 | RMB | 8.1991 | 0.15983
China | East Asia and Pacific | P076714 | C1 |  | P076714C2S5 | Ratio | 2003 / 2009 | Upgrading |  | 98.65% | 53.85% |  | 65.12% | 66.01%
China | East Asia and Pacific | P081749 | C1 |  | P081749C1 | Estimate | 2004 | New 4L Expressway | 36 | 105.1 | 357.69 | USD | 357.69 | 3.4033 |  |  |  | x | x
China | East Asia and Pacific | P081749 | C1 |  | P081749C1 | Actual | 2010 | New 4L Expressway | 36 | 106.4 | 600.1479 | USD | 600.1479 | 5.6405 |  |  |  | x | x
China | East Asia and Pacific | P081749 | C1 |  | P081749C1 | Ratio | 2004 / 2010 | New 4L Expressway | 100% | 101.2% | 167.8% |  | 167.8% | 165.7% |  |  |  | x | x | Weather shocks; Quality of estimates; | extreme weather conditions (exceptionally heavy rains) caused the collapse of some slopes and retaining walls, which also caused increase in construction cost; cost estimates for bid prices were significantly underestimated;
China | East Asia and Pacific | P081749 | C2 | S1 | P081749C2S1 | Estimate | 2004 | Upgrading | 36 | 85.8 | 177.4 | RMB | 21.4251 | 0.24971
China | East Asia and Pacific | P081749 | C2 | S1 | P081749C2S1 | Actual | 2010 | Upgrading | 36 | 85.18 | 150 | RMB | 21.9619 | 0.25783
China | East Asia and Pacific | P081749 | C1 |  | P081749C2S1 | Ratio | 2004 / 2010 | Upgrading | 100% | 99.28% | 84.55% |  | 102.5% | 103.3%
China | East Asia and Pacific | P091020 | C1 |  | P091020C1 | Estimate | 2006 | New 4L Expressway |  | 195 | 733.86 | USD | 733.86 | 3.7634 |  |  |  | x | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C1 | Actual | 2015 | New 4L Expressway |  | 195 | 1164.65 | USD | 1164.65 | 5.9726 |  |  |  | x | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C1 | Ratio | 2006 / 2015 | New 4L Expressway |  | 100% | 158.7% |  | 158.7% | 158.7% |  |  |  | x | x | Weather shocks; Political events; Capacity | A 7 month closure of a 300 meter stretch on one lane in YWE for safety reasons, because the parallel G205 was in danger of a landslide in a deep slope cut and a counterweight had to be placed on an YWE lane to stabilize the slope and to allow consolidation of the G205 embankment.; A 30% shortfall in expected toll revenue due to lower than expected traffic volume on YWE, as a result of the central government’s policy change to remove all tolls on Class II highways.; One sub-grade contract of YWE component was misprocured, because it started without the Bank’s ‘no objection’. The canceled funds, US$13.132 million, were transferred to the Rural Roads component.
China | East Asia and Pacific | P091020 | C2 |  | P091020C2 | Estimate | 2006 | Strengthening |  | 4222.63 | 3297.43 | RMB | 409.6186 | 0.097006 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C2 |  | P091020C2 | Actual | 2015 | Strengthening |  | 10289.94 | 8888.36 | RMB | 1454.7234 | 0.14137 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C2 | Ratio | 2006 / 2015 | Strengthening |  | 243.7% | 269.6% |  | 355.1% | 145.7% |  | x |  |  | x | Capacity; ; | (i) Implementation arrangements were complex, decentralized and appropriate. Implementation arrangements were complex, decentralized and appropriate. The PMO for World Bank Project at FPCD was responsible for the overall coordination and monitoring of implementing agencies, and served as the counterpart to the Bank. Responsibility for procurement and implementation of the YWE component rested under the Fujian Provincial Expressway Construction Directorate (FPECD), and the Longyan YWE Company and Sanming YWE Company established with capital from FPECD and the two municipalities. The two municipalities were in charge of resettlement implementation. This was a mammoth project: an expressway in a challenging topographical environment with 117 bridges (36 km), 32 tunnels (29 km), constituting 34% of its length. (ii) Given the meticulous preparation, the construction of the complex and costly Expressway was managed well and opened three months ahead of schedule. (iii) Training was key to successful implementation. Important international training addressed project management and toll road operations, financing, tunneling, supervision and new pavement technologies; however, some planned international study tours had to be canceled because of a change in national policy on overseas study tours. There were also domestic trainings on cement pavement maintenance technology for rural roads, bridge maintenance technology and management, and management of rural road construction. Training enhanced the technical capacity of local road maintenance staff, and played an important part in sustaining the long term impact of the project. On average, 95% of participants rated training as satisfactory.; ;
China | East Asia and Pacific | P091020 | C2 | S1 | P091020C2S1 | Estimate | 2006 | Strengthening |  | 489.44 | 307.18 | RMB | 38.159 | 0.077965 |  | x |  | x | x
China | East Asia and Pacific | P091020 | C2 | S1 | P091020C2S1 | Actual | 2015 | Strengthening |  | 1757.41 | 1622.89 | RMB | 265.6121 | 0.15114 |  | x |  | x | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C2S1 | Ratio | 2006 / 2015 | Strengthening |  | 359.1% | 528.3% |  | 696.1% | 193.9% |  | x |  | x | x | Change of project scope; ; | Additional financing to build 61 more roads. Specifically for Fuzhou section, additional 283.29 milliom RMB were allocated. ; ;
China | East Asia and Pacific | P091020 | C2 | S2 | P091020C2S2 | Estimate | 2006 | Strengthening |  | 566.95 | 656.21 | RMB | 81.5168 | 0.14378 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C2 | S2 | P091020C2S2 | Actual | 2015 | Strengthening |  | 1246.53 | 1328.55 | RMB | 217.4386 | 0.17444 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C2S2 | Ratio | 2006 / 2015 | Strengthening |  | 219.9% | 202.5% |  | 266.7% | 121.3% |  | x |  |  | x | Capacity; ; | (i) Implementation arrangements were complex, decentralized and appropriate. Implementation arrangements were complex, decentralized and appropriate. The PMO for World Bank Project at FPCD was responsible for the overall coordination and monitoring of implementing agencies, and served as the counterpart to the Bank. Responsibility for procurement and implementation of the YWE component rested under the Fujian Provincial Expressway Construction Directorate (FPECD), and the Longyan YWE Company and Sanming YWE Company established with capital from FPECD and the two municipalities. The two municipalities were in charge of resettlement implementation. This was a mammoth project: an expressway in a challenging topographical environment with 117 bridges (36 km), 32 tunnels (29 km), constituting 34% of its length. (ii) Given the meticulous preparation, the construction of the complex and costly Expressway was managed well and opened three months ahead of schedule. (iii) Training was key to successful implementation. Important international training addressed project management and toll road operations, financing, tunneling, supervision and new pavement technologies; however, some planned international study tours had to be canceled because of a change in national policy on overseas study tours. There were also domestic trainings on cement pavement maintenance technology for rural roads, bridge maintenance technology and management, and management of rural road construction. Training enhanced the technical capacity of local road maintenance staff, and played an important part in sustaining the long term impact of the project. On average, 95% of participants rated training as satisfactory.; ;
China | East Asia and Pacific | P091020 | C2 | S3 | P091020C2S3 | Estimate | 2006 | Strengthening |  | 1421.22 | 1046.25 | RMB | 129.9689 | 0.091449 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C2 | S3 | P091020C2S3 | Actual | 2015 | Strengthening |  | 2387.44 | 1872.56 | RMB | 306.4746 | 0.12837 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C2S3 | Ratio | 2006 / 2015 | Strengthening |  | 168% | 179% |  | 235.8% | 140.4% |  | x |  |  | x | Capacity; ; | (i) Implementation arrangements were complex, decentralized and appropriate. Implementation arrangements were complex, decentralized and appropriate. The PMO for World Bank Project at FPCD was responsible for the overall coordination and monitoring of implementing agencies, and served as the counterpart to the Bank. Responsibility for procurement and implementation of the YWE component rested under the Fujian Provincial Expressway Construction Directorate (FPECD), and the Longyan YWE Company and Sanming YWE Company established with capital from FPECD and the two municipalities. The two municipalities were in charge of resettlement implementation. This was a mammoth project: an expressway in a challenging topographical environment with 117 bridges (36 km), 32 tunnels (29 km), constituting 34% of its length. (ii) Given the meticulous preparation, the construction of the complex and costly Expressway was managed well and opened three months ahead of schedule. (iii) Training was key to successful implementation. Important international training addressed project management and toll road operations, financing, tunneling, supervision and new pavement technologies; however, some planned international study tours had to be canceled because of a change in national policy on overseas study tours. There were also domestic trainings on cement pavement maintenance technology for rural roads, bridge maintenance technology and management, and management of rural road construction. Training enhanced the technical capacity of local road maintenance staff, and played an important part in sustaining the long term impact of the project. On average, 95% of participants rated training as satisfactory.; ;
China | East Asia and Pacific | P091020 | C2 | S4 | P091020C2S4 | Estimate | 2006 | Strengthening |  | 574.08 | 441.63 | RMB | 54.8609 | 0.095563 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C2 | S4 | P091020C2S4 | Actual | 2015 | Strengthening |  | 1623.34 | 1349.35 | RMB | 220.8429 | 0.13604 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C2S4 | Ratio | 2006 / 2015 | Strengthening |  | 282.8% | 305.5% |  | 402.6% | 142.4% |  | x |  |  | x | Capacity; ; | (i) Implementation arrangements were complex, decentralized and appropriate. Implementation arrangements were complex, decentralized and appropriate. The PMO for World Bank Project at FPCD was responsible for the overall coordination and monitoring of implementing agencies, and served as the counterpart to the Bank. Responsibility for procurement and implementation of the YWE component rested under the Fujian Provincial Expressway Construction Directorate (FPECD), and the Longyan YWE Company and Sanming YWE Company established with capital from FPECD and the two municipalities. The two municipalities were in charge of resettlement implementation. This was a mammoth project: an expressway in a challenging topographical environment with 117 bridges (36 km), 32 tunnels (29 km), constituting 34% of its length. (ii) Given the meticulous preparation, the construction of the complex and costly Expressway was managed well and opened three months ahead of schedule. (iii) Training was key to successful implementation. Important international training addressed project management and toll road operations, financing, tunneling, supervision and new pavement technologies; however, some planned international study tours had to be canceled because of a change in national policy on overseas study tours. There were also domestic trainings on cement pavement maintenance technology for rural roads, bridge maintenance technology and management, and management of rural road construction. Training enhanced the technical capacity of local road maintenance staff, and played an important part in sustaining the long term impact of the project. On average, 95% of participants rated training as satisfactory.; ;
China | East Asia and Pacific | P091020 | C2 | S5 | P091020C2S5 | Estimate | 2006 | Strengthening |  | 671.13 | 458.18 | RMB | 56.9168 | 0.084807 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C2 | S5 | P091020C2S5 | Actual | 2015 | Strengthening |  | 1458.57 | 1086.86 | RMB | 177.8822 | 0.12196 |  | x |  |  | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C2S5 | Ratio | 2006 / 2015 | Strengthening |  | 217.3% | 237.2% |  | 312.5% | 143.8% |  | x |  |  | x | Capacity; ; | (i) Implementation arrangements were complex, decentralized and appropriate. Implementation arrangements were complex, decentralized and appropriate. The PMO for World Bank Project at FPCD was responsible for the overall coordination and monitoring of implementing agencies, and served as the counterpart to the Bank. Responsibility for procurement and implementation of the YWE component rested under the Fujian Provincial Expressway Construction Directorate (FPECD), and the Longyan YWE Company and Sanming YWE Company established with capital from FPECD and the two municipalities. The two municipalities were in charge of resettlement implementation. This was a mammoth project: an expressway in a challenging topographical environment with 117 bridges (36 km), 32 tunnels (29 km), constituting 34% of its length. (ii) Given the meticulous preparation, the construction of the complex and costly Expressway was managed well and opened three months ahead of schedule. (iii) Training was key to successful implementation. Important international training addressed project management and toll road operations, financing, tunneling, supervision and new pavement technologies; however, some planned international study tours had to be canceled because of a change in national policy on overseas study tours. There were also domestic trainings on cement pavement maintenance technology for rural roads, bridge maintenance technology and management, and management of rural road construction. Training enhanced the technical capacity of local road maintenance staff, and played an important part in sustaining the long term impact of the project. On average, 95% of participants rated training as satisfactory.; ;
China | East Asia and Pacific | P091020 | C2 | S6 | P091020C2S6 | Estimate | 2006 | Strengthening |  | 265.63 | 191.21 | RMB | 23.7528 | 0.089421 |  | x |  | x | x
China | East Asia and Pacific | P091020 | C2 | S6 | P091020C2S6 | Actual | 2015 | Strengthening |  | 1293.62 | 1125.8 | RMB | 184.2553 | 0.14243 |  | x |  | x | x
China | East Asia and Pacific | P091020 | C1 |  | P091020C2S6 | Ratio | 2006 / 2015 | Strengthening |  | 487% | 588.8% |  | 775.7% | 159.3% |  | x |  | x | x | Change of project scope; ; | Additional financing to build 50 more roads. Specifically for Ningde section, additional 220.03 milliom RMB were allocated. ; ;
China | East Asia and Pacific | P091020 | C2 | S7 | P091020C2S7 | Estimate | 2006 | Strengthening |  | 234.18 | 196.76 | RMB | 24.4422 | 0.10437
China | East Asia and Pacific | P091020 | C2 | S7 | P091020C2S7 | Actual | 2015 | Strengthening |  | 319.15 | 271.62 | RMB | 44.455 | 0.13929
China | East Asia and Pacific | P091020 | C1 |  | P091020C2S7 | Ratio | 2006 / 2015 | Strengthening |  | 136.3% | 138% |  | 181.9% | 133.5%
China | East Asia and Pacific | P099112 | C1 |  | P099112C1 | Estimate | 2008 | Strengthening | 36 | 885.6 | 162.837 | USD | 162.837 | 0.18387
China | East Asia and Pacific | P099112 | C1 |  | P099112C1 | Actual | 2012 | Strengthening | 33 | 840.845 | 191.219 | USD | 191.219 | 0.22741
China | East Asia and Pacific | P099112 | C1 |  | P099112C1 | Ratio | 2008 / 2012 | Strengthening | 91.67% | 94.95% | 117.4% |  | 117.4% | 123.7%
China | East Asia and Pacific | P099112 | C2 |  | P099112C2 | Estimate | 2008 | Upgrading |  | 320 | 166.313 | USD | 166.313 | 0.51973
China | East Asia and Pacific | P099112 | C2 |  | P099112C2 | Actual | 2012 | Upgrading | 34 | 320.6 | 214.771 | USD | 214.771 | 0.6699
China | East Asia and Pacific | P099112 | C1 |  | P099112C2 | Ratio | 2008 / 2012 | Upgrading |  | 100.2% | 129.1% |  | 129.1% | 128.9%
China | East Asia and Pacific | P099992 | C1 |  | P099992C1 | Estimate | 2006 | Widening and Reconstruction |  | 179 | 330.93 | USD | 330.93 | 1.8488
China | East Asia and Pacific | P099992 | C1 |  | P099992C1 | Actual | 2014 | Widening and Reconstruction |  | 107 | 161.66 | USD | 161.66 | 1.5108
China | East Asia and Pacific | P099992 | C1 |  | P099992C1 | Ratio | 2006 / 2014 | Widening and Reconstruction |  | 59.78% | 48.85% |  | 48.85% | 81.72%
China | East Asia and Pacific | P058844 | C1 |  | P058844C1 | Estimate | 2000 | New 4L Expressway | 25 | 95 | 294.8 | USD | 294.8 | 3.1032
China | East Asia and Pacific | P058844 | C1 |  | P058844C1 | Actual | 2007 | New 4L Expressway | 37 | 95 | 267.5 | USD | 267.5 | 2.8158
China | East Asia and Pacific | P058844 | C1 |  | P058844C1 | Ratio | 2000 / 2007 | New 4L Expressway | 148% | 100% | 90.74% |  | 90.74% | 90.74%
China | East Asia and Pacific | P058844 | C2 |  | P058844C2 | Estimate | 2000 | Upgrading |  | 400 | 43.9 | USD | 43.9 | 0.10975
China | East Asia and Pacific | P058844 | C2 |  | P058844C2 | Actual | 2007 | Upgrading |  | 373 | 38.9 | USD | 38.9 | 0.10429
China | East Asia and Pacific | P058844 | C1 |  | P058844C2 | Ratio | 2000 / 2007 | Upgrading |  | 93.25% | 88.61% |  | 88.61% | 95.02%
China | East Asia and Pacific | P058847 | C1 |  | P058847C1 | Estimate | 2002 | Widening and Reconstruction |  | 302.6 | 211.39 | USD | 211.39 | 0.69858
China | East Asia and Pacific | P058847 | C1 |  | P058847C1 | Actual | 2010 | Widening and Reconstruction |  | 302.6 | 278.52 | USD | 278.52 | 0.92042
China | East Asia and Pacific | P058847 | C1 |  | P058847C1 | Ratio | 2002 / 2010 | Widening and Reconstruction |  | 100% | 131.8% |  | 131.8% | 131.8%
China | East Asia and Pacific | P058847 | C2 |  | P058847C2 | Estimate | 2002 | Upgrading |  | 600 | 41.8 | USD | 41.8 | 0.069667
China | East Asia and Pacific | P058847 | C2 |  | P058847C2 | Actual | 2010 | Upgrading |  | 620 | 51.84 | USD | 51.84 | 0.083613
China | East Asia and Pacific | P058847 | C1 |  | P058847C2 | Ratio | 2002 / 2010 | Upgrading |  | 103.3% | 124% |  | 124% | 120%
China | East Asia and Pacific | P068752 | C1 |  | P068752C1 | Estimate | 2005 | Widening and Reconstruction | 36 | 177 | 172.69 | USD | 172.69 | 0.97565
China | East Asia and Pacific | P068752 | C1 |  | P068752C1 | Actual | 2011 | Widening and Reconstruction | 30 | 178.73 | 214.53 | USD | 214.53 | 1.2003
China | East Asia and Pacific | P068752 | C1 |  | P068752C1 | Ratio | 2005 / 2011 | Widening and Reconstruction | 83.33% | 101% | 124.2% |  | 124.2% | 123%
China | East Asia and Pacific | P068752 | C2 |  | P068752C2 | Estimate | 2005 | Upgrading |  | 431 | 51.3 | USD | 51.3 | 0.11903 |  | x |  |  | x
China | East Asia and Pacific | P068752 | C2 |  | P068752C2 | Actual | 2011 | Upgrading |  | 690 | 117.02 | USD | 117.02 | 0.16959 |  | x |  |  | x
China | East Asia and Pacific | P068752 | C1 |  | P068752C2 | Ratio | 2005 / 2011 | Upgrading |  | 160.1% | 228.1% |  | 228.1% | 142.5% |  | x |  |  | x | Change of project scope; ; | the change in the length of civil works resulted from lower initial price contract ; ;
China | East Asia and Pacific | P068752 | C2 | S1 | P068752C2S1 | Estimate | 2005 | Upgrading | 24 | 70.5 | 109.54 | CNY | 13.2295 | 0.18765
China | East Asia and Pacific | P068752 | C2 | S1 | P068752C2S1 | Actual | 2011 | Upgrading | 24 | 74.2 | 132.9 | CNY | 18.331 | 0.24705
China | East Asia and Pacific | P068752 | C1 |  | P068752C2S1 | Ratio | 2005 / 2011 | Upgrading | 100% | 105.2% | 121.3% |  | 138.6% | 131.7%
China | East Asia and Pacific | P068752 | C2 | S2 | P068752C2S2 | Estimate | 2005 | Upgrading | 18 | 138 | 134.95 | CNY | 16.2983 | 0.1181
China | East Asia and Pacific | P068752 | C2 | S2 | P068752C2S2 | Actual | 2011 | Upgrading | 18 | 135.9 | 128.2 | CNY | 17.6828 | 0.13012
China | East Asia and Pacific | P068752 | C1 |  | P068752C2S2 | Ratio | 2005 / 2011 | Upgrading | 100% | 98.48% | 95% |  | 108.5% | 110.2%
China | East Asia and Pacific | P068752 | C2 | S3 | P068752C2S3 | Estimate | 2005 | Upgrading | 18 | 103 | 88.43 | CNY | 10.68 | 0.10369 |  |  |  | x | x
China | East Asia and Pacific | P068752 | C2 | S3 | P068752C2S3 | Actual | 2011 | Upgrading | 30 | 118 | 230.4 | CNY | 31.7793 | 0.26932 |  |  |  | x | x
China | East Asia and Pacific | P068752 | C1 |  | P068752C2S3 | Ratio | 2005 / 2011 | Upgrading | 166.7% | 114.6% | 260.5% |  | 297.6% | 259.7% |  |  |  | x | x | Weather shocks ; Quality of estimates; | higher costs were incurred due to delays caused by poor weather conditions; differences between actual geological conditions and those adopted in design drawings ;
China | East Asia and Pacific | P068752 | C2 | S4 | P068752C2S4 | Estimate | 2005 | Upgrading | 18 | 82.5 | 44.01 | CNY | 5.3152 | 0.064427 |  |  |  | x | x
China | East Asia and Pacific | P068752 | C2 | S4 | P068752C2S4 | Actual | 2011 | Upgrading | 18 | 81.7 | 69.8 | CNY | 9.6276 | 0.11784 |  |  |  | x | x
China | East Asia and Pacific | P068752 | C1 |  | P068752C2S4 | Ratio | 2005 / 2011 | Upgrading | 100% | 99.03% | 158.6% |  | 181.1% | 182.9% |  |  |  | x | x | Weather shocks ; Quality of estimates; | higher costs were incurred due to delays caused by poor weather conditions; differences between actual geological conditions and those adopted in design drawings ;
China | East Asia and Pacific | P068752 | C2 | S5 | P068752C2S5 | Estimate | 2005 | Upgrading | 12 | 19.3 | 16.43 | CNY | 1.9843 | 0.10281
China | East Asia and Pacific | P068752 | C2 | S5 | P068752C2S5 | Actual | 2011 | Upgrading | 12 | 21.5 | 16.9 | CNY | 2.331 | 0.10842
China | East Asia and Pacific | P068752 | C1 |  | P068752C2S5 | Ratio | 2005 / 2011 | Upgrading | 100% | 111.4% | 102.9% |  | 117.5% | 105.5%
China | East Asia and Pacific | P069852 | C2 |  | P069852C2 | Estimate | 2004 | Reconstruction |  | 74.33 | 36.2 | USD | 36.2 | 0.48702
China | East Asia and Pacific | P069852 | C2 |  | P069852C2 | Actual | 2010 | Reconstruction |  | 70.83 | 51.71 | USD | 51.71 | 0.73006
China | East Asia and Pacific | P069852 | C1 |  | P069852C2 | Ratio | 2004 / 2010 | Reconstruction |  | 95.29% | 142.8% |  | 142.8% | 149.9%
China | East Asia and Pacific | P070441 | C1 |  | P070441C1 | Estimate | 2002 | New 4L Expressway | 66 | 243.5 | 505.6 | USD | 505.6 | 2.0764 |  |  |  | x | x
China | East Asia and Pacific | P070441 | C1 |  | P070441C1 | Actual | 2008 | New 4L Expressway | 66 | 243.5 | 802.61 | USD | 802.61 | 3.2961 |  |  |  | x | x
China | East Asia and Pacific | P070441 | C1 |  | P070441C1 | Ratio | 2002 / 2008 | New 4L Expressway | 100% | 100% | 158.7% |  | 158.7% | 158.7% |  |  |  | x | x | Quality of estimates; Macroeconomic conditions; Capacity of contractor | actual construction costs (excluding resettlement) were about 32% higher than the estimates; over the course of the project there was a 13.3% devaluation in the USD against the Chinese RMB; procurement cost overruns of under 15%
China | East Asia and Pacific | P070441 | C2 |  | P070441C2 | Estimate | 2002 | Upgrading |  | 259 | 66.2 | USD | 66.2 | 0.2556
China | East Asia and Pacific | P070441 | C2 |  | P070441C2 | Actual | 2008 | Upgrading |  | 259 | 42 | USD | 42 | 0.16216
China | East Asia and Pacific | P070441 | C1 |  | P070441C2 | Ratio | 2002 / 2008 | Upgrading |  | 100% | 63.44% |  | 63.44% | 63.44%
China | East Asia and Pacific | P070459 | C1 |  | P070459C1 | Estimate | 2002 | New 4L Expressway |  | 90 | 185.79 | USD | 185.79 | 2.0643
China | East Asia and Pacific | P070459 | C1 |  | P070459C1 | Actual | 2008 | New 4L Expressway |  | 90 | 169.05 | USD | 169.05 | 1.8783
China | East Asia and Pacific | P070459 | C1 |  | P070459C1 | Ratio | 2002 / 2008 | New 4L Expressway |  | 100% | 90.99% |  | 90.99% | 90.99%
China | East Asia and Pacific | P070459 | C2 |  | P070459C2 | Estimate | 2002 | Upgrading |  | 343 | 61.1 | USD | 61.1 | 0.17813 |  | x |  |  | x
China | East Asia and Pacific | P070459 | C2 |  | P070459C2 | Actual | 2008 | Upgrading |  | 664 | 81.65 | USD | 81.65 | 0.12297 |  | x |  |  | x
China | East Asia and Pacific | P070459 | C1 |  | P070459C2 | Ratio | 2002 / 2008 | Upgrading |  | 193.6% | 133.6% |  | 133.6% | 69.03% |  | x |  |  | x | Change of project scope; ; | the interconnecting roads were upgraded to four-lane roads as opposed to two-lane roads as agreed at the time of appraisal ; ;
China | East Asia and Pacific | P070459 | C2 | S1 | P070459C2S1 | Estimate | 2002 | Upgrading |  | 70 | 80 | CNY | 9.6386 | 0.13769
China | East Asia and Pacific | P070459 | C2 | S1 | P070459C2S1 | Actual | 2008 | Upgrading |  | 70 | 76.4 | CNY | 9.2271 | 0.13182
China | East Asia and Pacific | P070459 | C1 |  | P070459C2S1 | Ratio | 2002 / 2008 | Upgrading |  | 100% | 95.5% |  | 95.73% | 95.73%
China | East Asia and Pacific | P070459 | C2 | S2 | P070459C2S2 | Estimate | 2002 | Upgrading |  | 54 | 55 | CNY | 6.6265 | 0.12271
China | East Asia and Pacific | P070459 | C2 | S2 | P070459C2S2 | Actual | 2008 | Upgrading |  | 54 | 43.8 | CNY | 5.2899 | 0.09796
China | East Asia and Pacific | P070459 | C1 |  | P070459C2S2 | Ratio | 2002 / 2008 | Upgrading |  | 100% | 79.64% |  | 79.83% | 79.83%
China | East Asia and Pacific | P070459 | C2 | S3 | P070459C2S3 | Estimate | 2002 | Upgrading |  | 86 | 100 | CNY | 12.0482 | 0.1401
China | East Asia and Pacific | P070459 | C2 | S3 | P070459C2S3 | Actual | 2008 | Upgrading |  | 86 | 51.2 | CNY | 6.1836 | 0.071902
China | East Asia and Pacific | P070459 | C1 |  | P070459C2S3 | Ratio | 2002 / 2008 | Upgrading |  | 100% | 51.2% |  | 51.32% | 51.32%
China | East Asia and Pacific | P070459 | C2 | S4 | P070459C2S4 | Estimate | 2002 | Upgrading |  | 48 | 70 | CNY | 8.4337 | 0.1757
China | East Asia and Pacific | P070459 | C2 | S4 | P070459C2S4 | Actual | 2008 | Upgrading |  | 48 | 68.8 | CNY | 8.3092 | 0.17311
China | East Asia and Pacific | P070459 | C1 |  | P070459C2S4 | Ratio | 2002 / 2008 | Upgrading |  | 100% | 98.29% |  | 98.52% | 98.52%
China | East Asia and Pacific | P075613 | C1 |  | P075613C1 | Estimate | 2007 | New 4L Expressway |  | 87 | 561.24 | USD | 561.24 | 6.451 |  |  |  | x | x
China | East Asia and Pacific | P075613 | C1 |  | P075613C1 | Actual | 2013 | New 4L Expressway |  | 87 | 1096.66 | USD | 1096.66 | 12.6053 |  |  |  | x | x
China | East Asia and Pacific | P075613 | C1 |  | P075613C1 | Ratio | 2007 / 2013 | New 4L Expressway |  | 100% | 195.4% |  | 195.4% | 195.4% |  |  |  | x | x | Macroeconomic conditions; ; | high inflation of labor and fuel prices ; ;
China | East Asia and Pacific | P075613 | C2 |  | P075613C2 | Estimate | 2007 | Upgrading |  | 1480 | 47.22 | USD | 47.22 | 0.031905 |  |  |  | x | x
China | East Asia and Pacific | P075613 | C2 |  | P075613C2 | Actual | 2013 | Upgrading |  | 1480 | 77.59 | USD | 77.59 | 0.052426 |  |  |  | x | x
China | East Asia and Pacific | P075613 | C1 |  | P075613C2 | Ratio | 2007 / 2013 | Upgrading |  | 100% | 164.3% |  | 164.3% | 164.3% |  |  |  | x | x | Macroeconomic conditions; ; | high inflation of labor and fuel prices ; ;
China | East Asia and Pacific | P093906 | C1 |  | P093906C1 | Estimate | 2006 | New 4L Expressway |  | 117.1 | 627 | USD | 627 | 5.3544
China | East Asia and Pacific | P093906 | C1 |  | P093906C1 | Actual | 2011 | New 4L Expressway |  | 117.1 | 715.06 | USD | 715.06 | 6.1064
China | East Asia and Pacific | P093906 | C1 |  | P093906C1 | Ratio | 2006 / 2011 | New 4L Expressway |  | 100% | 114% |  | 114% | 114%
China | East Asia and Pacific | P093906 | C2 |  | P093906C2 | Estimate | 2006 | Upgrading |  | 83.3 | 74 | USD | 74 | 0.88836 | x |  | x |  | x
China | East Asia and Pacific | P093906 | C2 |  | P093906C2 | Actual | 2011 | Upgrading |  | 39 | 16.7 | USD | 16.7 | 0.42821 | x |  | x |  | x
China | East Asia and Pacific | P093906 | C1 |  | P093906C2 | Ratio | 2006 / 2011 | Upgrading |  | 46.82% | 22.57% |  | 22.57% | 48.2% | x |  | x |  | x | Change of project scope; Political events; Procurement system | Problems with counterpart financing, resulting from the Jiangxi RRIP program led to reducing the scope of the LRIP componen; Implementation was further complicated by the selection and later replacement by Ganzhou local government, of LRIP roads (Meilin-Longbu replaced by Anyuan-Dingnan road, and Chongyi-Longgou replaced by Xinjeng-Chijiang road, although the latter replacement was too late for implementation within the project timeframe). ; Misprocurement by the Guangzhou City Prefecture led to the cancellation of the Chongyi-Longgou.
China | East Asia and Pacific | P101258 | C1 |  | P101258C1 | Estimate | 2009 | New 4L Expressway | 40 | 173.6 | 1687.83 | USD | 1687.83 | 9.7225
China | East Asia and Pacific | P101258 | C1 |  | P101258C1 | Actual | 2016 | New 4L Expressway |  | 173.6 | 2000.66 | USD | 2000.66 | 11.5245
China | East Asia and Pacific | P101258 | C1 |  | P101258C1 | Ratio | 2009 / 2016 | New 4L Expressway |  | 100% | 118.5% |  | 118.5% | 118.5%
China | East Asia and Pacific | Project number: 42017-013 | C1 | S1 | Project number: 42017-013C1S1 | Estimate | 2010 | New 4L Expressway |  | 206.26 | 468.87 | CNY | 69.257 | 0.33578
China | East Asia and Pacific | Project number: 42017-013 | C1 | S1 | Project number: 42017-013C1S1 | Actual | 2016 | New 4L Expressway |  | 206.26 | 571.26 | CNY | 86.0331 | 0.41711
China | East Asia and Pacific | Project number: 42017-013 | C1 |  | Project number: 42017-013C1S1 | Ratio | 2010 / 2016 | New 4L Expressway |  | 100% | 121.8% |  | 124.2% | 124.2%
China | East Asia and Pacific | Project number: 42017-013 | C1 | S2 | Project number: 42017-013C1S2 | Estimate | 2010 | Upgrading |  | 127.92 | 41.15 | CNY | 6.0783 | 0.047516
China | East Asia and Pacific | Project number: 42017-013 | C1 | S2 | Project number: 42017-013C1S2 | Actual | 2016 | Upgrading |  | 127.92 | 47.25 | CNY | 7.116 | 0.055628
China | East Asia and Pacific | Project number: 42017-013 | C1 |  | Project number: 42017-013C1S2 | Ratio | 2010 / 2016 | Upgrading |  | 100% | 114.8% |  | 117.1% | 117.1%
China | East Asia and Pacific | Project number: 42017-013 | C1 | S3 | Project number: 42017-013C1S3 | Estimate | 2010 | New 2L Highway |  | 12.88 | 78.91 | CNY | 11.6558 | 0.90496
China | East Asia and Pacific | Project number: 42017-013 | C1 | S3 | Project number: 42017-013C1S3 | Actual | 2016 | New 2L Highway |  | 12.88 | 99.11 | CNY | 14.9262 | 1.1589
China | East Asia and Pacific | Project number: 42017-013 | C1 |  | Project number: 42017-013C1S3 | Ratio | 2010 / 2016 | New 2L Highway |  | 100% | 125.6% |  | 128.1% | 128.1%
Congo, Dem. Rep. | Sub-Saharan Africa | P057296 | C1 |  | P057296C1 | Estimate | 2007 | Strengthening | 21 | 1256 | 144 | USD | 144 | 0.11465 |  |  |  | x | x
Congo, Dem. Rep. | Sub-Saharan Africa | P057296 | C1 |  | P057296C1 | Actual | 2010 | Strengthening | 72 | 1047 | 207 | USD | 207 | 0.19771 |  |  |  | x | x
Congo, Dem. Rep. | Sub-Saharan Africa | P057296 | C1 |  | P057296C1 | Ratio | 2007 / 2010 | Strengthening | 342.9% | 83.36% | 143.8% |  | 143.8% | 172.4% |  |  |  | x | x | Political events ; Quality of estimates ; Capacity of counterpart | the DRC was emerging from one of the worst, largest and most complex conflicts in post-colonial Africa which had destroyed public institutions and the capacity of the government to execute development programs and projects; difficulty in making detailed and accurate assessments in the country at the time; asset conditions turned out to be worse than originally assessed ; lack of familiarity of the DRC government with the Bank's guidelines and procedures; difficulties in attracting reliable contractors; weak status of public finances
Croatia | Europe and Central Asia | P043195 | C3 |  | P043195C3 | Estimate | 2003 | New 4L Expressway | 30 | 6.5 | 87.8 | USD | 87.8 | 13.5077
Croatia | Europe and Central Asia | P043195 | C3 |  | P043195C3 | Actual | 2013 | New 4L Expressway | 39 | 6.36 | 117.4 | USD | 117.4 | 18.4591
Croatia | Europe and Central Asia | P043195 | C1 |  | P043195C3 | Ratio | 2003 / 2013 | New 4L Expressway | 130% | 97.85% | 133.7% |  | 133.7% | 136.7%
Djibouti | Middle East and North Africa | P069930 | C1 |  | P069930C1 | Estimate | 2000 | Reconstruction | 12 | 102 | 12 | USD | 12 | 0.11765
Djibouti | Middle East and North Africa | P069930 | C1 |  | P069930C1 | Actual | 2006 | Reconstruction | 18 | 98 | 13.7 | USD | 13.7 | 0.1398
Djibouti | Middle East and North Africa | P069930 | C1 |  | P069930C1 | Ratio | 2000 / 2006 | Reconstruction | 150% | 96.08% | 114.2% |  | 114.2% | 118.8%
Djibouti | Middle East and North Africa | P069930 | C2 |  | P069930C2 | Estimate | 2000 | Asphalt Mix Resurfacing | 12 | 86 | 2 | USD | 2 | 0.023256
Djibouti | Middle East and North Africa | P069930 | C2 |  | P069930C2 | Actual | 2006 | Asphalt Mix Resurfacing | 12 | 88 | 2.95 | USD | 2.95 | 0.033523
Djibouti | Middle East and North Africa | P069930 | C1 |  | P069930C2 | Ratio | 2000 / 2006 | Asphalt Mix Resurfacing | 100% | 102.3% | 147.5% |  | 147.5% | 144.1%
Estonia | Europe and Central Asia | P035775 | C1 |  | P035775C1 | Estimate | 2000 | Reconstruction |  | 176 | 43.3 | USD | 43.3 | 0.24602
Estonia | Europe and Central Asia | P035775 | C1 |  | P035775C1 | Actual | 2005 | Reconstruction |  | 240 | 49.29 | USD | 49.29 | 0.20538
Estonia | Europe and Central Asia | P035775 | C1 |  | P035775C1 | Ratio | 2000 / 2005 | Reconstruction |  | 136.4% | 113.8% |  | 113.8% | 83.48%
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S1 | P044613C1S1 | Estimate | 2003 | Upgrading | 36 | 127 | 35.02 | USD | 35.02 | 0.27575
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S1 | P044613C1S1 | Actual | 2010 | Upgrading | 51 | 127 | 49.72 | USD | 49.72 | 0.3915
Ethiopia | Sub-Saharan Africa | P044613 | C1 |  | P044613C1S1 | Ratio | 2003 / 2010 | Upgrading | 141.7% | 100% | 142% |  | 142% | 142%
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S2 | P044613C1S2 | Estimate | 2003 | Asphalt Mix Resurfacing | 36 | 79 | 19.35 | USD | 19.35 | 0.24494 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S2 | P044613C1S2 | Actual | 2010 | Asphalt Mix Resurfacing | 41 | 79 | 29.13 | USD | 29.13 | 0.36873 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P044613 | C1 |  | P044613C1S2 | Ratio | 2003 / 2010 | Asphalt Mix Resurfacing | 113.9% | 100% | 150.5% |  | 150.5% | 150.5% |  |  |  | x | x | Macroeconomic conditions ; ; | higher costs were incurred due to historical exchange rates of the SDR; ;
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S3 | P044613C1S3 | Estimate | 2003 | Upgrading | 36 | 98.9 | 24.11 | USD | 24.11 | 0.24378
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S3 | P044613C1S3 | Actual | 2010 | Upgrading | 42 | 98.9 | 33.33 | USD | 33.33 | 0.33701
Ethiopia | Sub-Saharan Africa | P044613 | C1 |  | P044613C1S3 | Ratio | 2003 / 2010 | Upgrading | 116.7% | 100% | 138.2% |  | 138.2% | 138.2%
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S4 | P044613C1S4 | Estimate | 2003 | Upgrading | 36 | 108 | 24.74 | USD | 24.74 | 0.22907 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S4 | P044613C1S4 | Actual | 2010 | Upgrading | 56 | 108 | 43.75 | USD | 43.75 | 0.40509 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P044613 | C1 |  | P044613C1S4 | Ratio | 2003 / 2010 | Upgrading | 155.6% | 100% | 176.8% |  | 176.8% | 176.8% |  |  |  | x | x | Macroeconomic conditions ; ; | higher costs were incurred due to historical exchange rates of the SDR ; ;
Ethiopia | Sub-Saharan Africa | P044613 | C2 |  | P044613C2 | Estimate | 2003 | New 1L Road | 36 | 119.4 | 28.66 | USD | 28.66 | 0.24003
Ethiopia | Sub-Saharan Africa | P044613 | C2 |  | P044613C2 | Actual | 2010 | New 1L Road | 42 | 99 | 19.43 | USD | 19.43 | 0.19626
Ethiopia | Sub-Saharan Africa | P044613 | C1 |  | P044613C2 | Ratio | 2003 / 2010 | New 1L Road | 116.7% | 82.91% | 67.79% |  | 67.79% | 81.76%
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S1 | P082998C1S1 | Estimate | 2004 | Upgrading | 49 | 316 | 62.04 | USD | 62.04 | 0.19633 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S1 | P082998C1S1 | Actual | 2012 | Upgrading |  | 246 | 196.53 | USD | 196.53 | 0.7989 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 |  | P082998C1S1 | Ratio | 2004 / 2012 | Upgrading |  | 77.85% | 316.8% |  | 316.8% | 406.9% |  |  |  | x | x | Quality of estimates; Change of project scope; | Disparity between the engineer’s estimate and the bids.; The cost increases resulted from variation orders and changes in design/correction of design errors and the associated impact on price adjustments.;
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S2 | P082998C1S2 | Estimate | 2004 | Upgrading | 48 | 86 | 20 | USD | 20 | 0.23256 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S2 | P082998C1S2 | Actual | 2012 | Upgrading |  | 86 | 48.69 | USD | 48.69 | 0.56616 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 |  | P082998C1S2 | Ratio | 2004 / 2012 | Upgrading |  | 100% | 243.4% |  | 243.4% | 243.4% |  |  |  | x | x | Quality of estimates; Change of project scope; | Disparity between the engineer’s estimate and the bids.; The cost increases resulted from variation orders and changes in design/correction of design errors and the associated impact on price adjustments.;
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S3 | P082998C1S3 | Estimate | 2004 | Upgrading | 48 | 108 | 25.02 | USD | 25.02 | 0.23167 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S3 | P082998C1S3 | Actual | 2012 | Upgrading |  | 108 | 79.18 | USD | 79.18 | 0.73315 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 |  | P082998C1S3 | Ratio | 2004 / 2012 | Upgrading |  | 100% | 316.5% |  | 316.5% | 316.5% |  |  |  | x | x | Quality of estimates; Change of project scope; | Disparity between the engineer’s estimate and the bids.; The cost increases resulted from variation orders and changes in design/correction of design errors and the associated impact on price adjustments.;
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S4 | P082998C1S4 | Estimate | 2004 | Upgrading | 32 | 83 | 25.46 | USD | 25.46 | 0.30675 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S4 | P082998C1S4 | Actual | 2007 | Upgrading | 56 | 83 | 108.85 | USD | 108.85 | 1.3114 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 |  | P082998C1S4 | Ratio | 2004 / 2007 | Upgrading | 175% | 100% | 427.5% |  | 427.5% | 427.5% |  |  |  | x | x | Quality of estimates; Change of project scope; | Disparity between the engineer’s estimate and the bids.; The cost increases resulted from variation orders and changes in design/correction of design errors and the associated impact on price adjustments.;
Ethiopia | Sub-Saharan Africa | P082998 | C2 | S1 | P082998C2S1 | Estimate | 2004 | New 2L Highway | 47 | 119 | 29.16 | USD | 29.16 | 0.24504 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C2 | S1 | P082998C2S1 | Actual | 2012 | New 2L Highway |  | 119 | 77.48 | USD | 77.48 | 0.65109 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 |  | P082998C2S1 | Ratio | 2004 / 2012 | New 2L Highway |  | 100% | 265.7% |  | 265.7% | 265.7% |  |  |  | x | x | Quality of estimates; Change of project scope; | Disparity between the engineer’s estimate and the bids.; The cost increases resulted from variation orders and changes in design/correction of design errors and the associated impact on price adjustments.;
Ethiopia | Sub-Saharan Africa | P082998 | C2 | S2 | P082998C2S2 | Estimate | 2004 | New 2L Highway | 52 | 137 | 17.87 | USD | 17.87 | 0.13044 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C2 | S2 | P082998C2S2 | Actual | 2012 | New 2L Highway |  | 137 | 70.6 | USD | 70.6 | 0.51533 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P082998 | C1 |  | P082998C2S2 | Ratio | 2004 / 2012 | New 2L Highway |  | 100% | 395.1% |  | 395.1% | 395.1% |  |  |  | x | x | Quality of estimates; Change of project scope; | Disparity between the engineer’s estimate and the bids.; The cost increases resulted from variation orders and changes in design/correction of design errors and the associated impact on price adjustments.;
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1 | Estimate | 2007 | Upgrading |  | 509 | 268.46 | USD | 268.46 | 0.52743 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1 | Actual | 2015 | Upgrading |  | 499.63 | 402.34 | USD | 402.34 | 0.80528 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1 | Ratio | 2007 / 2015 | Upgrading |  | 98.16% | 149.9% |  | 149.9% | 152.7% |  |  |  | x | x | Capacity of contractor; Procurement system; Competition | Quality of contractors and supervision consultant services: during appraisal this risk was correctly identified as substantial, and proved to be true during implementation. In particular the quality with regards to safeguards compliance fell short, particularly in early stages of implementation, with lack of adequate trained personnel on both the supervision and contractor side. The quality of Contractor project implementation varied greatly and due to lack of proper project management, as well as lack of adequate human resources works were delayed. High staff turnover also impacted the ability of the contractors to deliver quality services. ; The major factors that impacted project implementation are initial delays with procurement processes; quality of bidding documents and safeguards compliance. ; Shortage of materials: during 2010-2012, there was a shortage of cement in the country impacting project implementation and adding to delays in works activities.
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S1 | P091077C1S1 | Estimate | 2007 | Upgrading | 36.5 | 99 | 51.75 | USD | 51.75 | 0.52273 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S1 | P091077C1S1 | Actual | 2015 | Upgrading | 62.9333 | 99 | 83.58 | USD | 83.58 | 0.84424 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1S1 | Ratio | 2007 / 2015 | Upgrading | 172.4% | 100% | 161.5% |  | 161.5% | 161.5% |  |  |  | x | x | Capacity of contractor; Procurement system; Competition | Quality of contractors and supervision consultant services: during appraisal this risk was correctly identified as substantial, and proved to be true during implementation. In particular the quality with regards to safeguards compliance fell short, particularly in early stages of implementation, with lack of adequate trained personnel on both the supervision and contractor side. The quality of Contractor project implementation varied greatly and due to lack of proper project management, as well as lack of adequate human resources works were delayed. High staff turnover also impacted the ability of the contractors to deliver quality services. ; The major factors that impacted project implementation are initial delays with procurement processes; quality of bidding documents and safeguards compliance. ; Shortage of materials: during 2010-2012, there was a shortage of cement in the country impacting project implementation and adding to delays in works activities.
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S2 | P091077C1S2 | Estimate | 2007 | Reconstruction | 30.4333 | 66 | 37.63 | USD | 37.63 | 0.57015
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S2 | P091077C1S2 | Actual | 2015 | Reconstruction | 61.8667 | 66 | 55.81 | USD | 55.81 | 0.84561
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1S2 | Ratio | 2007 / 2015 | Reconstruction | 203.3% | 100% | 148.3% |  | 148.3% | 148.3%
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S3 | P091077C1S3 | Estimate | 2007 | Reconstruction | 30.5 | 65 | 39.4 | USD | 39.4 | 0.60615
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S3 | P091077C1S3 | Actual | 2015 | Reconstruction | 36.1333 | 65 | 48.6 | USD | 48.6 | 0.74769
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1S3 | Ratio | 2007 / 2015 | Reconstruction | 118.5% | 100% | 123.4% |  | 123.4% | 123.4%
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S4 | P091077C1S4 | Estimate | 2007 | Upgrading | 36.5 | 94.1 | 47.86 | USD | 47.86 | 0.50861 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S4 | P091077C1S4 | Actual | 2015 | Upgrading | 33.6333 | 94.1 | 80.6 | USD | 80.6 | 0.85654 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1S4 | Ratio | 2007 / 2015 | Upgrading | 92.15% | 100% | 168.4% |  | 168.4% | 168.4% |  |  |  | x | x | Capacity of contractor; Procurement system; Competition | Quality of contractors and supervision consultant services: during appraisal this risk was correctly identified as substantial, and proved to be true during implementation. In particular the quality with regards to safeguards compliance fell short, particularly in early stages of implementation, with lack of adequate trained personnel on both the supervision and contractor side. The quality of Contractor project implementation varied greatly and due to lack of proper project management, as well as lack of adequate human resources works were delayed. High staff turnover also impacted the ability of the contractors to deliver quality services. ; The major factors that impacted project implementation are initial delays with procurement processes; quality of bidding documents and safeguards compliance. ; Shortage of materials: during 2010-2012, there was a shortage of cement in the country impacting project implementation and adding to delays in works activities.
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S5 | P091077C1S5 | Estimate | 2007 | Upgrading | 36.5 | 109 | 58.54 | USD | 58.54 | 0.53706 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S5 | P091077C1S5 | Actual | 2015 | Upgrading | 56.6667 | 109 | 88.85 | USD | 88.85 | 0.81514 |  |  |  | x | x
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S5 | P091077C1S5 | Ratio | 2007 / 2015 | Upgrading | 155.3% | 100% |  |  | 151.8% | 151.8% |  |  |  | x | x | Capacity of contractor; Procurement system; Competition | Quality of contractors and supervision consultant services: during appraisal this risk was correctly identified as substantial, and proved to be true during implementation. In particular the quality with regards to safeguards compliance fell short, particularly in early stages of implementation, with lack of adequate trained personnel on both the supervision and contractor side. The quality of Contractor project implementation varied greatly and due to lack of proper project management, as well as lack of adequate human resources works were delayed. High staff turnover also impacted the ability of the contractors to deliver quality services. ; The major factors that impacted project implementation are initial delays with procurement processes; quality of bidding documents and safeguards compliance. ; Shortage of materials: during 2010-2012, there was a shortage of cement in the country impacting project implementation and adding to delays in works activities.
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S6 | P091077C1S6 | Estimate | 2007 | Upgrading | 30.3333 | 65.26 | 33.38 | USD | 33.38 | 0.51149
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S6 | P091077C1S6 | Actual | 2015 | Upgrading | 50.6667 | 65.26 | 33.06 | USD | 33.06 | 0.50659
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1S6 | Ratio | 2007 / 2015 | Upgrading | 167% | 100% | 99.04% |  | 99.04% | 99.04%
Georgia | Europe and Central Asia | P040556 | C1 |  | P040556C1 | Estimate | 2000 | Strengthening |  | 162 | 28.16 | USD | 28.16 | 0.17383
Georgia | Europe and Central Asia | P040556 | C1 |  | P040556C1 | Actual | 2006 | Strengthening |  | 167 | 28.48 | USD | 28.48 | 0.17054
Georgia | Europe and Central Asia | P040556 | C1 |  | P040556C1 | Ratio | 2000 / 2006 | Strengthening |  | 103.1% | 101.1% |  | 101.1% | 98.11%
Georgia | Europe and Central Asia | P083110 | C1 |  | P083110C1 | Estimate | 2006 | Widening and Reconstruction |  | 12.2 | 25.3971 | USD | 25.3971 | 2.0817
Georgia | Europe and Central Asia | P083110 | C1 |  | P083110C1 | Actual | 2013 | Widening and Reconstruction |  | 13 | 29.15 | USD | 29.15 | 2.2423
Georgia | Europe and Central Asia | P083110 | C1 |  | P083110C1 | Ratio | 2006 / 2013 | Widening and Reconstruction |  | 106.6% | 114.8% |  | 114.8% | 107.7%
Georgia | Europe and Central Asia | P086277 | C1 |  | P086277C1 | Estimate | 2004 | Strengthening | 64 | 500 | 20.54 | USD | 20.54 | 0.04108 |  | x |  | x | x
Georgia | Europe and Central Asia | P086277 | C1 |  | P086277C1 | Actual | 2013 | Strengthening | 82 | 842 | 129.94 | USD | 129.94 | 0.15432 |  | x |  | x | x
Georgia | Europe and Central Asia | P086277 | C1 |  | P086277C1 | Ratio | 2004 / 2013 | Strengthening | 128.1% | 168.4% | 632.6% |  | 632.6% | 375.7% |  | x |  | x | x | Change of project scope; Change of project scope; | During appraisal, the Bank team had argued for relatively low standard of rehabilitation with the counterpart arguing for a higher standard. During implementation, it was found that roads rehabilitated to the Bank suggested standards soon deteriorated after rehabilitation thus requiring maintenance interventions. This experience led the Bank team to agree that the roads be rehabilitated to higher standard; The project also had to implement three other Bank operations related to the upgrading of the E60 road corridor.;
Georgia | Europe and Central Asia | P094044 | C1 | S1 | P094044C1S1 | Estimate | 2007 | Widening | 20 | 24 | 41.95 | USD | 41.95 | 1.7479 |  |  |  | x | x
Georgia | Europe and Central Asia | P094044 | C1 | S1 | P094044C1S1 | Actual | 2012 | Widening | 28 | 24 | 69.2 | USD | 69.2 | 2.8833 |  |  |  | x | x
Georgia | Europe and Central Asia | P094044 | C1 |  | P094044C1S1 | Ratio | 2007 / 2012 | Widening | 140% | 100% | 165% |  | 165% | 165% |  |  |  | x | x | Political events; Quality of estimates; Weather shocks | (i) Political economy played the most direct and critical part in implementation of the Project. Due to its high visibility, the Project was under political watch and pressure right from the start of its preparation. The PAD explicitly highlighted “the Government’s priority for a speedy Project implementation” and even rated the risk of failure to implement it in a timely manner as low-to-medium. Due to that political pressure, the designs underwent quick review, procurement of the construction works was too speedy, and some Project road sections were twice opened prematurely to all traffic, which altogether affected the quality and timeliness of the work contracts and the quality of the outputs. (ii) The conflict with Russia in August 2008 interrupted construction and cut off some sources of materials. The contractor was not able to access the site for more than one week. ; Design and procurement of both road and bridge contracts took place at a very fast pace, and without proper and thorough review of designs. The timeline set for the preparation of the designs was 6 months, which was unrealistic and ambitious. The budget of 1.5% of the construction cost estimate was low and insufficient for the amount of surveys, geotechnical investigations, design development and checking required for a road project of this scale. The road designs were included in the bidding document in January 2008 — within a month after submission — without proper review by the RD. The road contract was signed in May 2008: 45 days given for the bid submission, while permitted under WB rules, was insufficient for the bidders to carry out site surveys and prepare informed bids for a contract of this size. Procurement of the bridge works was also carried out quickly; tenders were called in early 2009, and the contract was signed in April 2009. ; Harsh winter condition prevented the second road contractor from executing all remedial works and completing the remaining works — including those required by the Environmental Management Plan (EMP) — by the December 2011 deadline.
Guinea | Sub-Saharan Africa | P065127 | C1 |  | P065127C1 | Estimate | 2004 | Upgrading |  | 1270 | 23.9 | USD | 23.9 | 0.018819
Guinea | Sub-Saharan Africa | P065127 | C1 |  | P065127C1 | Actual | 2013 | Upgrading |  | 800 | 19 | USD | 19 | 0.02375
Guinea | Sub-Saharan Africa | P065127 | C1 |  | P065127C1 | Ratio | 2004 / 2013 | Upgrading |  | 62.99% | 79.5% |  | 79.5% | 126.2%
Guinea | Sub-Saharan Africa | AfDB P-GN-AB0-005 | C1 |  | AfDB P-GN-AB0-005 C1 | Estimate | 2012 | Asphalt Mix Resurfacing |  | 1080 | 8.3 | UA | 5.3896 | 0.0049904 | x | x | x
Guinea | Sub-Saharan Africa | AfDB P-GN-AB0-005 | C1 |  | AfDB P-GN-AB0-005 C1 | Actual | 2011 | Asphalt Mix Resurfacing |  | 278 | 3.326 | UA | 2.1185 | 0.0076204 | x | x | x | Procurement system | Procurement procedures were inadequatelyapplied resulting in poor selection of most service providers, which affected the performance (P.9)
Guinea | Sub-Saharan Africa | AfDB P-GN-AB0-005 | C1 |  | AfDB P-GN-AB0-005 C1 | Ratio | 2012 / 2011 | Asphalt Mix Resurfacing |  | 25.74% | 40.07% |  | 39.31% | 152.7% | x | x | x | Capacity of contractors | only 15% of works was completed three years after the beginning of the project (annex p. 1/4) | ; Procurement system; Capacity of contractors | ; Procurement procedures were inadequatelyapplied resulting in poor selection of most service providers, which affected the performance (P.9); only 15% of works was completed three years after the beginning of the project (annex p. 1/4)
Haiti | Latin America and Caribbean | P095523 | C1 | S1 | P095523C1S1 | Estimate | 2006 | Upgrading |  | 38.8 | 6.8 | USD | 6.8 | 0.17526 | x |  |  | x | x
Haiti | Latin America and Caribbean | P095523 | C1 | S1 | P095523C1S1 | Actual | 2014 | Upgrading |  | 8 | 8.08 | USD | 8.08 | 1.01 | x |  |  | x | x
Haiti | Latin America and Caribbean | P095523 | C1 |  | P095523C1S1 | Ratio | 2006 / 2014 | Upgrading |  | 20.62% | 118.8% |  | 118.8% | 576.3% | x |  |  | x | x | Capacity of Counterpart; Weather shocks; | Public sector weakness: The weakness of public sector management in Haiti was a long- standing issue that was yet to be resolved at the time of project implementation. It has not been resolved to date. Public sector institutions largely depend on external assistance to carry out their functions. Most projects are managed by ad hoc PCUs similarly supported by external assistance. Institutional capacity is with the private and NGO service sector paying higher salaries and therefore attracting more qualified staff.; Disruptions and delays caused by the 2007/2008 hurricanes and the 2010 earthquake: ;
Haiti | Latin America and Caribbean | P095523 | C1 | S2 | P095523C1S2 | Estimate | 2006 | Upgrading |  | 63 | 2.4 | USD | 2.4 | 0.038095 |  |  |  | x | x
Haiti | Latin America and Caribbean | P095523 | C1 | S2 | P095523C1S2 | Actual | 2014 | Upgrading |  | 40 | 8.17 | USD | 8.17 | 0.20425 |  |  |  | x | x
Haiti | Latin America and Caribbean | P095523 | C1 |  | P095523C1S2 | Ratio | 2006 / 2014 | Upgrading |  | 63.49% | 340.4% |  | 340.4% | 536.2% |  |  |  | x | x | Capacity of Counterpart; Weather shocks; | Public sector weakness: The weakness of public sector management in Haiti was a long- standing issue that was yet to be resolved at the time of project implementation. It has not been resolved to date. Public sector institutions largely depend on external assistance to carry out their functions. Most projects are managed by ad hoc PCUs similarly supported by external assistance. Institutional capacity is with the private and NGO service sector paying higher salaries and therefore attracting more qualified staff.; Disruptions and delays caused by the 2007/2008 hurricanes and the 2010 earthquake: ;
Honduras | Latin America and Caribbean | P057538 | C1 | S1 | P057538C1S1 | Estimate | 2000 | Strengthening |  | 84 | 19.2 | USD | 19.2 | 0.22857 |  |  |  | x | x
Honduras | Latin America and Caribbean | P057538 | C1 | S1 | P057538C1S1 | Actual | 2007 | Strengthening | 35 | 50 | 20.4 | USD | 20.4 | 0.408 |  |  |  | x | x
Honduras | Latin America and Caribbean | P057538 | C1 |  | P057538C1S1 | Ratio | 2000 / 2007 | Strengthening |  | 59.52% | 106.2% |  | 106.2% | 178.5% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; | Higher costs were incurred as a result of the SDR/US dollar devaluation; most of the civil works carried out under the Project experienced cost increases in relation to estimate; (these increases resulted from: additional tasks identified during works execution not contemplated during road engineering designs; changes needed due to problems in engineering designs and to considerable lags between the dates of design preparation and of works execution and price adjustments higher than originally budgeted);
Honduras | Latin America and Caribbean | P057538 | C1 | S2 | P057538C1S2 | Estimate | 2000 | Strengthening |  | 40.2 | 6.3 | USD | 6.3 | 0.15672 |  |  |  | x | x
Honduras | Latin America and Caribbean | P057538 | C1 | S2 | P057538C1S2 | Actual | 2007 | Strengthening |  | 40.2 | 10.1 | USD | 10.1 | 0.25124 |  |  |  | x | x
Honduras | Latin America and Caribbean | P057538 | C1 |  | P057538C1S2 | Ratio | 2000 / 2007 | Strengthening |  | 100% | 160.3% |  | 160.3% | 160.3% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; | Higher costs were incurred as a result of the SDR/US dollar devaluation; most of the civil works carried out under the Project experienced cost increases in relation to estimate; (these increases resulted from: additional tasks identified during works execution not contemplated during road engineering designs; changes needed due to problems in engineering designs and to considerable lags between the dates of design preparation and of works execution and price adjustments higher than originally budgeted);
Honduras | Latin America and Caribbean | P057538 | C1 | S3 | P057538C1S3 | Estimate | 2000 | Upgrading |  | 46.5 | 18 | USD | 18 | 0.3871
Honduras | Latin America and Caribbean | P057538 | C1 | S3 | P057538C1S3 | Actual | 2007 | Upgrading | 37 | 46.6 | 18.5 | USD | 18.5 | 0.397
Honduras | Latin America and Caribbean | P057538 | C1 |  | P057538C1S3 | Ratio | 2000 / 2007 | Upgrading |  | 100.2% | 102.8% |  | 102.8% | 102.6%
Honduras | Latin America and Caribbean | P057538 | C1 | S4 | P057538C1S4 | Estimate | 2000 | Upgrading |  | 47 | 13.5 | USD | 13.5 | 0.28723
Honduras | Latin America and Caribbean | P057538 | C1 | S4 | P057538C1S4 | Actual | 2007 | Upgrading | 26 | 47 | 14.5 | USD | 14.5 | 0.30851
Honduras | Latin America and Caribbean | P057538 | C1 |  | P057538C1S4 | Ratio | 2000 / 2007 | Upgrading |  | 100% | 107.4% |  | 107.4% | 107.4%
Honduras | Latin America and Caribbean | P057538 | C2 |  | P057538C2 | Estimate | 2000 | Reconstruction |  | 100 | 8.5 | USD | 8.5 | 0.085
Honduras | Latin America and Caribbean | P057538 | C2 |  | P057538C2 | Actual | 2007 | Reconstruction |  | 102 | 4.9 | USD | 4.9 | 0.048039
Honduras | Latin America and Caribbean | P057538 | C1 |  | P057538C2 | Ratio | 2000 / 2007 | Reconstruction |  | 102% | 57.65% |  | 57.65% | 56.52%
Honduras | Latin America and Caribbean | P057538 | C3 |  | P057538C3 | Estimate | 2000 | Routine Maintenance |  | 900 | 4 | USD | 4 | 0.0044444 |  | x |  |  | x
Honduras | Latin America and Caribbean | P057538 | C3 |  | P057538C3 | Actual | 2007 | Routine Maintenance |  | 1670 | 7.8 | USD | 7.8 | 0.0046707 |  | x |  |  | x
Honduras | Latin America and Caribbean | P057538 | C1 |  | P057538C3 | Ratio | 2000 / 2007 | Routine Maintenance |  | 185.6% | 195% |  | 195% | 105.1% |  | x |  |  | x | Change of project scope; ; | the greater actual length resulted from the highly satisfactory performance of the road maintenace pilot program to that date (Dec 2005); ;
Honduras | Latin America and Caribbean | P109058 | C1 | S1 | P109058C1S1 | Estimate | 2008 | Upgrading |  | 46.4 | 16.87 | USD | 16.87 | 0.36358
Honduras | Latin America and Caribbean | P109058 | C1 | S1 | P109058C1S1 | Actual | 2015 | Upgrading | 16 | 46.4 | 18.3 | USD | 18.3 | 0.3944
Honduras | Latin America and Caribbean | P109058 | C1 |  | P109058C1S1 | Ratio | 2008 / 2015 | Upgrading |  | 100% | 108.5% |  | 108.5% | 108.5%
Honduras | Latin America and Caribbean | P109058 | C1 | S2 | P109058C1S2 | Estimate | 2008 | Upgrading |  | 30.5 | 17.07 | USD | 17.07 | 0.55967
Honduras | Latin America and Caribbean | P109058 | C1 | S2 | P109058C1S2 | Actual | 2015 | Upgrading | 24 | 30.5 | 22.1 | USD | 22.1 | 0.72459
Honduras | Latin America and Caribbean | P109058 | C1 |  | P109058C1S2 | Ratio | 2008 / 2015 | Upgrading |  | 100% | 129.5% |  | 129.5% | 129.5%
Honduras | Latin America and Caribbean | P109058 | C1 | S3 | P109058C1S3 | Estimate | 2008 | Upgrading |  | 60.5 | 17.73 | USD | 17.73 | 0.29306 | x |  |  | x | x
Honduras | Latin America and Caribbean | P109058 | C1 | S3 | P109058C1S3 | Actual | 2015 | Upgrading | 43 | 22 | 20.26 | USD | 20.26 | 0.92091 | x |  |  | x | x
Honduras | Latin America and Caribbean | P109058 | C1 |  | P109058C1S3 | Ratio | 2008 / 2015 | Upgrading |  | 36.36% | 114.3% |  | 114.3% | 314.2% | x |  |  | x | x | Weather shocks; Political events; | Tropical Storm No. 16 led to change in priorities where funding was diverted to emergency infrastructure restoration; With the 2010-2013 incoming presidential administration, there was a change in management and strategy in the counterpart, which led to a reversal in many aspects of the program, and accordingly, very little initial progress could be made in the implementation of the relevant component of the project;
India | South Asia | P067606 | C1 |  | P067606C1 | Estimate | 2002 | Upgrading | 36 | 971 | 286 | USD | 286 | 0.29454
India | South Asia | P067606 | C1 |  | P067606C1 | Actual | 2011 | Upgrading | 45 | 685 | 217 | USD | 217 | 0.31679
India | South Asia | P067606 | C1 |  | P067606C1 | Ratio | 2002 / 2011 | Upgrading | 125% | 70.55% | 75.87% |  | 75.87% | 107.6%
India | South Asia | P067606 | C2 |  | P067606C2 | Estimate | 2002 | Asphalt Mix Resurfacing | 24 | 2513 | 225.2 | USD | 225.2 | 0.089614 |  |  |  | x | x
India | South Asia | P067606 | C2 |  | P067606C2 | Actual | 2011 | Asphalt Mix Resurfacing | 30 | 1910 | 271 | USD | 271 | 0.14188 |  |  |  | x | x
India | South Asia | P067606 | C1 |  | P067606C2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing | 125% | 76% | 120.3% |  | 120.3% | 158.3% |  |  |  | x | x | Capacity of counterpart; Capacity of counterpart ; Macroeconomic conditions | cost implications were incurred as a result of technically deficient road designs; the delay in the start of Phase-II contributed to the occurrence of a cost overrun of 16% by April 2006; cost overrun was incurred due to US$ depreciation against INR
India | South Asia | P069889 | C1 |  | P069889C1 | Estimate | 2007 | Widening and Reconstruction |  | 184 | 36.76 | USD | 36.76 | 0.19978 |  |  |  | x | x
India | South Asia | P069889 | C1 |  | P069889C1 | Actual | 2011 | Widening and Reconstruction |  | 174 | 87.6 | USD | 87.6 | 0.50345 |  |  |  | x | x
India | South Asia | P069889 | C1 |  | P069889C1 | Ratio | 2007 / 2011 | Widening and Reconstruction |  | 94.57% | 238.3% |  | 238.3% | 252% |  |  |  | x | x | Capacity of contractors; Weather shocks ; Macroeconomic conditions | deficient engineering designs and overall slow implementation performance of the contractors led to cost overruns; increases in supervision costs and the costs of civil works; heavy and longer than normal monsoon period lasting over five months; shortage and disruptions of major commodities such as bitumen, oil, cement, steel and diesel fuel
India | South Asia | P069889 | C2 |  | P069889C2 | Estimate | 2007 | Surface Treatment Resurfacing |  | 520 | 17.66 | USD | 17.66 | 0.033962
India | South Asia | P069889 | C2 |  | P069889C2 | Actual | 2011 | Surface Treatment Resurfacing |  | 300 | 11.4 | USD | 11.4 | 0.038
India | South Asia | P069889 | C1 |  | P069889C2 | Ratio | 2007 / 2011 | Surface Treatment Resurfacing |  | 57.69% | 64.55% |  | 64.55% | 111.9% | [6 empty] | diesel fuel; ;
India | South Asia | P071244 | C1 |  | P071244C1 | Estimate | 2001 | Widening |  | 420 | 618.08 | USD | 618.08 | 1.4716
India | South Asia | P071244 | C1 |  | P071244C1 | Actual | 2009 | Widening | 81 | 416.76 | 694.44 | USD | 694.44 | 1.6663
India | South Asia | P071244 | C1 |  | P071244C1 | Ratio | 2001 / 2009 | Widening |  | 99.23% | 112.4% |  | 112.4% | 113.2%
India | South Asia | P073776 | C1 |  | P073776C1 | Estimate | 2003 | New 4L Expressway | 24 | 84.708 | 240.41 | USD | 240.41 | 2.8381
India | South Asia | P073776 | C1 |  | P073776C1 | Actual | 2010 | New 4L Expressway | 63 | 84.8 | 301.36 | USD | 301.36 | 3.5538
India | South Asia | P073776 | C1 |  | P073776C1 | Ratio | 2003 / 2010 | New 4L Expressway | 262.5% | 100.1% | 125.4% |  | 125.4% | 125.2%
India | South Asia | P077856 | C1 |  | P077856C1 | Estimate | 2004 | Widening | 48 | 483 | 802.87 | USD | 802.87 | 1.6623
India | South Asia | P077856 | C1 |  | P077856C1 | Actual | 2012 | Widening | 84 | 327 | 800.12 | USD | 800.12 | 2.4469
India | South Asia | P077856 | C1 |  | P077856C1 | Ratio | 2004 / 2012 | Widening | 175% | 67.7% | 99.66% |  | 99.66% | 147.2%
India | South Asia | P009972 | C1 | S1 | P009972C1S1 | Estimate | 2000 | Widening and Reconstruction | 42 | 62 | 86 | USD | 86 | 1.3871
India | South Asia | P009972 | C1 | S1 | P009972C1S1 | Actual | 2008 | Widening and Reconstruction | 77 | 62 | 2893 | INR | 62.1349 | 1.0022
India | South Asia | P009972 | C1 |  | P009972C1S1 | Ratio | 2000 / 2008 | Widening and Reconstruction | 183.3% | 100% | 3364% |  | 72.25% | 72.25%
India | South Asia | P009972 | C1 | S2 | P009972C1S2 | Estimate | 2000 | Widening and Reconstruction | 40 | 77 | 101.7 | USD | 101.7 | 1.3208
India | South Asia | P009972 | C1 | S2 | P009972C1S2 | Actual | 2008 | Widening and Reconstruction | 93 | 77 | 2955.3 | INR | 63.4729 | 0.82432
India | South Asia | P009972 | C1 |  | P009972C1S2 | Ratio | 2000 / 2008 | Widening and Reconstruction | 232.5% | 100% | 2906% |  | 62.41% | 62.41%
India | South Asia | P009972 | C1 | S3 | P009972C1S3 | Estimate | 2000 | Widening and Reconstruction | 36 | 43 | 50.3 | USD | 50.3 | 1.1698
India | South Asia | P009972 | C1 | S3 | P009972C1S3 | Actual | 2008 | Widening and Reconstruction | 46 | 43 | 1798.6 | INR | 38.6297 | 0.89837
India | South Asia | P009972 | C1 |  | P009972C1S3 | Ratio | 2000 / 2008 | Widening and Reconstruction | 127.8% | 100% | 3576% |  | 76.8% | 76.8%
India | South Asia | P009972 | C1 | S4 | P009972C1S4 | Estimate | 2000 | Widening and Reconstruction | 39 | 72 | 77.6 | USD | 77.6 | 1.0778
India | South Asia | P009972 | C1 | S4 | P009972C1S4 | Actual | 2008 | Widening and Reconstruction | 83 | 72 | 2654.8 | INR | 57.0189 | 0.79193
India | South Asia | P009972 | C1 |  | P009972C1S4 | Ratio | 2000 / 2008 | Widening and Reconstruction | 212.8% | 100% | 3421% |  | 73.48% | 73.48%
India | South Asia | P009972 | C1 | S5 | P009972C1S5 | Estimate | 2000 | Widening and Reconstruction | 36 | 40 | 68 | USD | 68 | 1.7
India | South Asia | P009972 | C1 | S5 | P009972C1S5 | Actual | 2008 | Widening and Reconstruction | 63 | 45 | 2299.6 | INR | 49.39 | 1.0976
India | South Asia | P009972 | C1 |  | P009972C1S5 | Ratio | 2000 / 2008 | Widening and Reconstruction | 175% | 112.5% | 3382% |  | 72.63% | 64.56%
India | South Asia | P009972 | C1 | S6 | P009972C1S6 | Estimate | 2000 | Widening and Reconstruction | 36 | 45 | 65.4 | USD | 65.4 | 1.4533
India | South Asia | P009972 | C1 | S6 | P009972C1S6 | Actual | 2008 | Widening and Reconstruction | 57 | 40 | 2179.9 | INR | 46.8192 | 1.1705
India | South Asia | P009972 | C1 |  | P009972C1S6 | Ratio | 2000 / 2008 | Widening and Reconstruction | 158.3% | 88.89% | 3333% |  | 71.59% | 80.54%
India | South Asia | P009972 | C1 | S7 | P009972C1S7 | Estimate | 2000 | Widening and Reconstruction | 42 | 138.8 | 161.8 | USD | 161.8 | 1.1657
India | South Asia | P009972 | C1 | S7 | P009972C1S7 | Actual | 2008 | Widening and Reconstruction | 84 | 138.8 | 5845.9 | INR | 125.5563 | 0.90458
India | South Asia | P009972 | C1 |  | P009972C1S7 | Ratio | 2000 / 2008 | Widening and Reconstruction | 200% | 100% | 3613% |  | 77.6% | 77.6%
India | South Asia | P050649 | C1 |  | P050649C1 | Estimate | 2003 | Widening and Reconstruction | 48 | 750 | 320.97 | USD | 320.97 | 0.42796
India | South Asia | P050649 | C1 |  | P050649C1 | Actual | 2012 | Widening and Reconstruction |  | 724 | 385.83 | USD | 385.83 | 0.53291
India | South Asia | P050649 | C1 |  | P050649C1 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 96.53% | 120.2% |  | 120.2% | 124.5%
India | South Asia | P050649 | C1 | S1 | P050649C1S1 | Estimate | 2003 | Widening and Reconstruction |  | 401 | 138.54 | USD | 138.54 | 0.34549
India | South Asia | P050649 | C1 | S1 | P050649C1S1 | Actual | 2012 | Widening and Reconstruction |  | 378.6 | 6796 | INR | 133.5167 | 0.35266
India | South Asia | P050649 | C1 |  | P050649C1S1 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 94.41% | 4905% |  | 96.37% | 102.1%
India | South Asia | P050649 | C1 | S2 | P050649C1S2 | Estimate | 2003 | Widening and Reconstruction |  | 116 | 42.71 | USD | 42.71 | 0.36819 |  |  |  | x | x
India | South Asia | P050649 | C1 | S2 | P050649C1S2 | Actual | 2012 | Widening and Reconstruction |  | 118.6 | 3494.8 | INR | 68.6601 | 0.57892 |  |  |  | x | x
India | South Asia | P050649 | C1 |  | P050649C1S2 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 102.2% | 8183% |  | 160.8% | 157.2% |  |  |  | x | x | Macroeconomic conditions ; Weather shocks; Quality of estimates | increased costs of the upgrading works due to delays and the consequent increase in the prices of key construction materials (bitumen and steel); appreciation of Indian Rupee vis-à-vis the US Dollar; higher costs were incurred due to heavy monsoons and tsunamis that took place during the extended construction periods ; actual costs of O&M were higher vis-à-vis the estimate cost
India | South Asia | P050649 | C1 | S3 | P050649C1S3 | Estimate | 2003 | Widening and Reconstruction |  | 100 | 25.83 | USD | 25.83 | 0.2583 |  |  |  | x | x
India | South Asia | P050649 | C1 | S3 | P050649C1S3 | Actual | 2012 | Widening and Reconstruction |  | 100 | 2642.2 | INR | 51.9096 | 0.5191 |  |  |  | x | x
India | South Asia | P050649 | C1 |  | P050649C1S3 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 100% | 10229% |  | 201% | 201% |  |  |  | x | x | Macroeconomic conditions ; Weather shocks; Quality of estimates | increased costs of the upgrading works due to delays and the consequent increase in the prices of key construction materials (bitumen and steel); appreciation of Indian Rupee vis-à-vis the US Dollar; higher costs were incurred due to heavy monsoons and tsunamis that took place during the extended construction periods ; actual costs of O&M were higher vis-à-vis the estimate cost
India | South Asia | P050649 | C1 | S4 | P050649C1S4 | Estimate | 2003 | Widening and Reconstruction |  | 118 | 23.96 | USD | 23.96 | 0.20305 |  |  |  | x | x
India | South Asia | P050649 | C1 | S4 | P050649C1S4 | Actual | 2012 | Widening and Reconstruction |  | 114.6 | 2162.6 | INR | 42.4872 | 0.37074 |  |  |  | x | x
India | South Asia | P050649 | C1 |  | P050649C1S4 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 97.12% | 9026% |  | 177.3% | 182.6% |  |  |  | x | x | Macroeconomic conditions ; Weather shocks; Quality of estimates | increased costs of the upgrading works due to delays and the consequent increase in the prices of key construction materials (bitumen and steel); appreciation of Indian Rupee vis-à-vis the US Dollar; higher costs were incurred due to heavy monsoons and tsunamis that took place during the extended construction periods ; actual costs of O&M were higher vis-à-vis the estimate cost
India | South Asia | P050649 | C2 |  | P050649C2 | Estimate | 2003 | Reconstruction | 48 | 2000 | 110.72 | USD | 110.72 | 0.05536
India | South Asia | P050649 | C2 |  | P050649C2 | Actual | 2012 | Reconstruction |  | 1330 | 106.18 | USD | 106.18 | 0.079835
India | South Asia | P050649 | C1 |  | P050649C2 | Ratio | 2003 / 2012 | Reconstruction |  | 66.5% | 95.9% |  | 95.9% | 144.2%
India | South Asia | P070421 | C1 |  | P070421C1 | Estimate | 2001 | Widening and Reconstruction |  | 1000 | 270.83 | USD | 270.83 | 0.27083 |  |  |  | x | x
India | South Asia | P070421 | C1 |  | P070421C1 | Actual | 2008 | Widening and Reconstruction |  | 874 | 356.2 | USD | 356.2 | 0.40755 |  |  |  | x | x
India | South Asia | P070421 | C1 |  | P070421C1 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 87.4% | 131.5% |  | 131.5% | 150.5% |  |  |  | x | x | Macroeconomic conditions; Capacity of contractor; | dollar depreciation and higher than expected increase in prices of construction materials (cement, steel, and bitumen); significant cost increases resulted from the technical capacity constraints and the lack of proper construction management skills and experience of local contractors;
India | South Asia | P070421 | C1 | S1 | P070421C1S1 | Estimate | 2001 | Widening and Reconstruction |  | 76 | 16.51 | USD | 16.51 | 0.21724
India | South Asia | P070421 | C1 | S1 | P070421C1S1 | Actual | 2008 | Widening and Reconstruction |  | 76 | 23.5 | USD | 23.5 | 0.30921
India | South Asia | P070421 | C1 |  | P070421C1S1 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 142.3% |  | 142.3% | 142.3%
India | South Asia | P070421 | C1 | S10 | P070421C1S10 | Estimate | 2001 | Widening and Reconstruction |  | 143.49 | 34.61 | USD | 34.61 | 0.2412 |  |  |  | x | x
India | South Asia | P070421 | C1 | S10 | P070421C1S10 | Actual | 2008 | Widening and Reconstruction |  | 143.49 | 68.5 | USD | 68.5 | 0.47739 |  |  |  | x | x
India | South Asia | P070421 | C1 |  | P070421C1S10 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 197.9% |  | 197.9% | 197.9% |  |  |  | x | x | Macroeconomic conditions; Capacity of contractor; | dollar depreciation and higher than expected increase in prices of construction materials (cement, steel, and bitumen); significant cost increases resulted from the technical capacity constraints and the lack of proper construction management skills and experience of local contractors;
India | South Asia | P070421 | C1 | S11 | P070421C1S11 | Estimate | 2001 | New 2L Highway |  | 50 | 12.19 | USD | 12.19 | 0.2438 |  |  | x |  | x
India | South Asia | P070421 | C1 | S11 | P070421C1S11 | Actual | 2008 | New 2L Highway |  | 50 | 2.1 | USD | 2.1 | 0.042 |  |  | x |  | x
India | South Asia | P070421 | C1 |  | P070421C1S11 | Ratio | 2001 / 2008 | New 2L Highway |  | 100% | 17.23% |  | 17.23% | 17.23% |  |  | x |  | x | Quality of estimates; ; | lower actual costs were incurred as a result of lower vehicle operating costs and capital costs ; ;
India | South Asia | P070421 | C1 | S2 | P070421C1S2 | Estimate | 2001 | Widening and Reconstruction |  | 78 | 18.89 | USD | 18.89 | 0.24218
India | South Asia | P070421 | C1 | S2 | P070421C1S2 | Actual | 2008 | Widening and Reconstruction |  | 78 | 21.7 | USD | 21.7 | 0.27821
India | South Asia | P070421 | C1 |  | P070421C1S2 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 114.9% |  | 114.9% | 114.9%
India | South Asia | P070421 | C1 | S3 | P070421C1S3 | Estimate | 2001 | Widening and Reconstruction |  | 189 | 40.01 | USD | 40.01 | 0.21169
India | South Asia | P070421 | C1 | S3 | P070421C1S3 | Actual | 2008 | Widening and Reconstruction |  | 189 | 43.6 | USD | 43.6 | 0.23069
India | South Asia | P070421 | C1 |  | P070421C1S3 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 109% |  | 109% | 109%
India | South Asia | P070421 | C1 | S4 | P070421C1S4 | Estimate | 2001 | Widening and Reconstruction |  | 20 | 4.34 | USD | 4.34 | 0.217
India | South Asia | P070421 | C1 | S4 | P070421C1S4 | Actual | 2008 | Widening and Reconstruction |  | 20 | 3.5 | USD | 3.5 | 0.175
India | South Asia | P070421 | C1 |  | P070421C1S4 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 80.65% |  | 80.65% | 80.65%
India | South Asia | P070421 | C1 | S5 | P070421C1S5 | Estimate | 2001 | Widening and Reconstruction |  | 31 | 7.76 | USD | 7.76 | 0.25032
India | South Asia | P070421 | C1 | S5 | P070421C1S5 | Actual | 2008 | Widening and Reconstruction |  | 31 | 9 | USD | 9 | 0.29032
India | South Asia | P070421 | C1 |  | P070421C1S5 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 116% |  | 116% | 116%
India | South Asia | P070421 | C1 | S6 | P070421C1S6 | Estimate | 2001 | Widening and Reconstruction |  | 94.13 | 22.94 | USD | 22.94 | 0.24371
India | South Asia | P070421 | C1 | S6 | P070421C1S6 | Actual | 2008 | Widening and Reconstruction |  | 94.13 | 21.5 | USD | 21.5 | 0.22841
India | South Asia | P070421 | C1 |  | P070421C1S6 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 93.72% |  | 93.72% | 93.72%
India | South Asia | P070421 | C1 | S7 | P070421C1S7 | Estimate | 2001 | Widening and Reconstruction |  | 103.94 | 25.35 | USD | 25.35 | 0.24389
India | South Asia | P070421 | C1 | S7 | P070421C1S7 | Actual | 2008 | Widening and Reconstruction |  | 103.94 | 14.5 | USD | 14.5 | 0.1395
India | South Asia | P070421 | C1 |  | P070421C1S7 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 57.2% |  | 57.2% | 57.2%
India | South Asia | P070421 | C1 | S8 | P070421C1S8 | Estimate | 2001 | Widening and Reconstruction |  | 170.62 | 45.67 | USD | 45.67 | 0.26767 |  |  | x |  | x
India | South Asia | P070421 | C1 | S8 | P070421C1S8 | Actual | 2008 | Widening and Reconstruction |  | 170.62 | 17.7 | USD | 17.7 | 0.10374 |  |  | x |  | x
India | South Asia | P070421 | C1 |  | P070421C1S8 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 38.76% |  | 38.76% | 38.76% |  |  | x |  | x | Quality of estimates; ; | lower actual costs were incurred as a result of lower vehicle operating costs and capital costs ; ;
India | South Asia | P070421 | C1 | S9 | P070421C1S9 | Estimate | 2001 | Widening and Reconstruction |  | 35.2 | 8.58 | USD | 8.58 | 0.24375 |  |  |  | x | x
India | South Asia | P070421 | C1 | S9 | P070421C1S9 | Actual | 2008 | Widening and Reconstruction |  | 35.2 | 84.8 | USD | 84.8 | 2.4091 |  |  |  | x | x
India | South Asia | P070421 | C1 |  | P070421C1S9 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% | 988.3% |  | 988.3% | 988.3% |  |  |  | x | x | Capacity of contractor; Macroeconomic conditions; | significant cost increases resulted from the technical capacity constraints and the lack of proper construction management skills and experience of local contractors; dollar depreciation and higher than expected increase in prices of construction materials (cement, steel, and bitumen);
India | South Asia | P070421 | C2 |  | P070421C2 | Estimate | 2001 | Asphalt Mix Resurfacing |  | 1300 | 91.15 | USD | 91.15 | 0.070115 |  |  |  | x | x
India | South Asia | P070421 | C2 |  | P070421C2 | Actual | 2008 | Asphalt Mix Resurfacing |  | 1250 | 158.73 | USD | 158.73 | 0.12698 |  |  |  | x | x
India | South Asia | P070421 | C1 |  | P070421C2 | Ratio | 2001 / 2008 | Asphalt Mix Resurfacing |  | 96.15% | 174.1% |  | 174.1% | 181.1% |  |  |  | x | x | Capacity of contractor; Macroeconomic conditions; | significant cost increases resulted from the technical capacity constraints and the lack of proper construction management skills and experience of local contractors; dollar depreciation and higher than expected increase in prices of construction materials (cement, steel, and bitumen);
India | South Asia | P072539 | C1 |  | P072539C1 | Estimate | 2002 | Widening and Reconstruction |  | 579 | 227.2 | USD | 227.2 | 0.3924 | x |  |  | x | x
India | South Asia | P072539 | C1 |  | P072539C1 | Actual | 2011 | Widening and Reconstruction |  | 254 | 163.41 | USD | 163.41 | 0.64335 | x |  |  | x | x
India | South Asia | P072539 | C1 |  | P072539C1 | Ratio | 2002 / 2011 | Widening and Reconstruction |  | 43.87% | 71.92% |  | 71.92% | 164% | x |  |  | x | x | Capacity of counterpart (Procurement system); Change of project scope; Quality of estimates | poor procurement planning contributed to cost escalations ; the change in the length of civil works resulted from the restructuring of the project the project (2008) following the contractors' termination of contracts due to non payment of bills; the project was completed with a 35% cost overrun associated with land acquisition and pre-construction activities for road widening works of the original budget plan
India | South Asia | P072539 | C2 |  | P072539C2 | Estimate | 2002 | Asphalt Mix Resurfacing |  | 1009 | 54.1 | USD | 54.1 | 0.053617 |  |  |  | x | x
India | South Asia | P072539 | C2 |  | P072539C2 | Actual | 2011 | Asphalt Mix Resurfacing |  | 1156 | 129.44 | USD | 129.44 | 0.11197 |  |  |  | x | x
India | South Asia | P072539 | C1 |  | P072539C2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 114.6% | 239.3% |  | 239.3% | 208.8% |  |  |  | x | x | Capacity of counterpart (Procurement system); Quality of estimates; | poor procurement planning contributed to cost escalations ; the project was completed with a 35% cost overrun associated with land acquisition and pre-construction activities for road widening works of the original budget plan ;
India | South Asia | P077977 | C1 | S1 | P077977C1S1 | Estimate | 2004 | Upgrading | 12 | 672 | 1135.68 | INR | 25.2373 | 0.037556
India | South Asia | P077977 | C1 | S1 | P077977C1S1 | Actual | 2012 | Upgrading | 24 | 984 | 2192.3 | INR | 39.4157 | 0.040057
India | South Asia | P077977 | C1 |  | P077977C1S1 | Ratio | 2004 / 2012 | Upgrading | 200% | 146.4% | 193% |  | 156.2% | 106.7% | [5 empty] | Change of project scope; ; | the change in the length of civil works resulted from the fact that some works originally envisaged for Jharkhand were dispensed which caused a reallocation of funds ; ;
India | South Asia | P077977 | C1 | S2 | P077977C1S2 | Estimate | 2004 | Upgrading | 12 | 130 | 291.2 | INR | 6.4711 | 0.049778
India | South Asia | P077977 | C1 | S2 | P077977C1S2 | Actual | 2012 | Upgrading | 18 | 126 | 308.5 | INR | 5.5466 | 0.04402
India | South Asia | P077977 | C1 |  | P077977C1S2 | Ratio | 2004 / 2012 | Upgrading | 150% | 96.92% | 105.9% |  | 85.71% | 88.43%
India | South Asia | P077977 | C1 | S3 | P077977C1S3 | Estimate | 2004 | Upgrading | 12 | 2282 | 3605.56 | INR | 80.1236 | 0.035111 |  | x |  |  | x
India | South Asia | P077977 | C1 | S3 | P077977C1S3 | Actual | 2012 | Upgrading | 18 | 6287 | 10619.3 | INR | 190.9259 | 0.030368 |  | x |  |  | x
India | South Asia | P077977 | C1 |  | P077977C1S3 | Ratio | 2004 / 2012 | Upgrading | 150% | 275.5% | 294.5% |  | 238.3% | 86.49% |  | x |  |  | x | Change of project scope; ; | the change in the length of civil works resulted from the fact that some works originally envisaged for Jharkhand were dispensed which caused a reallocation of funds ; ;
India | South Asia | P077977 | C1 | S4 | P077977C1S4 | Estimate | 2004 | Upgrading | 12 | 1466 | 3342.48 | INR | 74.2773 | 0.050667 |  | x |  |  | x
India | South Asia | P077977 | C1 | S4 | P077977C1S4 | Actual | 2012 | Upgrading | 18 | 2227.9 | 6874.3 | INR | 123.594 | 0.055476 |  | x |  |  | x
India | South Asia | P077977 | C1 |  | P077977C1S4 | Ratio | 2004 / 2012 | Upgrading | 150% | 152% | 205.7% |  | 166.4% | 109.5% |  | x |  |  | x | Change of project scope; ; | the change in the length of civil works resulted from the fact that some works originally envisaged for Jharkhand were dispensed which caused a reallocation of funds ; ;
India | South Asia | P096023 | C1 | S1 | P096023C1S1 | Estimate | 2008 | Partial Widening and Reconstruction |  | 68 | 32.2 | USD | 32.2 | 0.47353
India | South Asia | P096023 | C1 | S1 | P096023C1S1 | Actual | 2017 | Partial Widening and Reconstruction | 48 | 68 | 1830 | INR | 27.5064 | 0.40451
India | South Asia | P096023 | C1 |  | P096023C1S1 | Ratio | 2008 / 2017 | Partial Widening and Reconstruction |  | 100% | 5683% |  | 85.42% | 85.42%
India | South Asia | P096023 | C1 | S2 | P096023C1S2 | Estimate | 2008 | Partial Widening and Reconstruction |  | 41 | 22 | USD | 22 | 0.53659
India | South Asia | P096023 | C1 | S2 | P096023C1S2 | Actual | 2017 | Partial Widening and Reconstruction | 36 | 39 | 1529 | INR | 22.9821 | 0.58928
India | South Asia | P096023 | C1 |  | P096023C1S2 | Ratio | 2008 / 2017 | Partial Widening and Reconstruction |  | 95.12% | 6950% |  | 104.5% | 109.8%
Indonesia | East Asia and Pacific | P040578 | C1 | S1 | P040578C1S1 | Estimate | 2001 | Asphalt Mix Resurfacing |  | 1000 | 44.78 | USD | 44.78 | 0.04478
Indonesia | East Asia and Pacific | P040578 | C1 | S1 | P040578C1S1 | Actual | 2006 | Asphalt Mix Resurfacing |  | 1111 | 50.33 | USD | 50.33 | 0.045302
Indonesia | East Asia and Pacific | P040578 | C1 |  | P040578C1S1 | Ratio | 2001 / 2006 | Asphalt Mix Resurfacing |  | 111.1% | 112.4% |  | 112.4% | 101.2%
Indonesia | East Asia and Pacific | P040578 | C1 | S2 | P040578C1S2 | Estimate | 2001 | Reconstruction |  | 1250 | 104.03 | USD | 104.03 | 0.083224
Indonesia | East Asia and Pacific | P040578 | C1 | S2 | P040578C1S2 | Actual | 2006 | Reconstruction |  | 1705 | 145.96 | USD | 145.96 | 0.085607
Indonesia | East Asia and Pacific | P040578 | C1 |  | P040578C1S2 | Ratio | 2001 / 2006 | Reconstruction |  | 136.4% | 140.3% |  | 140.3% | 102.9%
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1 | Estimate | 2004 | Reconstruction | 86 | 3119.2 | 158.75 | USD | 158.75 | 0.050894 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1 | Actual | 2012 | Reconstruction | 86 | 1543 | 184.47 | USD | 184.47 | 0.11955 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1 | Ratio | 2004 / 2012 | Reconstruction | 100% | 49.47% | 116.2% |  | 116.2% | 234.9% | x |  |  | x | x | Macroeconomic conditions; Capacity of counterpart; Change of project scope | the Construction Price Index almost doubled between January 2005 and December 2010, with particularly sharp increases through 2008; the on-grant financing agreement between the national and sub-national governments required 100% pre-financing by the sub-national governments and many of them experienced a lack of funds to provide the full portion of the contract amount;; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed
Indonesia | East Asia and Pacific | P074290 | C1 | S1 | P074290C1S1 | Estimate | 2004 | Asphalt Mix Resurfacing |  | 124.1 | 8.16 | USD | 8.16 | 0.065753 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 | S1 | P074290C1S1 | Actual | 2012 | Asphalt Mix Resurfacing |  | 47.2 | 6.2 | USD | 6.2 | 0.13136 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S1 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 38.03% | 75.98% |  | 75.98% | 199.8% | x |  |  | x | x | Capacity of counterpart; Change of project scope; | the on-grant financing agreement between the national and sub-national governments required 100% pre-financing by the sub-national governments and many of them experienced a lack of funds to provide the full portion of the contract amount;; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed;
Indonesia | East Asia and Pacific | P074290 | C1 | S2 | P074290C1S2 | Estimate | 2004 | Reconstruction |  | 90.2 | 8.05 | USD | 8.05 | 0.089246 |  | x |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 | S2 | P074290C1S2 | Actual | 2012 | Reconstruction |  | 392.2 | 68.69 | USD | 68.69 | 0.17514 |  | x |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S2 | Ratio | 2004 / 2012 | Reconstruction |  | 434.8% | 853.3% |  | 853.3% | 196.2% |  | x |  | x | x | Macroeconomic conditions; Change of project scope; Change of project scope | the Construction Price Index almost doubled between January 2005 and December 2010, with particularly sharp increases through 2008; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed; Fewer national inter-urban roads (C1S1) were resurfaced, but more of these roads were reconstructed
Indonesia | East Asia and Pacific | P074290 | C1 | S3 | P074290C1S3 | Estimate | 2004 | Asphalt Mix Resurfacing |  | 58.4 | 5.37 | USD | 5.37 | 0.091952
Indonesia | East Asia and Pacific | P074290 | C1 | S3 | P074290C1S3 | Actual | 2012 | Asphalt Mix Resurfacing |  | 51.8 | 6.74 | USD | 6.74 | 0.13012
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S3 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 88.7% | 125.5% |  | 125.5% | 141.5%
Indonesia | East Asia and Pacific | P074290 | C1 | S4 | P074290C1S4 | Estimate | 2004 | Reconstruction |  | 51 | 7.22 | USD | 7.22 | 0.14157 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 | S4 | P074290C1S4 | Actual | 2012 | Reconstruction |  | 19.5 | 6.25 | USD | 6.25 | 0.32051 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S4 | Ratio | 2004 / 2012 | Reconstruction |  | 38.24% | 86.57% |  | 86.57% | 226.4% | x |  |  | x | x | Macroeconomic conditions; Capacity of counterpart; Change of project scope | the Construction Price Index almost doubled between January 2005 and December 2010, with particularly sharp increases through 2008; the on-grant financing agreement between the national and sub-national governments required 100% pre-financing by the sub-national governments and many of them experienced a lack of funds to provide the full portion of the contract amount;; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed
Indonesia | East Asia and Pacific | P074290 | C1 | S5 | P074290C1S5 | Estimate | 2004 | Asphalt Mix Resurfacing |  | 372.9 | 19.31 | USD | 19.31 | 0.051783 | x |  |  |  | x
Indonesia | East Asia and Pacific | P074290 | C1 | S5 | P074290C1S5 | Actual | 2012 | Asphalt Mix Resurfacing |  | 120.7 | 9.08 | USD | 9.08 | 0.075228 | x |  |  |  | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S5 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 32.37% | 47.02% |  | 47.02% | 145.3% | x |  |  |  | x | Macroeconomic conditions; Capacity of counterpart; Change of project scope | the Construction Price Index almost doubled between January 2005 and December 2010, with particularly sharp increases through 2008; the on-grant financing agreement between the national and sub-national governments required 100% pre-financing by the sub-national governments and many of them experienced a lack of funds to provide the full portion of the contract amount;; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed
Indonesia | East Asia and Pacific | P074290 | C1 | S6 | P074290C1S6 | Estimate | 2004 | Reconstruction |  | 438.1 | 41.49 | USD | 41.49 | 0.094704 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 | S6 | P074290C1S6 | Actual | 2012 | Reconstruction |  | 179.2 | 31.94 | USD | 31.94 | 0.17824 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S6 | Ratio | 2004 / 2012 | Reconstruction |  | 40.9% | 76.98% |  | 76.98% | 188.2% | x |  |  | x | x | Macroeconomic conditions; Capacity of counterpart; Change of project scope | the Construction Price Index almost doubled between January 2005 and December 2010, with particularly sharp increases through 2008; the on-grant financing agreement between the national and sub-national governments required 100% pre-financing by the sub-national governments and many of them experienced a lack of funds to provide the full portion of the contract amount;; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed
Indonesia | East Asia and Pacific | P074290 | C1 | S7 | P074290C1S7 | Estimate | 2004 | Asphalt Mix Resurfacing |  | 1049.7 | 25.26 | USD | 25.26 | 0.024064 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 | S7 | P074290C1S7 | Actual | 2012 | Asphalt Mix Resurfacing |  | 273.5 | 14.29 | USD | 14.29 | 0.052249 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S7 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 26.06% | 56.57% |  | 56.57% | 217.1% | x |  |  | x | x | Macroeconomic conditions; Capacity of counterpart; Change of project scope | the Construction Price Index almost doubled between January 2005 and December 2010, with particularly sharp increases through 2008; the on-grant financing agreement between the national and sub-national governments required 100% pre-financing by the sub-national governments and many of them experienced a lack of funds to provide the full portion of the contract amount;; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed
Indonesia | East Asia and Pacific | P074290 | C1 | S8 | P074290C1S8 | Estimate | 2004 | Reconstruction |  | 934.8 | 43.89 | USD | 43.89 | 0.046951 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 | S8 | P074290C1S8 | Actual | 2012 | Reconstruction |  | 458.9 | 41.28 | USD | 41.28 | 0.089954 | x |  |  | x | x
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1S8 | Ratio | 2004 / 2012 | Reconstruction |  | 49.09% | 94.05% |  | 94.05% | 191.6% | x |  |  | x | x | Macroeconomic conditions; Capacity of counterpart; Change of project scope | the Construction Price Index almost doubled between January 2005 and December 2010, with particularly sharp increases through 2008; the on-grant financing agreement between the national and sub-national governments required 100% pre-financing by the sub-national governments and many of them experienced a lack of funds to provide the full portion of the contract amount;; It was anticipated that there would be 230 contract packages, but only 104 contract packages were completed
Indonesia | East Asia and Pacific | P079906 | C1 |  | P079906C1 | Estimate | 2006 | Reconstruction |  | 401.5 | 262.1 | USD | 262.1 | 0.6528
Indonesia | East Asia and Pacific | P079906 | C1 |  | P079906C1 | Actual | 2014 | Reconstruction |  | 228.41 | 208.8 | USD | 208.8 | 0.91415
Indonesia | East Asia and Pacific | P079906 | C1 |  | P079906C1 | Ratio | 2006 / 2014 | Reconstruction |  | 56.89% | 79.66% |  | 79.66% | 140%
Indonesia | East Asia and Pacific | P079906 | C1 | S1 | P079906C1S1 | Estimate | 2006 | Strengthening |  | 141.8 | 75.1 | USD | 75.1 | 0.52962
Indonesia | East Asia and Pacific | P079906 | C1 | S1 | P079906C1S1 | Actual | 2014 | Strengthening |  | 106.4 | 63.2 | USD | 63.2 | 0.59398
Indonesia | East Asia and Pacific | P079906 | C1 |  | P079906C1S1 | Ratio | 2006 / 2014 | Strengthening |  | 75.04% | 84.15% |  | 84.15% | 112.2%
Indonesia | East Asia and Pacific | P079906 | C1 | S2 | P079906C1S2 | Estimate | 2006 | Widening |  | 102.5 | 99.7 | USD | 99.7 | 0.97268
Indonesia | East Asia and Pacific | P079906 | C1 | S2 | P079906C1S2 | Actual | 2014 | Widening |  | 84.8 | 94.7 | USD | 94.7 | 1.1167
Indonesia | East Asia and Pacific | P079906 | C1 |  | P079906C1S2 | Ratio | 2006 / 2014 | Widening |  | 82.73% | 94.98% |  | 94.98% | 114.8%
Indonesia | East Asia and Pacific | P079906 | C1 | S3 | P079906C1S3 | Estimate | 2006 | New 2L Highway |  | 46.8 | 52.23 | USD | 52.23 | 1.116
Indonesia | East Asia and Pacific | P079906 | C1 | S3 | P079906C1S3 | Actual | 2014 | New 2L Highway |  | 37.1 | 42.6 | USD | 42.6 | 1.1482
Indonesia | East Asia and Pacific | P079906 | C1 |  | P079906C1S3 | Ratio | 2006 / 2014 | New 2L Highway |  | 79.27% | 81.56% |  | 81.56% | 102.9%
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1 | Estimate | 2014 | Strengthening |  | 450 | 81.53 | USD | 81.53 | 0.18118 | x |  |  | x | x
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1 | Actual | 2014 | Strengthening |  | 193.5 | 66.29 | USD | 66.29 | 0.34258 | x |  |  | x | x
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1 | Ratio | 2014 / 2014 | Strengthening |  | 43% | 81.31% |  | 81.31% | 189.1% | x |  |  | x | x | Capacity of Counterpart; Change of project scope; Political events | Despite a high degree of project readiness and client commitment at the preparation stage, the project experienced early implementation delay partly due to delay in ratification by Parliament before effectiveness could be declared (ISR 1) and partly due to delay in tendering sub-projects under Part A (ISR 2). On the former issue, ratification was stalled due to the overall country context at the time. The Bank team was supported by the CD, who sent a letter to the MoF urging the GoI to take action towards credit signing and effectiveness; The project was able to disburse approximately 85 percent of project funds by the time of project closing. There were several restructurings. ; Increasingly difficult operating environment due to the worsening security situation: The effect of security issues on the project cannot be overstated. First, it disrupted or delayed the progress of tendering packages and performing rehabilitation works as different areas of the country became inaccessible due to insecurity. Second, it proved difficult to attract qualified international bidders for the technical assistance components as international consulting firms were reluctant to come to Baghdad. Third, price contingencies were inadequate to cover the rising cost of sourcing construction material. Fourth, the difficult operating environment and depletion of resources caused several contractors to underperform on their responsibilities, leading to work sites being vacated or subcontracted without prior approval.
Iraq | Middle East and North Africa | P087735 | C1 | S1 | P087735C1S1 | Estimate | 2014 | Strengthening | 9 | 10 | 2.5 | USD | 2.5 | 0.25
Iraq | Middle East and North Africa | P087735 | C1 | S1 | P087735C1S1 | Actual | 2014 | Strengthening | 12 | 10 | 2.4 | USD | 2.4 | 0.24
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S1 | Ratio | 2014 / 2014 | Strengthening | 133.3% | 100% | 96% |  | 96% | 96%
Iraq | Middle East and North Africa | P087735 | C1 | S10 | P087735C1S10 | Estimate | 2014 | Reconstruction |  | 41 | 18.4 | USD | 18.4 | 0.44878
Iraq | Middle East and North Africa | P087735 | C1 | S10 | P087735C1S10 | Actual | 2014 | Reconstruction | 32 | 41 | 18.3 | USD | 18.3 | 0.44634
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S10 | Ratio | 2014 / 2014 | Reconstruction |  | 100% | 99.46% |  | 99.46% | 99.46%
Iraq | Middle East and North Africa | P087735 | C1 | S11 | P087735C1S11 | Estimate | 2014 | Strengthening |  | 14.1 | 2.3 | USD | 2.3 | 0.16312
Iraq | Middle East and North Africa | P087735 | C1 | S11 | P087735C1S11 | Actual | 2014 | Strengthening | 6 | 14.1 | 2 | USD | 2 | 0.14184
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S11 | Ratio | 2014 / 2014 | Strengthening |  | 100% | 86.96% |  | 86.96% | 86.96%
Iraq | Middle East and North Africa | P087735 | C1 | S12 | P087735C1S12 | Estimate | 2014 | Strengthening |  | 12.7 | 2 | USD | 2 | 0.15748
Iraq | Middle East and North Africa | P087735 | C1 | S12 | P087735C1S12 | Actual | 2014 | Strengthening | 21 | 12.7 | 1.9 | USD | 1.9 | 0.14961
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S12 | Ratio | 2014 / 2014 | Strengthening |  | 100% | 95% |  | 95% | 95%
Iraq | Middle East and North Africa | P087735 | C1 | S13 | P087735C1S13 | Estimate | 2014 | Strengthening | 15 | 25 | 5.9 | USD | 5.9 | 0.236
Iraq | Middle East and North Africa | P087735 | C1 | S13 | P087735C1S13 | Actual | 2014 | Strengthening | 21 | 25 | 6.7 | USD | 6.7 | 0.268
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S13 | Ratio | 2014 / 2014 | Strengthening | 140% | 100% | 113.6% |  | 113.6% | 113.6%
Iraq | Middle East and North Africa | P087735 | C1 | S2 | P087735C1S2 | Estimate | 2014 | Strengthening | 12 | 11 | 2.1 | USD | 2.1 | 0.19091
Iraq | Middle East and North Africa | P087735 | C1 | S2 | P087735C1S2 | Actual | 2014 | Strengthening | 13 | 11 | 2.1 | USD | 2.1 | 0.19091
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S2 | Ratio | 2014 / 2014 | Strengthening | 108.3% | 100% | 100% |  | 100% | 100%
Iraq | Middle East and North Africa | P087735 | C1 | S3 | P087735C1S3 | Estimate | 2014 | Strengthening | 13 | 19 | 3.1 | USD | 3.1 | 0.16316
Iraq | Middle East and North Africa | P087735 | C1 | S3 | P087735C1S3 | Actual | 2014 | Strengthening | 17 | 19 | 3.3 | USD | 3.3 | 0.17368
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S3 | Ratio | 2014 / 2014 | Strengthening | 130.8% | 100% | 106.5% |  | 106.5% | 106.5%
Iraq | Middle East and North Africa | P087735 | C1 | S4 | P087735C1S4 | Estimate | 2014 | Strengthening | 6 | 10 | 1.3 | USD | 1.3 | 0.13
Iraq | Middle East and North Africa | P087735 | C1 | S4 | P087735C1S4 | Actual | 2014 | Strengthening | 6 | 10 | 1.2 | USD | 1.2 | 0.12
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S4 | Ratio | 2014 / 2014 | Strengthening | 100% | 100% | 92.31% |  | 92.31% | 92.31%
Iraq | Middle East and North Africa | P087735 | C1 | S5 | P087735C1S5 | Estimate | 2014 | Strengthening | 12 | 10 | 2.1 | USD | 2.1 | 0.21
Iraq | Middle East and North Africa | P087735 | C1 | S5 | P087735C1S5 | Actual | 2014 | Strengthening | 12 | 10 | 2.1 | USD | 2.1 | 0.21
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S5 | Ratio | 2014 / 2014 | Strengthening | 100% | 100% | 100% |  | 100% | 100%
Iraq | Middle East and North Africa | P087735 | C1 | S6 | P087735C1S6 | Estimate | 2014 | Strengthening |  | 15.5 | 2.8 | USD | 2.8 | 0.18065
Iraq | Middle East and North Africa | P087735 | C1 | S6 | P087735C1S6 | Actual | 2014 | Strengthening | 11 | 15.5 | 2.5 | USD | 2.5 | 0.16129
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S6 | Ratio | 2014 / 2014 | Strengthening |  | 100% | 89.29% |  | 89.29% | 89.29%
Iraq | Middle East and North Africa | P087735 | C1 | S7 | P087735C1S7 | Estimate | 2014 | Strengthening | 10 | 21.2 | 3.5 | USD | 3.5 | 0.16509
Iraq | Middle East and North Africa | P087735 | C1 | S7 | P087735C1S7 | Actual | 2014 | Strengthening | 9 | 21.2 | 3.4 | USD | 3.4 | 0.16038
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S7 | Ratio | 2014 / 2014 | Strengthening | 90% | 100% | 97.14% |  | 97.14% | 97.14%
Iraq | Middle East and North Africa | P087735 | C1 | S8 | P087735C1S8 | Estimate | 2014 | Strengthening |  | 20 | 4.2 | USD | 4.2 | 0.21
Iraq | Middle East and North Africa | P087735 | C1 | S8 | P087735C1S8 | Actual | 2014 | Strengthening | 33 | 20 | 4.8 | USD | 4.8 | 0.24
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S8 | Ratio | 2014 / 2014 | Strengthening |  | 100% | 114.3% |  | 114.3% | 114.3%
Iraq | Middle East and North Africa | P087735 | C1 | S9 | P087735C1S9 | Estimate | 2014 | Reconstruction |  | 41 | 18.4 | USD | 18.4 | 0.44878
Iraq | Middle East and North Africa | P087735 | C1 | S9 | P087735C1S9 | Actual | 2014 | Reconstruction | 32 | 41 | 18.3 | USD | 18.3 | 0.44634
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1S9 | Ratio | 2014 / 2014 | Reconstruction |  | 100% | 99.46% |  | 99.46% | 99.46%
Iraq | Middle East and North Africa | P087735 | C2 |  | P087735C2 | Estimate | 2014 | Widening |  | 113.5 | 40.79 | USD | 40.79 | 0.35938
Iraq | Middle East and North Africa | P087735 | C2 |  | P087735C2 | Actual | 2014 | Widening |  | 120.1 | 47.87 | USD | 47.87 | 0.39858
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C2 | Ratio | 2014 / 2014 | Widening |  | 105.8% | 117.4% |  | 117.4% | 110.9%
Iraq | Middle East and North Africa | P087735 | C2 | S1 | P087735C2S1 | Estimate | 2014 | Widening |  | 38.5 | 34.9 | USD | 34.9 | 0.90649
Iraq | Middle East and North Africa | P087735 | C2 | S1 | P087735C2S1 | Actual | 2014 | Widening | 26 | 38.5 | 40.7 | USD | 40.7 | 1.0571
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C2S1 | Ratio | 2014 / 2014 | Widening |  | 100% | 116.6% |  | 116.6% | 116.6%
Iraq | Middle East and North Africa | P087735 | C2 | S2 | P087735C2S2 | Estimate | 2014 | Reconstruction |  | 17.1 | 2 | USD | 2 | 0.11696
Iraq | Middle East and North Africa | P087735 | C2 | S2 | P087735C2S2 | Actual | 2014 | Reconstruction | 12 | 17.1 | 2 | USD | 2 | 0.11696
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C2S2 | Ratio | 2014 / 2014 | Reconstruction |  | 100% | 100% |  | 100% | 100%
Iraq | Middle East and North Africa | P087735 | C2 | S3 | P087735C2S3 | Estimate | 2014 | Surface Treatment Resurfacing |  | 27.1 | 1.8 | USD | 1.8 | 0.066421
Iraq | Middle East and North Africa | P087735 | C2 | S3 | P087735C2S3 | Actual | 2014 | Surface Treatment Resurfacing | 12 | 27.1 | 1.8 | USD | 1.8 | 0.066421
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C2S3 | Ratio | 2014 / 2014 | Surface Treatment Resurfacing |  | 100% | 100% |  | 100% | 100%
Iraq | Middle East and North Africa | P087735 | C2 | S4 | P087735C2S4 | Estimate | 2014 | Surface Treatment Resurfacing |  | 19.4 | 2.3 | USD | 2.3 | 0.11856
Iraq | Middle East and North Africa | P087735 | C2 | S4 | P087735C2S4 | Actual | 2014 | Surface Treatment Resurfacing | 12 | 19.4 | 2.2 | USD | 2.2 | 0.1134
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C2S4 | Ratio | 2014 / 2014 | Surface Treatment Resurfacing |  | 100% | 95.65% |  | 95.65% | 95.65%
Jordan | Middle East and North Africa | P081505 | C1 | S1 | P081505C1S1 | Estimate | 2004 | New 4L Expressway | 46 | 18.5 | 43.6 | USD | 43.6 | 2.3568 |  |  |  | x | x
Jordan | Middle East and North Africa | P081505 | C1 | S1 | P081505C1S1 | Actual | 2013 | New 4L Expressway |  | 18.5 | 116.1 | USD | 116.1 | 6.2757 |  |  |  | x | x
Jordan | Middle East and North Africa | P081505 | C1 |  | P081505C1S1 | Ratio | 2004 / 2013 | New 4L Expressway |  | 100% | 266.3% |  | 266.3% | 266.3% |  |  |  | x | x | Political events; Competition; Quality of estimates | repeated sabotage of the Arab Gas Pipeline in the Sinai Peninsula bringing relatively inexpensive gas from Egypt, and the need to substitute this gas with expensive liquid fuel from elsewhere to maintain electric power supplies; Retendering for section 1 due to only 2 bidders participating in initial tender; virtually all the specific forecasts proved overoptimistic
Jordan | Middle East and North Africa | P081505 | C1 | S2 | P081505C1S2 | Estimate | 2004 | New 4L Expressway | 39 | 14.5 | 34.16 | USD | 34.16 | 2.3559 |  |  |  | x | x
Jordan | Middle East and North Africa | P081505 | C1 | S2 | P081505C1S2 | Actual | 2013 | New 4L Expressway |  | 14.5 | 77 | USD | 77 | 5.3103 |  |  |  | x | x
Jordan | Middle East and North Africa | P081505 | C1 |  | P081505C1S2 | Ratio | 2004 / 2013 | New 4L Expressway |  | 100% | 225.4% |  | 225.4% | 225.4% |  |  |  | x | x | Political events; Quality of estimates; | repeated sabotage of the Arab Gas Pipeline in the Sinai Peninsula bringing relatively inexpensive gas from Egypt, and the need to substitute this gas with expensive liquid fuel from elsewhere to maintain electric power supplies; virtually all the specific forecasts proved overoptimistic;
Jordan | Middle East and North Africa | P081505 | C1 | S3 | P081505C1S3 | Estimate | 2004 | New 4L Expressway | 38 | 7 | 29.16 | USD | 29.16 | 4.1657 |  |  |  | x | x
Jordan | Middle East and North Africa | P081505 | C1 | S3 | P081505C1S3 | Actual | 2013 | New 4L Expressway |  | 7 | 86.8 | USD | 86.8 | 12.4 |  |  |  | x | x
Jordan | Middle East and North Africa | P081505 | C1 |  | P081505C1S3 | Ratio | 2004 / 2013 | New 4L Expressway |  | 100% | 297.7% |  | 297.7% | 297.7% |  |  |  | x | x | Political events; Quality of estimates; | repeated sabotage of the Arab Gas Pipeline in the Sinai Peninsula bringing relatively inexpensive gas from Egypt, and the need to substitute this gas with expensive liquid fuel from elsewhere to maintain electric power supplies; virtually all the specific forecasts proved overoptimistic;
Kazakhstan | Europe and Central Asia | Project numbers 29568 & 32463 | C1 |  | Project numbers 29568 & 32463 C1 | Estimate | 2000 | Surface Treatment Resurfacing |  | 245 | 73.62 | KAZ | 0.51798 | 0.0021142 | x |  | x
Kazakhstan | Europe and Central Asia | Project numbers 29568 & 32463 | C1 |  | Project numbers 29568 & 32463 C1 | Actual | 2007 | Surface Treatment Resurfacing |  | 221 | 111.5 | KAZ | 0.90983 | 0.0041169 | x |  | x
Kazakhstan | Europe and Central Asia | Project numbers 29568 & 32463 | C1 |  | Project numbers 29568 & 32463 C1 | Ratio | 2000 / 2007 | Surface Treatment Resurfacing |  | 90.2% | 151.5% |  | 175.7% | 194.7% | x |  | x | macroeconomic conditions | A contributing factor to cost overruns was the higher than expected price escalation for major construction inputs over a longer implementation period. Particularly, the cost of bitumen increased by 50% per annum during the period 2003–2007, and the rate of price escalation was high for steel, cement, and labor. The price escalation of 2.4% per annum estimated at appraisal was, therefore, far exceeded. (PCR p.5) - The length of the rehabilitated road was reduced due to the increased works on the main road sections as a result of very poor condition of the pavement and major bridges (PCR p. 2) | ; ; macroeconomic conditions | ; ; A contributing factor to cost overruns was the higher than expected price escalation for major construction inputs over a longer implementation period. Particularly, the cost of bitumen increased by 50% per annum during the period 2003–2007, and the rate of price escalation was high for steel, cement, and labor. The price escalation of 2.4% per annum estimated at appraisal was, therefore, far exceeded. (PCR p.5) - The length of the rehabilitated road was reduced due to the increased works on the main road sections as a result of very poor condition of the pavement and major bridges (PCR p. 2)
Kazakhstan | Europe and Central Asia | Project Number: 43439-023 | C1 |  | Project Number: 43439-023 C1 | Estimate | 2010 | Asphalt Mix Resurfacing |  | 200.5 | 271.4 | USD | 271.4 | 1.3536
Kazakhstan | Europe and Central Asia | Project Number: 43439-023 | C1 |  | Project Number: 43439-023 C1 | Actual | 2016 | Asphalt Mix Resurfacing |  | 200.5 | 163.51 | USD | 163.51 | 0.81551
Kazakhstan | Europe and Central Asia | Project Number: 43439-023 | C1 |  | Project Number: 43439-023 C1 | Ratio | 2010 / 2016 | Asphalt Mix Resurfacing |  | 100% | 60.25% |  | 60.25% | 60.25%
Kenya | Sub-Saharan Africa | P082615 | C1 | S1 | P082615C1S1 | Estimate | 2004 | Widening and Reconstruction | 28 | 35 | 14.69 | USD | 14.69 | 0.41971 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 | S1 | P082615C1S1 | Actual | 2016 | Widening and Reconstruction |  | 35 | 48.63 | USD | 48.63 | 1.3894 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 |  | P082615C1S1 | Ratio | 2004 / 2016 | Widening and Reconstruction |  | 100% | 331% |  | 331% | 331% |  |  |  | x | x | Political events; Macroeconomic conditions; Weather shocks | Post-election violence displaced about 350,000 people and led the [Project] to suspend operations in several locations due to temporal unavailability of labor; The prices of key construction materials in the international market increased, particularly steel, fuel and bitumen, resulting in high bid prices of the civil works contracts; Floods in 2006/07 caused significant deterioration in the project road sections, meaning that additional works became necessary
Kenya | Sub-Saharan Africa | P082615 | C1 | S2 | P082615C1S2 | Estimate | 2004 | Reconstruction | 39 | 55 | 27.91 | USD | 27.91 | 0.50745 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 | S2 | P082615C1S2 | Actual | 2016 | Reconstruction |  | 33 | 65.23 | USD | 65.23 | 1.9767 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 |  | P082615C1S2 | Ratio | 2004 / 2016 | Reconstruction |  | 60% | 233.7% |  | 233.7% | 389.5% |  |  |  | x | x | Political events; Macroeconomic conditions; Weather shocks | Post-election violence displaced about 350,000 people and led the [Project] to suspend operations in several locations due to temporal unavailability of labor; The prices of key construction materials in the international market increased, particularly steel, fuel and bitumen, resulting in high bid prices of the civil works contracts; Floods in 2006/07 caused significant deterioration in the project road sections, meaning that additional works became necessary
Kenya | Sub-Saharan Africa | P082615 | C1 | S3 | P082615C1S3 | Estimate | 2004 | Widening | 37 | 33 | 38.42 | USD | 38.42 | 1.1642 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 | S3 | P082615C1S3 | Actual | 2016 | Widening |  | 33 | 115.39 | USD | 115.39 | 3.4967 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 |  | P082615C1S3 | Ratio | 2004 / 2016 | Widening |  | 100% | 300.3% |  | 300.3% | 300.3% |  |  |  | x | x | Political events; Macroeconomic conditions; Weather shocks | Post-election violence displaced about 350,000 people and led the [Project] to suspend operations in several locations due to temporal unavailability of labor; The prices of key construction materials in the international market increased, particularly steel, fuel and bitumen, resulting in high bid prices of the civil works contracts; Floods in 2006/07 caused significant deterioration in the project road sections, meaning that additional works became necessary
Kenya | Sub-Saharan Africa | P082615 | C1 | S4 | P082615C1S4 | Estimate | 2004 | Reconstruction | 38 | 97 | 40.68 | USD | 40.68 | 0.41938 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 | S4 | P082615C1S4 | Actual | 2016 | Reconstruction |  | 100 | 138.04 | USD | 138.04 | 1.3804 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 |  | P082615C1S4 | Ratio | 2004 / 2016 | Reconstruction |  | 103.1% | 339.3% |  | 339.3% | 329.2% |  |  |  | x | x | Political events; Macroeconomic conditions; Weather shocks | Post-election violence displaced about 350,000 people and led the [Project] to suspend operations in several locations due to temporal unavailability of labor; The prices of key construction materials in the international market increased, particularly steel, fuel and bitumen, resulting in high bid prices of the civil works contracts; Floods in 2006/07 caused significant deterioration in the project road sections, meaning that additional works became necessary
Kenya | Sub-Saharan Africa | P082615 | C1 | S5 | P082615C1S5 | Estimate | 2004 | Reconstruction | 37 | 145 | 46.33 | USD | 46.33 | 0.31952 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 | S5 | P082615C1S5 | Actual | 2016 | Reconstruction |  | 133 | 171.68 | USD | 171.68 | 1.2908 |  |  |  | x | x
Kenya | Sub-Saharan Africa | P082615 | C1 |  | P082615C1S5 | Ratio | 2004 / 2016 | Reconstruction |  | 91.72% | 370.6% |  | 370.6% | 404% |  |  |  | x | x | Political events; Macroeconomic conditions; Weather shocks | Post-election violence displaced about 350,000 people and led the [Project] to suspend operations in several locations due to temporal unavailability of labor; The prices of key construction materials in the international market increased, particularly steel, fuel and bitumen, resulting in high bid prices of the civil works contracts; Floods in 2006/07 caused significant deterioration in the project road sections, meaning that additional works became necessary
Kenya | Sub-Saharan Africa | AfDB project P-KE-DB0-019 | C1 |  | AfDB project P-KE-DB0-019C1 | Estimate | 2010 | Reconstruction | 24 | 73 | 3831.8796 | KES | 48.3622 | 0.6625
Kenya | Sub-Saharan Africa | AfDB project P-KE-DB0-019 | C1 |  | AfDB project P-KE-DB0-019C1 | Actual | 2017 | Reconstruction | 34 | 73 | 5001.2774 | KES | 48.3823 | 0.66277
Kenya | Sub-Saharan Africa | AfDB project P-KE-DB0-019 | C1 |  | AfDB project P-KE-DB0-019C1 | Ratio | 2010 / 2017 | Reconstruction | 141.7% | 100% | 130.5% |  | 100% | 100%
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 | S1 | P107608C1S1 | Estimate | 2009 | Upgrading | 24 | 30 | 25.79 | USD | 25.79 | 0.85967
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 | S1 | P107608C1S1 | Actual | 2015 | Upgrading | 26 | 32 | 24.1 | USD | 24.1 | 0.75313
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 |  | P107608C1S1 | Ratio | 2009 / 2015 | Upgrading | 108.3% | 106.7% | 93.45% |  | 93.45% | 87.61%
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 | S2 | P107608C1S2 | Estimate | 2015 | Upgrading |  | 18 | 13.2 | USD | 13.2 | 0.73333
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 | S2 | P107608C1S2 | Actual | 2011 | Upgrading |  | 18.1 | 14.5 | USD | 14.5 | 0.8011
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 |  | P107608C1S2 | Ratio | 2015 / 2011 | Upgrading |  | 100.6% | 109.8% |  | 109.8% | 109.2%
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 |  | P050719C1 | Estimate | 2000 | Strengthening |  | 98 | 21.75 | USD | 21.75 | 0.22194
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 |  | P050719C1 | Actual | 2006 | Strengthening |  | 105 | 20.64 | USD | 20.64 | 0.19657
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 |  | P050719C1 | Ratio | 2000 / 2006 | Strengthening |  | 107.1% | 94.9% |  | 94.9% | 88.57%
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S1 | P050719C1S1 | Estimate | 2000 | Strengthening | 28 | 72 | 16.5 | USD | 16.5 | 0.22917
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S1 | P050719C1S1 | Actual | 2006 | Strengthening |  | 80 | 15.3 | USD | 15.3 | 0.19125
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 |  | P050719C1S1 | Ratio | 2000 / 2006 | Strengthening |  | 111.1% | 92.73% |  | 92.73% | 83.45%
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S2 | P050719C1S2 | Estimate | 2000 | Strengthening | 16 | 14 | 3.4 | USD | 3.4 | 0.24286
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S2 | P050719C1S2 | Actual | 2006 | Strengthening |  | 14 | 3.45 | USD | 3.45 | 0.24643
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 |  | P050719C1S2 | Ratio | 2000 / 2006 | Strengthening |  | 100% | 101.5% |  | 101.5% | 101.5%
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S3 | P050719C1S3 | Estimate | 2000 | Strengthening | 16 | 12 | 1.9 | USD | 1.9 | 0.15833
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S3 | P050719C1S3 | Actual | 2006 | Strengthening |  | 11 | 1.89 | USD | 1.89 | 0.17182
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 |  | P050719C1S3 | Ratio | 2000 / 2006 | Strengthening |  | 91.67% | 99.47% |  | 99.47% | 108.5%
Lao PDR | East Asia and Pacific | P064821 | C1 | S1 | P064821C1S1 | Estimate | 2001 | Bituminous Pavement Preventive Treatment |  | 1400 | 29.31 | USD | 29.31 | 0.020936 |  | x |  |  | x
Lao PDR | East Asia and Pacific | P064821 | C1 | S1 | P064821C1S1 | Actual | 2005 | Bituminous Pavement Preventive Treatment |  | 2762 | 32.08 | USD | 32.08 | 0.011615 |  | x |  |  | x
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S1 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 197.3% | 109.5% |  | 109.5% | 55.48% |  | x |  |  | x | Change of project scope; ; | the change in the length of civil works resulted from the threefold expansion of the ongoing maintenance program; ;
Lao PDR | East Asia and Pacific | P064821 | C1 | S10 | P064821C1S10 | Estimate | 2001 | Bituminous Pavement Preventive Treatment |  | 20 | 0.39 | USD | 0.39 | 0.0195
Lao PDR | East Asia and Pacific | P064821 | C1 | S10 | P064821C1S10 | Actual | 2005 | Bituminous Pavement Preventive Treatment |  | 20 | 0.32 | USD | 0.32 | 0.016
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S10 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% | 82.05% |  | 82.05% | 82.05%
Lao PDR | East Asia and Pacific | P064821 | C1 | S11 | P064821C1S11 | Estimate | 2001 | Gravel Resurfacing |  | 50 | 0.55 | USD | 0.55 | 0.011
Lao PDR | East Asia and Pacific | P064821 | C1 | S11 | P064821C1S11 | Actual | 2005 | Gravel Resurfacing |  | 50 | 0.46 | USD | 0.46 | 0.0092
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S11 | Ratio | 2001 / 2005 | Gravel Resurfacing |  | 100% | 83.64% |  | 83.64% | 83.64%
Lao PDR | East Asia and Pacific | P064821 | C1 | S2 | P064821C1S2 | Estimate | 2001 | Routine Maintenance |  | 15250 | 13.41 | USD | 13.41 | 0.00087934 |  | x | x |  | x
Lao PDR | East Asia and Pacific | P064821 | C1 | S2 | P064821C1S2 | Actual | 2005 | Routine Maintenance |  | 25028 | 5.72 | USD | 5.72 | 0.00022854 |  | x | x |  | x
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S2 | Ratio | 2001 / 2005 | Routine Maintenance |  | 164.1% | 42.65% |  | 42.65% | 25.99% |  | x | x |  | x | Capacity of counterpart (Procurement system); Quality of estimates; Change of project scope | lower costs were incurred due to cost effective competitive bidding procedures; much lower bid prices of maintenance works compared to the engineer's estimates; the change in the length of the civil works was made possible due to the threefold expansion of the ongoing maintenance program; the higher coverage of periodic maintenance reduced the needs for routine maintenance on some sections which led to a reduction of the actual costs for routine maintenance
Lao PDR | East Asia and Pacific | P064821 | C1 | S3 | P064821C1S3 | Estimate | 2001 | Gravel Resurfacing |  | 45 | 0.41 | USD | 0.41 | 0.0091111
Lao PDR | East Asia and Pacific | P064821 | C1 | S3 | P064821C1S3 | Actual | 2005 | Gravel Resurfacing |  | 45 | 0.34 | USD | 0.34 | 0.0075556
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S3 | Ratio | 2001 / 2005 | Gravel Resurfacing |  | 100% | 82.93% |  | 82.93% | 82.93%
Lao PDR | East Asia and Pacific | P064821 | C1 | S4 | P064821C1S4 | Estimate | 2001 | Bituminous Pavement Preventive Treatment |  | 30 | 0.7 | USD | 0.7 | 0.023333
Lao PDR | East Asia and Pacific | P064821 | C1 | S4 | P064821C1S4 | Actual | 2005 | Bituminous Pavement Preventive Treatment |  | 30 | 0.65 | USD | 0.65 | 0.021667
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S4 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% | 92.86% |  | 92.86% | 92.86%
Lao PDR | East Asia and Pacific | P064821 | C1 | S5 | P064821C1S5 | Estimate | 2001 | Bituminous Pavement Preventive Treatment |  | 50 | 0.86 | USD | 0.86 | 0.0172
Lao PDR | East Asia and Pacific | P064821 | C1 | S5 | P064821C1S5 | Actual | 2005 | Bituminous Pavement Preventive Treatment |  | 50 | 0.71 | USD | 0.71 | 0.0142
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S5 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% | 82.56% |  | 82.56% | 82.56%
Lao PDR | East Asia and Pacific | P064821 | C1 | S6 | P064821C1S6 | Estimate | 2001 | Bituminous Pavement Preventive Treatment |  | 50 | 0.98 | USD | 0.98 | 0.0196
Lao PDR | East Asia and Pacific | P064821 | C1 | S6 | P064821C1S6 | Actual | 2005 | Bituminous Pavement Preventive Treatment |  | 50 | 0.81 | USD | 0.81 | 0.0162
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S6 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% | 82.65% |  | 82.65% | 82.65%
Lao PDR | East Asia and Pacific | P064821 | C1 | S7 | P064821C1S7 | Estimate | 2001 | Gravel Resurfacing |  | 40 | 0.44 | USD | 0.44 | 0.011
Lao PDR | East Asia and Pacific | P064821 | C1 | S7 | P064821C1S7 | Actual | 2005 | Gravel Resurfacing |  | 40 | 0.37 | USD | 0.37 | 0.00925
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S7 | Ratio | 2001 / 2005 | Gravel Resurfacing |  | 100% | 84.09% |  | 84.09% | 84.09%
Lao PDR | East Asia and Pacific | P064821 | C1 | S8 | P064821C1S8 | Estimate | 2001 | Bituminous Pavement Preventive Treatment |  | 15 | 0.29 | USD | 0.29 | 0.019333
Lao PDR | East Asia and Pacific | P064821 | C1 | S8 | P064821C1S8 | Actual | 2005 | Bituminous Pavement Preventive Treatment |  | 15 | 0.24 | USD | 0.24 | 0.016
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S8 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% | 82.76% |  | 82.76% | 82.76%
Lao PDR | East Asia and Pacific | P064821 | C1 | S9 | P064821C1S9 | Estimate | 2001 | Bituminous Pavement Preventive Treatment |  | 20 | 0.39 | USD | 0.39 | 0.0195
Lao PDR | East Asia and Pacific | P064821 | C1 | S9 | P064821C1S9 | Actual | 2005 | Bituminous Pavement Preventive Treatment |  | 20 | 0.31 | USD | 0.31 | 0.0155
Lao PDR | East Asia and Pacific | P064821 | C1 |  | P064821C1S9 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% | 79.49% |  | 79.49% | 79.49%
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1 | Estimate | 2004 | Routine Maintenance | 57 | 22765 | 56.3 | USD | 56.3 | 0.0024731 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1 | Actual | 2012 | Routine Maintenance | 72 | 15560 | 102.8 | USD | 102.8 | 0.0066067 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1 | Ratio | 2004 / 2012 | Routine Maintenance | 126.3% | 68.35% | 182.6% |  | 182.6% | 267.1% |  |  |  | x | x | Weather shocks; Political events; | Flood damage caused by the Mekong River in 2008 and flooding caused by Typhoon Ketsana in 2009; the floods and landslides created undue damages to roads and bridges in many provinces, which required additional financing of over US$40 million.; A Prime Ministerial budget circular placed a threshold on the MPWT maintenance budget; setting a budget ceiling unrelated to actual need placed a significant risk on the financial and physical sustainability of the road maintenance program;
Lao PDR | East Asia and Pacific | P083543 | C1 | S1 | P083543C1S1 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 12 | 0.12 | USD | 0.12 | 0.01
Lao PDR | East Asia and Pacific | P083543 | C1 | S1 | P083543C1S1 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 12 | 0.12091 | USD | 0.12091 | 0.010076
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S1 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 100.8% |  | 100.8% | 100.8%
Lao PDR | East Asia and Pacific | P083543 | C1 | S10 | P083543C1S10 | Estimate | 2004 | Asphalt Mix Resurfacing | 12 | 7 | 0.146 | USD | 0.146 | 0.020857
Lao PDR | East Asia and Pacific | P083543 | C1 | S10 | P083543C1S10 | Actual | 2011 | Asphalt Mix Resurfacing | 12 | 7 | 0.16998 | USD | 0.16998 | 0.024283
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S10 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% | 116.4% |  | 116.4% | 116.4%
Lao PDR | East Asia and Pacific | P083543 | C1 | S11 | P083543C1S11 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 24 | 0.27 | USD | 0.27 | 0.01125
Lao PDR | East Asia and Pacific | P083543 | C1 | S11 | P083543C1S11 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 24 | 0.22249 | USD | 0.22249 | 0.0092706
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S11 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 82.41% |  | 82.41% | 82.41%
Lao PDR | East Asia and Pacific | P083543 | C1 | S12 | P083543C1S12 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 24 | 0.2 | USD | 0.2 | 0.0083333
Lao PDR | East Asia and Pacific | P083543 | C1 | S12 | P083543C1S12 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 24 | 0.13794 | USD | 0.13794 | 0.0057473
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S12 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 68.97% |  | 68.97% | 68.97%
Lao PDR | East Asia and Pacific | P083543 | C1 | S13 | P083543C1S13 | Estimate | 2004 | Asphalt Mix Resurfacing | 12 | 20 | 0.4 | USD | 0.4 | 0.02
Lao PDR | East Asia and Pacific | P083543 | C1 | S13 | P083543C1S13 | Actual | 2011 | Asphalt Mix Resurfacing | 12 | 20 | 0.30755 | USD | 0.30755 | 0.015378
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S13 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% | 76.89% |  | 76.89% | 76.89%
Lao PDR | East Asia and Pacific | P083543 | C1 | S14 | P083543C1S14 | Estimate | 2004 | Gravel Resurfacing | 12 | 24 | 0.17 | USD | 0.17 | 0.0070833
Lao PDR | East Asia and Pacific | P083543 | C1 | S14 | P083543C1S14 | Actual | 2011 | Gravel Resurfacing | 12 | 24 | 0.12388 | USD | 0.12388 | 0.0051619
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S14 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 72.87% |  | 72.87% | 72.87%
Lao PDR | East Asia and Pacific | P083543 | C1 | S15 | P083543C1S15 | Estimate | 2004 | Gravel Resurfacing | 12 | 19 | 0.12 | USD | 0.12 | 0.0063158
Lao PDR | East Asia and Pacific | P083543 | C1 | S15 | P083543C1S15 | Actual | 2011 | Gravel Resurfacing | 12 | 19 | 0.13714 | USD | 0.13714 | 0.0072177
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S15 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 114.3% |  | 114.3% | 114.3%
Lao PDR | East Asia and Pacific | P083543 | C1 | S16 | P083543C1S16 | Estimate | 2004 | Gravel Resurfacing | 12 | 57 | 0.35 | USD | 0.35 | 0.0061404
Lao PDR | East Asia and Pacific | P083543 | C1 | S16 | P083543C1S16 | Actual | 2011 | Gravel Resurfacing | 12 | 57 | 0.35654 | USD | 0.35654 | 0.0062551
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S16 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 101.9% |  | 101.9% | 101.9%
Lao PDR | East Asia and Pacific | P083543 | C1 | S17 | P083543C1S17 | Estimate | 2004 | Asphalt Mix Resurfacing | 12 | 12 | 0.24 | USD | 0.24 | 0.02
Lao PDR | East Asia and Pacific | P083543 | C1 | S17 | P083543C1S17 | Actual | 2011 | Asphalt Mix Resurfacing | 12 | 12 | 0.20007 | USD | 0.20007 | 0.016672
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S17 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% | 83.36% |  | 83.36% | 83.36%
Lao PDR | East Asia and Pacific | P083543 | C1 | S18 | P083543C1S18 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 14 | 0.15 | USD | 0.15 | 0.010714
Lao PDR | East Asia and Pacific | P083543 | C1 | S18 | P083543C1S18 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 14 | 0.13292 | USD | 0.13292 | 0.0094941
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S18 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 88.61% |  | 88.61% | 88.61%
Lao PDR | East Asia and Pacific | P083543 | C1 | S19 | P083543C1S19 | Estimate | 2004 | Gravel Resurfacing | 12 | 32 | 0.25 | USD | 0.25 | 0.0078125 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 | S19 | P083543C1S19 | Actual | 2011 | Gravel Resurfacing | 12 | 32 | 0.39508 | USD | 0.39508 | 0.012346 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S19 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 158% |  | 158% | 158% |  |  |  | x | x | Weather shocks; Political events; | Flood damage caused by the Mekong River in 2008 and flooding caused by Typhoon Ketsana in 2009; the floods and landslides created undue damages to roads and bridges in many provinces, which required additional financing of over US$40 million.; A Prime Ministerial budget circular placed a threshold on the MPWT maintenance budget; setting a budget ceiling unrelated to actual need placed a significant risk on the financial and physical sustainability of the road maintenance program;
Lao PDR | East Asia and Pacific | P083543 | C1 | S2 | P083543C1S2 | Estimate | 2004 | Asphalt Mix Resurfacing | 12 | 16 | 0.34 | USD | 0.34 | 0.02125
Lao PDR | East Asia and Pacific | P083543 | C1 | S2 | P083543C1S2 | Actual | 2011 | Asphalt Mix Resurfacing | 12 | 16 | 0.37198 | USD | 0.37198 | 0.023249
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S2 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% | 109.4% |  | 109.4% | 109.4%
Lao PDR | East Asia and Pacific | P083543 | C1 | S20 | P083543C1S20 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 31 | 0.27 | USD | 0.27 | 0.0087097
Lao PDR | East Asia and Pacific | P083543 | C1 | S20 | P083543C1S20 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 31 | 0.16953 | USD | 0.16953 | 0.0054687
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S20 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 62.79% |  | 62.79% | 62.79%
Lao PDR | East Asia and Pacific | P083543 | C1 | S21 | P083543C1S21 | Estimate | 2004 | Gravel Resurfacing | 12 | 53 | 0.22 | USD | 0.22 | 0.0041509
Lao PDR | East Asia and Pacific | P083543 | C1 | S21 | P083543C1S21 | Actual | 2011 | Gravel Resurfacing | 12 | 53 | 0.12999 | USD | 0.12999 | 0.0024526
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S21 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 59.09% |  | 59.09% | 59.09%
Lao PDR | East Asia and Pacific | P083543 | C1 | S22 | P083543C1S22 | Estimate | 2004 | Asphalt Mix Resurfacing | 12 | 8 | 0.165 | USD | 0.165 | 0.020625
Lao PDR | East Asia and Pacific | P083543 | C1 | S22 | P083543C1S22 | Actual | 2011 | Asphalt Mix Resurfacing | 12 | 8 | 0.12582 | USD | 0.12582 | 0.015728
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S22 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% | 76.26% |  | 76.26% | 76.26%
Lao PDR | East Asia and Pacific | P083543 | C1 | S23 | P083543C1S23 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 20 | 0.2 | USD | 0.2 | 0.01
Lao PDR | East Asia and Pacific | P083543 | C1 | S23 | P083543C1S23 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 20 | 0.16444 | USD | 0.16444 | 0.0082218
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S23 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 82.22% |  | 82.22% | 82.22%
Lao PDR | East Asia and Pacific | P083543 | C1 | S24 | P083543C1S24 | Estimate | 2004 | Gravel Resurfacing | 12 | 26 | 0.2 | USD | 0.2 | 0.0076923
Lao PDR | East Asia and Pacific | P083543 | C1 | S24 | P083543C1S24 | Actual | 2011 | Gravel Resurfacing | 12 | 26 | 0.16328 | USD | 0.16328 | 0.0062798
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S24 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 81.64% |  | 81.64% | 81.64%
Lao PDR | East Asia and Pacific | P083543 | C1 | S25 | P083543C1S25 | Estimate | 2004 | Gravel Resurfacing | 12 | 30 | 0.2 | USD | 0.2 | 0.0066667
Lao PDR | East Asia and Pacific | P083543 | C1 | S25 | P083543C1S25 | Actual | 2011 | Gravel Resurfacing | 12 | 30 | 0.10724 | USD | 0.10724 | 0.0035747
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S25 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 53.62% |  | 53.62% | 53.62%
Lao PDR | East Asia and Pacific | P083543 | C1 | S26 | P083543C1S26 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 39 | 0.35 | USD | 0.35 | 0.0089744
Lao PDR | East Asia and Pacific | P083543 | C1 | S26 | P083543C1S26 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 39 | 0.35428 | USD | 0.35428 | 0.009084
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S26 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 101.2% |  | 101.2% | 101.2%
Lao PDR | East Asia and Pacific | P083543 | C1 | S27 | P083543C1S27 | Estimate | 2004 | Gravel Resurfacing | 12 | 16 | 0.14 | USD | 0.14 | 0.00875
Lao PDR | East Asia and Pacific | P083543 | C1 | S27 | P083543C1S27 | Actual | 2011 | Gravel Resurfacing | 12 | 16 | 0.16004 | USD | 0.16004 | 0.010002
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S27 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 114.3% |  | 114.3% | 114.3%
Lao PDR | East Asia and Pacific | P083543 | C1 | S28 | P083543C1S28 | Estimate | 2004 | Gravel Resurfacing | 12 | 38.3 | 0.1658 | USD | 0.1658 | 0.004329 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 | S28 | P083543C1S28 | Actual | 2011 | Gravel Resurfacing | 12 | 38.3 | 0.34259 | USD | 0.34259 | 0.008945 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S28 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 206.6% |  | 206.6% | 206.6% |  |  |  | x | x | Weather shocks; Political events; | Flood damage caused by the Mekong River in 2008 and flooding caused by Typhoon Ketsana in 2009; the floods and landslides created undue damages to roads and bridges in many provinces, which required additional financing of over US$40 million.; A Prime Ministerial budget circular placed a threshold on the MPWT maintenance budget; setting a budget ceiling unrelated to actual need placed a significant risk on the financial and physical sustainability of the road maintenance program;
Lao PDR | East Asia and Pacific | P083543 | C1 | S29 | P083543C1S29 | Estimate | 2004 | Gravel Resurfacing | 12 | 30.5 | 0.132 | USD | 0.132 | 0.004328 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 | S29 | P083543C1S29 | Actual | 2011 | Gravel Resurfacing | 12 | 30.5 | 0.31079 | USD | 0.31079 | 0.01019 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S29 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 235.4% |  | 235.4% | 235.4% |  |  |  | x | x | Weather shocks; Political events; | Flood damage caused by the Mekong River in 2008 and flooding caused by Typhoon Ketsana in 2009; the floods and landslides created undue damages to roads and bridges in many provinces, which required additional financing of over US$40 million.; A Prime Ministerial budget circular placed a threshold on the MPWT maintenance budget; setting a budget ceiling unrelated to actual need placed a significant risk on the financial and physical sustainability of the road maintenance program;
Lao PDR | East Asia and Pacific | P083543 | C1 | S3 | P083543C1S3 | Estimate | 2004 | Gravel Resurfacing | 12 | 19 | 0.14 | USD | 0.14 | 0.0073684
Lao PDR | East Asia and Pacific | P083543 | C1 | S3 | P083543C1S3 | Actual | 2011 | Gravel Resurfacing | 12 | 19 | 0.082601 | USD | 0.082601 | 0.0043474
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S3 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 59% |  | 59% | 59%
Lao PDR | East Asia and Pacific | P083543 | C1 | S30 | P083543C1S30 | Estimate | 2004 | Gravel Resurfacing | 12 | 24.2 | 0.10471 | USD | 0.10471 | 0.004327
Lao PDR | East Asia and Pacific | P083543 | C1 | S30 | P083543C1S30 | Actual | 2011 | Gravel Resurfacing | 12 | 24.2 | 0.085305 | USD | 0.085305 | 0.003525
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S30 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 81.47% |  | 81.47% | 81.47%
Lao PDR | East Asia and Pacific | P083543 | C1 | S31 | P083543C1S31 | Estimate | 2004 | Gravel Resurfacing | 12 | 17 | 0.073576 | USD | 0.073576 | 0.004328
Lao PDR | East Asia and Pacific | P083543 | C1 | S31 | P083543C1S31 | Actual | 2011 | Gravel Resurfacing | 12 | 17 | 0.061404 | USD | 0.061404 | 0.003612
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S31 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 83.46% |  | 83.46% | 83.46%
Lao PDR | East Asia and Pacific | P083543 | C1 | S32 | P083543C1S32 | Estimate | 2004 | Gravel Resurfacing | 12 | 44.3 | 0.19173 | USD | 0.19173 | 0.004328
Lao PDR | East Asia and Pacific | P083543 | C1 | S32 | P083543C1S32 | Actual | 2011 | Gravel Resurfacing | 12 | 44.3 | 0.22624 | USD | 0.22624 | 0.005107
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S32 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 118% |  | 118% | 118%
Lao PDR | East Asia and Pacific | P083543 | C1 | S33 | P083543C1S33 | Estimate | 2004 | Gravel Resurfacing | 12 | 43 | 0.1861 | USD | 0.1861 | 0.004328
Lao PDR | East Asia and Pacific | P083543 | C1 | S33 | P083543C1S33 | Actual | 2011 | Gravel Resurfacing | 12 | 43 | 0.20447 | USD | 0.20447 | 0.004755
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S33 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 109.9% |  | 109.9% | 109.9%
Lao PDR | East Asia and Pacific | P083543 | C1 | S34 | P083543C1S34 | Estimate | 2004 | Gravel Resurfacing | 12 | 11 | 0.047597 | USD | 0.047597 | 0.004327 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 | S34 | P083543C1S34 | Actual | 2011 | Gravel Resurfacing | 12 | 11 | 0.0759 | USD | 0.0759 | 0.0069 |  |  |  | x | x
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S34 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 159.5% |  | 159.5% | 159.5% |  |  |  | x | x | Weather shocks; Political events; | Flood damage caused by the Mekong River in 2008 and flooding caused by Typhoon Ketsana in 2009; the floods and landslides created undue damages to roads and bridges in many provinces, which required additional financing of over US$40 million.; A Prime Ministerial budget circular placed a threshold on the MPWT maintenance budget; setting a budget ceiling unrelated to actual need placed a significant risk on the financial and physical sustainability of the road maintenance program;
Lao PDR | East Asia and Pacific | P083543 | C1 | S35 | P083543C1S35 | Estimate | 2004 | Gravel Resurfacing | 12 | 16.5 | 0.071429 | USD | 0.071429 | 0.004329
Lao PDR | East Asia and Pacific | P083543 | C1 | S35 | P083543C1S35 | Actual | 2011 | Gravel Resurfacing | 12 | 16.5 | 0.082104 | USD | 0.082104 | 0.004976
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S35 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 114.9% |  | 114.9% | 114.9%
Lao PDR | East Asia and Pacific | P083543 | C1 | S36 | P083543C1S36 | Estimate | 2004 | Gravel Resurfacing | 12 | 30.6 | 0.13241 | USD | 0.13241 | 0.004327
Lao PDR | East Asia and Pacific | P083543 | C1 | S36 | P083543C1S36 | Actual | 2011 | Gravel Resurfacing | 12 | 30.6 | 0.13155 | USD | 0.13155 | 0.004299
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S36 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 99.35% |  | 99.35% | 99.35%
Lao PDR | East Asia and Pacific | P083543 | C1 | S37 | P083543C1S37 | Estimate | 2004 | Asphalt Mix Resurfacing | 12 | 17.8 | 0.57195 | USD | 0.57195 | 0.032132
Lao PDR | East Asia and Pacific | P083543 | C1 | S37 | P083543C1S37 | Actual | 2011 | Asphalt Mix Resurfacing | 12 | 17.8 | 0.57676 | USD | 0.57676 | 0.032402
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S37 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% | 100.8% |  | 100.8% | 100.8%
Lao PDR | East Asia and Pacific | P083543 | C1 | S38 | P083543C1S38 | Estimate | 2004 | Gravel Resurfacing | 12 | 4.3 | 0.018585 | USD | 0.018585 | 0.004322
Lao PDR | East Asia and Pacific | P083543 | C1 | S38 | P083543C1S38 | Actual | 2011 | Gravel Resurfacing | 12 | 4.3 | 0.026273 | USD | 0.026273 | 0.00611
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S38 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 141.4% |  | 141.4% | 141.4%
Lao PDR | East Asia and Pacific | P083543 | C1 | S39 | P083543C1S39 | Estimate | 2004 | Gravel Resurfacing | 12 | 90.5 | 0.3915 | USD | 0.3915 | 0.004326
Lao PDR | East Asia and Pacific | P083543 | C1 | S39 | P083543C1S39 | Actual | 2011 | Gravel Resurfacing | 12 | 90.5 | 0.49956 | USD | 0.49956 | 0.00552
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S39 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 127.6% |  | 127.6% | 127.6%
Lao PDR | East Asia and Pacific | P083543 | C1 | S4 | P083543C1S4 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 24 | 0.23 | USD | 0.23 | 0.0095833
Lao PDR | East Asia and Pacific | P083543 | C1 | S4 | P083543C1S4 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 24 | 0.33329 | USD | 0.33329 | 0.013887
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S4 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 144.9% |  | 144.9% | 144.9%
Lao PDR | East Asia and Pacific | P083543 | C1 | S40 | P083543C1S40 | Estimate | 2004 | Gravel Resurfacing | 12 | 33.4 | 0.14449 | USD | 0.14449 | 0.004326
Lao PDR | East Asia and Pacific | P083543 | C1 | S40 | P083543C1S40 | Actual | 2011 | Gravel Resurfacing | 12 | 33.4 | 0.18928 | USD | 0.18928 | 0.005667
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S40 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 131% |  | 131% | 131%
Lao PDR | East Asia and Pacific | P083543 | C1 | S5 | P083543C1S5 | Estimate | 2004 | Surface Treatment Resurfacing | 12 | 17 | 0.17 | USD | 0.17 | 0.01
Lao PDR | East Asia and Pacific | P083543 | C1 | S5 | P083543C1S5 | Actual | 2011 | Surface Treatment Resurfacing | 12 | 17 | 0.17722 | USD | 0.17722 | 0.010425
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S5 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% | 104.2% |  | 104.2% | 104.2%
Lao PDR | East Asia and Pacific | P083543 | C1 | S6 | P083543C1S6 | Estimate | 2004 | Asphalt Mix Resurfacing | 12 | 8 | 0.165 | USD | 0.165 | 0.020625
Lao PDR | East Asia and Pacific | P083543 | C1 | S6 | P083543C1S6 | Actual | 2011 | Asphalt Mix Resurfacing | 12 | 8 | 0.18325 | USD | 0.18325 | 0.022906
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S6 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% | 111.1% |  | 111.1% | 111.1%
Lao PDR | East Asia and Pacific | P083543 | C1 | S7 | P083543C1S7 | Estimate | 2004 | Gravel Resurfacing | 12 | 19 | 0.15 | USD | 0.15 | 0.0078947
Lao PDR | East Asia and Pacific | P083543 | C1 | S7 | P083543C1S7 | Actual | 2011 | Gravel Resurfacing | 12 | 19 | 0.11315 | USD | 0.11315 | 0.0059553
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S7 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 75.43% |  | 75.43% | 75.43%
Lao PDR | East Asia and Pacific | P083543 | C1 | S8 | P083543C1S8 | Estimate | 2004 | Gravel Resurfacing | 12 | 32 | 0.25 | USD | 0.25 | 0.0078125
Lao PDR | East Asia and Pacific | P083543 | C1 | S8 | P083543C1S8 | Actual | 2011 | Gravel Resurfacing | 12 | 32 | 0.21797 | USD | 0.21797 | 0.0068116
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S8 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 87.19% |  | 87.19% | 87.19%
Lao PDR | East Asia and Pacific | P083543 | C1 | S9 | P083543C1S9 | Estimate | 2004 | Gravel Resurfacing | 12 | 32 | 0.4 | USD | 0.4 | 0.0125
Lao PDR | East Asia and Pacific | P083543 | C1 | S9 | P083543C1S9 | Actual | 2011 | Gravel Resurfacing | 12 | 32 | 0.4059 | USD | 0.4059 | 0.012684
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1S9 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% | 101.5% |  | 101.5% | 101.5%
Lesotho | Sub-Saharan Africa | P075566 | C1 |  | P075566C1 | Estimate | 2006 | Strengthening |  | 53 | 21.25 | USD | 21.25 | 0.40094 |  | x |  |  | x
Lesotho | Sub-Saharan Africa | P075566 | C1 |  | P075566C1 | Actual | 2015 | Strengthening |  | 110 | 63.86 | USD | 63.86 | 0.58055 |  | x |  |  | x
Lesotho | Sub-Saharan Africa | P075566 | C1 |  | P075566C1 | Ratio | 2006 / 2015 | Strengthening |  | 207.5% | 300.5% |  | 300.5% | 144.8% |  | x |  |  | x | Change of project scope; ; | Under the Additional Financing it was originally intended to apply periodic maintenance (resealing and repairs) to two sections of road (64 km) – Nyene-Makhoroane and Teyateyaneng-Mapoteng Junction. However, after heavy damage to both roads due to extensive flooding complete rehabilitation became necessary. Since there was insufficient IDA funding for the whole 64 km, the Bank focused on the first lot (20 km) of the NyeneMakhoroane road, and GOL undertook to cover the costs of the latter (17 km) as well as the Teyateyaneng-Mapoteng road.; ;
Lesotho | Sub-Saharan Africa | AfDB loan number: CS/LES/TR/86/18 | C1 |  | AfDB loan number: CS/LES/TR/86/18 C1 | Estimate | 1985 | Upgrading | 24 | 22 | 13.2934 | ZAR | 5.9665 | 0.2712 | x |  | x
Lesotho | Sub-Saharan Africa | AfDB loan number: CS/LES/TR/86/18 | C1 |  | AfDB loan number: CS/LES/TR/86/18 C1 | Actual | 1991 | Upgrading | 35 | 22 | 30.6144 | ZAR | 11.0881 | 0.50401 | x |  | x
Lesotho | Sub-Saharan Africa | AfDB loan number: CS/LES/TR/86/18 | C1 |  | AfDB loan number: CS/LES/TR/86/18 C1 | Ratio | 1985 / 1991 | Upgrading | 145.8% | 100% | 230.3% |  | 185.8% | 185.8% | x |  | x | Quality of estimates |  | ; ; Quality of estimates
Lesotho | Sub-Saharan Africa | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 | C1 |  | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 C1 | Estimate | 1987 | Upgrading | 24 | 109 | 57.4662 | ZAR | 28.225 | 0.25895 | x |  | x
Lesotho | Sub-Saharan Africa | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 | C1 |  | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 C1 | Actual | 1997 | Upgrading | 84 | 109 | 336.6647 | ZAR | 73.0768 | 0.67043 | x |  | x
Lesotho | Sub-Saharan Africa | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 | C1 |  | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 C1 | Ratio | 1987 / 1997 | Upgrading | 350% | 100% | 585.8% |  | 258.9% | 258.9% | x |  | x | change of project scope | The actual project cost exceeded the appraisal estimate mainly because of changes in the design (p.15) | ; ; change of project scope | ; ; The actual project cost exceeded the appraisal estimate mainly because of changes in the design (p.15)
Macedonia, FYR | Europe and Central Asia | P091723 | C1 |  | P091723C1 | Estimate | 2007 | Widening | 26 | 7.3 | 13.11 | USD | 13.11 | 1.7959
Macedonia, FYR | Europe and Central Asia | P091723 | C1 |  | P091723C1 | Actual | 2012 | Widening | 33 | 7.3 | 18.15 | USD | 18.15 | 2.4863
Macedonia, FYR | Europe and Central Asia | P091723 | C1 |  | P091723C1 | Ratio | 2007 / 2012 | Widening | 126.9% | 100% | 138.4% |  | 138.4% | 138.4%
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S1 | P107840C1S1 | Estimate | 2008 | Reconstruction |  | 15.2 | 1.38 | EUR | 2.0909 | 0.13756
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S1 | P107840C1S1 | Actual | 2016 | Reconstruction | 25 | 19.1 | 1.67 | EUR | 2.5098 | 0.1314
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S1 | Ratio | 2008 / 2016 | Reconstruction |  | 125.7% | 121% |  | 120% | 95.52% | [5 empty] | Capacity of Counterpart; ; | Staffing constraints of the Implementation Agency17: PESR’s staffing levels were not fully sufficient at times to manage the Project and meet its other responsibilities including managing a parallel support project funded by the EBRD and projects funded from the Macedonian National budget. PESR’s oversight of local roads rehabilitation, which is outside its mandate, consumed more of its time than necessary due to large number of road projects and relatively weak design capacity of some municipalities. The recruitment of additional qualified staff, particularly engineers, was constrained by their unavailability in the market. Only by 2011, PESR18 had increased the number of engineers in its employment to a sufficient level, so that the additional work load did not significantly affect PESR’s project management capabilities. Quality of design and works: The lack of detailed design for regional road rehabilitation led to prolonged implementation periods for selected roads. Initially, the typical designs used did not include full considerations of road safety, therefore requiring additional enhancements – i.e. road signs, marking and guardrails. Upon revealing these shortcoming during project supervision of ongoing works, the Bank team engaged a road safety consultant to prepare road safety audits to include necessary road interventions into the scope of works. The opportunity for design improvement was used not just for mitigating purposes, but also for introducing modern approaches to road safety by complying with newly adopted Guidelines for road safety developed in line with EU regulations. A close cooperation between PESR and the Bank resulted in the road safety interventions being incorporated in the ongoing rehabilitation works and in a standalone initiative - a Road Safety Demonstration Road Project that was added for demonstration purposes of good practices in road safety.; ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S10 | P107840C1S10 | Estimate | 2008 | Reconstruction |  | 18.1 | 1.65 | EUR | 2.5 | 0.13812
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S10 | P107840C1S10 | Actual | 2016 | Reconstruction | 20 | 13.2 | 1.47 | EUR | 2.2092 | 0.16736
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S10 | Ratio | 2008 / 2016 | Reconstruction |  | 72.93% | 89.09% |  | 88.37% | 121.2% | [5 empty] | ; Quality of estimates; | ; The economic analysis done at appraisal was carried out for the Regional roads component, for which specific road sections have been identified. The analysis was done using the Highway Design and Maintenance Standards Model (HDM-III) comparing the rehabilitation alternative (the “project scenario”) to a base case (or “do minimum”) alternative. According to ICR's Economic and Financial Anlaysis sections on pp. 35-37, the ratio of the actual per estimated rehabilitation costs per km varies from 0.59 to 2.02. ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S11 | P107840C1S11 | Estimate | 2008 | Reconstruction |  | 28.1 | 2.74 | EUR | 4.1515 | 0.14774
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S11 | P107840C1S11 | Actual | 2016 | Reconstruction | 25 | 24.4 | 2.17 | EUR | 3.2612 | 0.13366
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S11 | Ratio | 2008 / 2016 | Reconstruction |  | 86.83% | 79.2% |  | 78.55% | 90.47% | [5 empty] | Capacity of Counterpart; Quality of estimates; | Staffing constraints of the Implementation Agency17: PESR’s staffing levels were not fully sufficient at times to manage the Project and meet its other responsibilities including managing a parallel support project funded by the EBRD and projects funded from the Macedonian National budget. PESR’s oversight of local roads rehabilitation, which is outside its mandate, consumed more of its time than necessary due to large number of road projects and relatively weak design capacity of some municipalities. The recruitment of additional qualified staff, particularly engineers, was constrained by their unavailability in the market. Only by 2011, PESR18 had increased the number of engineers in its employment to a sufficient level, so that the additional work load did not significantly affect PESR’s project management capabilities. Quality of design and works: The lack of detailed design for regional road rehabilitation led to prolonged implementation periods for selected roads. Initially, the typical designs used did not include full considerations of road safety, therefore requiring additional enhancements – i.e. road signs, marking and guardrails. Upon revealing these shortcoming during project supervision of ongoing works, the Bank team engaged a road safety consultant to prepare road safety audits to include necessary road interventions into the scope of works. The opportunity for design improvement was used not just for mitigating purposes, but also for introducing modern approaches to road safety by complying with newly adopted Guidelines for road safety developed in line with EU regulations. A close cooperation between PESR and the Bank resulted in the road safety interventions being incorporated in the ongoing rehabilitation works and in a standalone initiative - a Road Safety Demonstration Road Project that was added for demonstration purposes of good practices in road safety.; The economic analysis done at appraisal was carried out for the Regional roads component, for which specific road sections have been identified. The analysis was done using the Highway Design and Maintenance Standards Model (HDM-III) comparing the rehabilitation alternative (the “project scenario”) to a base case (or “do minimum”) alternative. According to ICR's Economic and Financial Anlaysis sections on pp. 35-37, the ratio of the actual per estimated rehabilitation costs per km varies from 0.59 to 2.02. ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S2 | P107840C1S2 | Estimate | 2008 | Reconstruction |  | 38 | 3.46 | EUR | 5.2424 | 0.13796
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S2 | P107840C1S2 | Actual | 2016 | Reconstruction | 28 | 35.4 | 2.45 | EUR | 3.682 | 0.10401
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S2 | Ratio | 2008 / 2016 | Reconstruction |  | 93.16% | 70.81% |  | 70.23% | 75.39% | [5 empty] | Capacity of Counterpart; ; | Staffing constraints of the Implementation Agency17: PESR’s staffing levels were not fully sufficient at times to manage the Project and meet its other responsibilities including managing a parallel support project funded by the EBRD and projects funded from the Macedonian National budget. PESR’s oversight of local roads rehabilitation, which is outside its mandate, consumed more of its time than necessary due to large number of road projects and relatively weak design capacity of some municipalities. The recruitment of additional qualified staff, particularly engineers, was constrained by their unavailability in the market. Only by 2011, PESR18 had increased the number of engineers in its employment to a sufficient level, so that the additional work load did not significantly affect PESR’s project management capabilities. Quality of design and works: The lack of detailed design for regional road rehabilitation led to prolonged implementation periods for selected roads. Initially, the typical designs used did not include full considerations of road safety, therefore requiring additional enhancements – i.e. road signs, marking and guardrails. Upon revealing these shortcoming during project supervision of ongoing works, the Bank team engaged a road safety consultant to prepare road safety audits to include necessary road interventions into the scope of works. The opportunity for design improvement was used not just for mitigating purposes, but also for introducing modern approaches to road safety by complying with newly adopted Guidelines for road safety developed in line with EU regulations. A close cooperation between PESR and the Bank resulted in the road safety interventions being incorporated in the ongoing rehabilitation works and in a standalone initiative - a Road Safety Demonstration Road Project that was added for demonstration purposes of good practices in road safety.; ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S3 | P107840C1S3 | Estimate | 2008 | Reconstruction |  | 27.1 | 2.47 | EUR | 3.7424 | 0.1381
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S3 | P107840C1S3 | Actual | 2016 | Reconstruction | 8 | 33.4 | 3.06 | EUR | 4.5987 | 0.13769
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S3 | Ratio | 2008 / 2016 | Reconstruction |  | 123.2% | 123.9% |  | 122.9% | 99.7% | [5 empty] | ; Quality of estimates; | ; The economic analysis done at appraisal was carried out for the Regional roads component, for which specific road sections have been identified. The analysis was done using the Highway Design and Maintenance Standards Model (HDM-III) comparing the rehabilitation alternative (the “project scenario”) to a base case (or “do minimum”) alternative. According to ICR's Economic and Financial Anlaysis sections on pp. 35-37, the ratio of the actual per estimated rehabilitation costs per km varies from 0.59 to 2.02. ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S4 | P107840C1S4 | Estimate | 2008 | Reconstruction |  | 11.5 | 1.35 | EUR | 2.0455 | 0.17787
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S4 | P107840C1S4 | Actual | 2016 | Reconstruction | 8 | 14.3 | 0.99 | EUR | 1.4878 | 0.10404
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S4 | Ratio | 2008 / 2016 | Reconstruction |  | 124.3% | 73.33% |  | 72.74% | 58.5% | [5 empty] | Capacity of Counterpart; Quality of estimates; | Staffing constraints of the Implementation Agency17: PESR’s staffing levels were not fully sufficient at times to manage the Project and meet its other responsibilities including managing a parallel support project funded by the EBRD and projects funded from the Macedonian National budget. PESR’s oversight of local roads rehabilitation, which is outside its mandate, consumed more of its time than necessary due to large number of road projects and relatively weak design capacity of some municipalities. The recruitment of additional qualified staff, particularly engineers, was constrained by their unavailability in the market. Only by 2011, PESR18 had increased the number of engineers in its employment to a sufficient level, so that the additional work load did not significantly affect PESR’s project management capabilities. Quality of design and works: The lack of detailed design for regional road rehabilitation led to prolonged implementation periods for selected roads. Initially, the typical designs used did not include full considerations of road safety, therefore requiring additional enhancements – i.e. road signs, marking and guardrails. Upon revealing these shortcoming during project supervision of ongoing works, the Bank team engaged a road safety consultant to prepare road safety audits to include necessary road interventions into the scope of works. The opportunity for design improvement was used not just for mitigating purposes, but also for introducing modern approaches to road safety by complying with newly adopted Guidelines for road safety developed in line with EU regulations. A close cooperation between PESR and the Bank resulted in the road safety interventions being incorporated in the ongoing rehabilitation works and in a standalone initiative - a Road Safety Demonstration Road Project that was added for demonstration purposes of good practices in road safety.; The economic analysis done at appraisal was carried out for the Regional roads component, for which specific road sections have been identified. The analysis was done using the Highway Design and Maintenance Standards Model (HDM-III) comparing the rehabilitation alternative (the “project scenario”) to a base case (or “do minimum”) alternative. According to ICR's Economic and Financial Anlaysis sections on pp. 35-37, the ratio of the actual per estimated rehabilitation costs per km varies from 0.59 to 2.02. ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S5 | P107840C1S5 | Estimate | 2008 | Reconstruction |  | 25.3 | 2.3 | EUR | 3.4848 | 0.13774
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S5 | P107840C1S5 | Actual | 2016 | Reconstruction | 25 | 25.5 | 2.98 | EUR | 4.4785 | 0.17563
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S5 | Ratio | 2008 / 2016 | Reconstruction |  | 100.8% | 129.6% |  | 128.5% | 127.5% | [5 empty] | Capacity of Counterpart; ; | Staffing constraints of the Implementation Agency17: PESR’s staffing levels were not fully sufficient at times to manage the Project and meet its other responsibilities including managing a parallel support project funded by the EBRD and projects funded from the Macedonian National budget. PESR’s oversight of local roads rehabilitation, which is outside its mandate, consumed more of its time than necessary due to large number of road projects and relatively weak design capacity of some municipalities. The recruitment of additional qualified staff, particularly engineers, was constrained by their unavailability in the market. Only by 2011, PESR18 had increased the number of engineers in its employment to a sufficient level, so that the additional work load did not significantly affect PESR’s project management capabilities. Quality of design and works: The lack of detailed design for regional road rehabilitation led to prolonged implementation periods for selected roads. Initially, the typical designs used did not include full considerations of road safety, therefore requiring additional enhancements – i.e. road signs, marking and guardrails. Upon revealing these shortcoming during project supervision of ongoing works, the Bank team engaged a road safety consultant to prepare road safety audits to include necessary road interventions into the scope of works. The opportunity for design improvement was used not just for mitigating purposes, but also for introducing modern approaches to road safety by complying with newly adopted Guidelines for road safety developed in line with EU regulations. A close cooperation between PESR and the Bank resulted in the road safety interventions being incorporated in the ongoing rehabilitation works and in a standalone initiative - a Road Safety Demonstration Road Project that was added for demonstration purposes of good practices in road safety.; ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S6 | P107840C1S6 | Estimate | 2008 | Reconstruction |  | 22 | 2 | EUR | 3.0303 | 0.13774 |  |  |  | x | x
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S6 | P107840C1S6 | Actual | 2016 | Reconstruction | 6 | 24.2 | 4.45 | EUR | 6.6877 | 0.27635 |  |  |  | x | x
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S6 | Ratio | 2008 / 2016 | Reconstruction |  | 110% | 222.5% |  | 220.7% | 200.6% |  |  |  | x | x | Capacity of Counterpart; Quality of estimates; Weather shocks | The counterpart's staffing levels were not fully sufficient at times to manage the Project and meet its other responsibilities including managing a parallel support project funded by the EBRD and projects funded from the Macedonian National budget.; The lack of detailed design for regional road rehabilitation led to prolonged implementation periods for selected roads.; During 2010, the country faced several cases of landslides and erosion negatively affecting the road network as a result of extraordinary periodic heavy rainfall.
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S7 | P107840C1S7 | Estimate | 2008 | Reconstruction |  | 27.8 | 3.61 | EUR | 5.4697 | 0.19675
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S7 | P107840C1S7 | Actual | 2016 | Reconstruction | 26 | 38.2 | 3.98 | EUR | 5.9814 | 0.15658
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S7 | Ratio | 2008 / 2016 | Reconstruction |  | 137.4% | 110.2% |  | 109.4% | 79.58%
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S8 | P107840C1S8 | Estimate | 2008 | Reconstruction |  | 36 | 3.28 | EUR | 4.9697 | 0.13805
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S8 | P107840C1S8 | Actual | 2016 | Reconstruction | 26 | 37 | 3.86 | EUR | 5.801 | 0.15678
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S8 | Ratio | 2008 / 2016 | Reconstruction |  | 102.8% | 117.7% |  | 116.7% | 113.6%
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S9 | P107840C1S9 | Estimate | 2008 | Reconstruction |  | 25.8 | 3.35 | EUR | 5.0758 | 0.19673
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S9 | P107840C1S9 | Actual | 2016 | Reconstruction | 20 | 18.8 | 1.52 | EUR | 2.2843 | 0.12151
Macedonia, FYR | Europe and Central Asia | P107840 | C1 |  | P107840C1S9 | Ratio | 2008 / 2016 | Reconstruction |  | 72.87% | 45.37% |  | 45% | 61.76%
Madagascar | Sub-Saharan Africa | P073689 | C1 |  | P073689C1 | Estimate | 2002 | Reconstruction |  | 3000 | 30 | USD | 30 | 0.01 | x |  |  | x | x
Madagascar | Sub-Saharan Africa | P073689 | C1 |  | P073689C1 | Actual | 2013 | Reconstruction |  | 1400 | 28 | USD | 28 | 0.02 | x |  |  | x | x
Madagascar | Sub-Saharan Africa | P073689 | C1 |  | P073689C1 | Ratio | 2002 / 2013 | Reconstruction |  | 46.67% | 93.33% |  | 93.33% | 200% | x |  |  | x | x | Change of project scope ; ; | full rehabilitation was undertaken for the rural roads instead of the agreed basic access standard which caused an increase in the cost per km thus leading to only about 1400 km of rural roads being rehabilitated against the original target of 3000 km; ;
Madagascar | Sub-Saharan Africa | P082806 | C1 | S1 | P082806C1S1 | Estimate | 2003 | Asphalt Mix Resurfacing | 24 | 249 | 6.6901 | USD | 6.6901 | 0.026868 |  |  |  | x | x
Madagascar | Sub-Saharan Africa | P082806 | C1 | S1 | P082806C1S1 | Actual | 2013 | Asphalt Mix Resurfacing | 39 | 314.5 | 42.6795 | USD | 42.6795 | 0.13571 |  |  |  | x | x
Madagascar | Sub-Saharan Africa | P082806 | C1 |  | P082806C1S1 | Ratio | 2003 / 2013 | Asphalt Mix Resurfacing | 162.5% | 126.3% | 637.9% |  | 637.9% | 505.1% |  |  |  | x | x | ; Weather shocks; Macroeconomic conditions | ; Two cyclones and an unusual heavy rain created heavy damages; repairs had to be undertaken and financed by the contract. ; Upward contract price revision due mainly to the substantial gasoline price increase
Madagascar | Sub-Saharan Africa | P082806 | C1 | S2 | P082806C1S2 | Estimate | 2003 | Asphalt Mix Resurfacing | 17 | 295 | 7.9261 | USD | 7.9261 | 0.026868 | x |  |  | x | x
Madagascar | Sub-Saharan Africa | P082806 | C1 | S2 | P082806C1S2 | Actual | 2013 | Asphalt Mix Resurfacing | 17 | 143.9 | 15.0672 | USD | 15.0672 | 0.10471 | x |  |  | x | x
Madagascar | Sub-Saharan Africa | P082806 | C1 |  | P082806C1S2 | Ratio | 2003 / 2013 | Asphalt Mix Resurfacing | 100% | 48.78% | 190.1% |  | 190.1% | 389.7% | x |  |  | x | x | Weather shocks; Change of project scope; Macroeconomic conditions | Two cyclones and an unusual heavy rain created heavy damages; repairs had to be undertaken and financed by the contract. ; The change in the length of the civil works actually executed on RN2 and RN7 roads is due to an adjustment of the scope of activities during the January 2006 restructuring to reflect a shift in priorities; Upward contract price revision due mainly to the substantial gasoline price increase
Madagascar | Sub-Saharan Africa | P082806 | C1 | S3 | P082806C1S3 | Estimate | 2003 | Gravel Resurfacing | 36 | 181 | 59.3278 | USD | 59.3278 | 0.32778 |  |  | x |  | x
Madagascar | Sub-Saharan Africa | P082806 | C1 | S3 | P082806C1S3 | Actual | 2013 | Gravel Resurfacing | 10 | 183 | 5.8617 | USD | 5.8617 | 0.032031 |  |  | x |  | x
Madagascar | Sub-Saharan Africa | P082806 | C1 |  | P082806C1S3 | Ratio | 2003 / 2013 | Gravel Resurfacing | 27.78% | 101.1% | 9.88% |  | 9.88% | 9.772% |  |  | x |  | x | ; Change of project scope; | ; The actual cost is much less than the estimated cost because the type of work carried out on that road was much cheaper than the type of work initially planned. At execution, the work was “downgraded” from paving the road to doing spot improvements; during the negotiation of a second contract, the available budget was found to be insufficient;
Madagascar | Sub-Saharan Africa | P052208 | C1 | S1 | P052208C1S1 | Estimate | 2000 | Surface Treatment Resurfacing |  | 527 | 9.4 | USD | 9.4 | 0.017837 |  |  |  | x | x
Madagascar | Sub-Saharan Africa | P052208 | C1 | S1 | P052208C1S1 | Actual | 2006 | Surface Treatment Resurfacing |  | 527 | 20.9 | USD | 20.9 | 0.039658 |  |  |  | x | x
Madagascar | Sub-Saharan Africa | P052208 | C1 |  | P052208C1S1 | Ratio | 2000 / 2006 | Surface Treatment Resurfacing |  | 100% | 222.3% |  | 222.3% | 222.3% |  |  |  | x | x | Political events ; Weather shocks ; Macroeconomic conditions | an economic crisis ensued as a result of the political crisis over the outcome of the presidential elections in December 2001; extra-costs were incurred for additional works to rehabilitate the cyclone damaged works in progress, and for compensations to contractors ; cost fluctuations (inflation, international oil price, valuation of the national currency)
Malawi | Sub-Saharan Africa | AfDB loan F/MLW/AGR(RD)/87/15 | C1 |  | AfDB loan F/MLW/AGR(RD)/87/15C1 | Estimate | 1987 | Upgrading |  | 62 | 1.015 | MWK | 0.46136 | 0.0074413 | x |  | x
Malawi | Sub-Saharan Africa | AfDB loan F/MLW/AGR(RD)/87/15 | C1 |  | AfDB loan F/MLW/AGR(RD)/87/15C1 | Actual | 1999 | Upgrading |  | 65 | 1.894 | MWK | 0.042967 | 0.00066104 | x |  | x
Malawi | Sub-Saharan Africa | AfDB loan F/MLW/AGR(RD)/87/15 | C1 |  | AfDB loan F/MLW/AGR(RD)/87/15C1 | Ratio | 1987 / 1999 | Upgrading |  | 104.8% | 186.6% |  | 9.313% | 8.883% | x |  | x | Macroeconomic conditions | It should be noted that devaluation of the local currency over the implementation period of the project more than doubled project costs when measured in MWK (PCR p. 3). Instead of improving five roads, totalling 62 km, the project improved four roads, totalling 65 km, exceeding the projected target by nearly 5% while remaining within the original budget [when costs are calculated using the UA currency (AfDB currency)] (PCR p.6). | ; ; Macroeconomic conditions | ; ; It should be noted that devaluation of the local currency over the implementation period of the project more than doubled project costs when measured in MWK (PCR p. 3). Instead of improving five roads, totalling 62 km, the project improved four roads, totalling 65 km, exceeding the projected target by nearly 5% while remaining within the original budget [when costs are calculated using the UA currency (AfDB currency)] (PCR p.6).
Mali | Sub-Saharan Africa | P079749_2 | C1 | S2 | P079749_2C1S2 | Estimate | 2008 | Asphalt Mix Resurfacing |  | 154 | 4 | USD | 4 | 0.025974 |  |  |  | x | x
Mali | Sub-Saharan Africa | P079749_2 | C1 | S2 | P079749_2C1S2 | Actual | 2015 | Asphalt Mix Resurfacing | 47 | 199 | 27.6 | USD | 27.6 | 0.13869 |  |  |  | x | x
Mali | Sub-Saharan Africa | P079749_2 | C1 |  | P079749_2C1S2 | Ratio | 2008 / 2015 | Asphalt Mix Resurfacing |  | 129.2% | 690% |  | 690% | 534% |  |  |  | x | x | Quality of estimates; ; | The estimate provided in the ICR on p. 43 has an error/typo and is too low. In addition, the estimated cost and the actual cost compare different length of roads. While the estimated cost includes Bamako – Bougouni road (about 154 km), the actual cost includes (i) part of the rehabilitation of the Bamako-Bougouni (154 km) section of the Corridor and (ii) rehabilitation and strengthening of the Sikasso-Heremakono (45 km) section of the corridor. Moreover, the actual cost includes additional activities apart from the road work (supervision, etc).; ;
Mali | Sub-Saharan Africa | P090075 | C1 |  | P090075C1 | Estimate | 2007 | Gravel Resurfacing |  | 2150 | 81 | USD | 81 | 0.037674
Mali | Sub-Saharan Africa | P090075 | C1 |  | P090075C1 | Actual | 2016 | Gravel Resurfacing | 37 | 2485 | 76.77 | USD | 76.77 | 0.030893
Mali | Sub-Saharan Africa | P090075 | C1 |  | P090075C1 | Ratio | 2007 / 2016 | Gravel Resurfacing |  | 115.6% | 94.78% |  | 94.78% | 82%
Mali | Sub-Saharan Africa | P079351 | C1 |  | P079351C1 | Estimate | 2004 | Asphalt Mix Resurfacing | 60 | 564 | 32.48 | USD | 32.48 | 0.057589 | x |  |  | x | x
Mali | Sub-Saharan Africa | P079351 | C1 |  | P079351C1 | Actual | 2010 | Asphalt Mix Resurfacing | 72 | 239 | 32.1 | USD | 32.1 | 0.13431 | x |  |  | x | x
Mali | Sub-Saharan Africa | P079351 | C1 |  | P079351C1 | Ratio | 2004 / 2010 | Asphalt Mix Resurfacing | 120% | 42.38% | 98.83% |  | 98.83% | 233.2% | x |  |  | x | x | Capacity of counterpart; Procurement system; | Continued weak procurement capacity of the newly restructured roads agency (DNR); The cost of road works for Bamako – Bougouni doubled from about US$17.8 million at appraisal to about US$37.5 million based on actual bids received; therefore only 85 km out of the planned 407 km of maintenance works on the Sévaré – Gao road could be funded;
Mauritius | Sub-Saharan Africa | P091828 | C1 | S1 | P091828C1S1 | Estimate | 2009 | Partial Widening and Reconstruction |  | 12.1 | 21.6 | USD | 21.6 | 1.7851 |  |  |  | x | x
Mauritius | Sub-Saharan Africa | P091828 | C1 | S1 | P091828C1S1 | Actual | 2015 | Partial Widening and Reconstruction | 18 | 12.1 | 33.88 | USD | 33.88 | 2.8 |  |  |  | x | x
Mauritius | Sub-Saharan Africa | P091828 | C1 |  | P091828C1S1 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction |  | 100% | 156.9% |  | 156.9% | 156.9% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; | There was an unanticipated increase in crude oil prices, which, since Mauritius is a series of islands, increased the costs of imported materials; The cost estimates of upgrading B6 road were not carefully checked at the project appraisal stage in Dec 2009; it was not until the completion of the bidding documents in late 2010 that the cost estimates were updated and revised to US$31.7 million (constituting about a 20 percent increase);;
Mauritius | Sub-Saharan Africa | P091828 | C1 | S2 | P091828C1S2 | Estimate | 2009 | Reconstruction |  | 5 | 4.64 | USD | 4.64 | 0.928
Mauritius | Sub-Saharan Africa | P091828 | C1 | S2 | P091828C1S2 | Actual | 2015 | Reconstruction | 10 | 5 | 3.752 | USD | 3.752 | 0.75041
Mauritius | Sub-Saharan Africa | P091828 | C1 |  | P091828C1S2 | Ratio | 2009 / 2015 | Reconstruction |  | 100% | 80.86% |  | 80.86% | 80.86%
Mauritius | Sub-Saharan Africa | P091828 | C1 | S3 | P091828C1S3 | Estimate | 2009 | Reconstruction |  | 8 | 3.33 | USD | 3.33 | 0.41625 |  |  |  | x | x
Mauritius | Sub-Saharan Africa | P091828 | C1 | S3 | P091828C1S3 | Actual | 2015 | Reconstruction | 10 | 8 | 6.385 | USD | 6.385 | 0.79812 |  |  |  | x | x
Mauritius | Sub-Saharan Africa | P091828 | C1 |  | P091828C1S3 | Ratio | 2009 / 2015 | Reconstruction |  | 100% | 191.7% |  | 191.7% | 191.7% |  |  |  | x | x | Macroeconomic conditions; Change of project scope; | There was an unanticipated increase in crude oil prices, which, since Mauritius is a series of islands, increased the costs of imported materials; Total cost increased due to additional works performed to seal up cracked existing bituminous pavement layers;
Mauritius | Sub-Saharan Africa | P091828 | C1 | S4 | P091828C1S4 | Estimate | 2009 | Reconstruction |  | 4 | 2.43 | USD | 2.43 | 0.6075
Mauritius | Sub-Saharan Africa | P091828 | C1 | S4 | P091828C1S4 | Actual | 2015 | Reconstruction | 6 | 4 | 2.2313 | USD | 2.2313 | 0.55783
Mauritius | Sub-Saharan Africa | P091828 | C1 |  | P091828C1S4 | Ratio | 2009 / 2015 | Reconstruction |  | 100% | 91.82% |  | 91.82% | 91.82%
Mexico | Latin America and Caribbean | P065779 | C1 | S1 | P065779C1S1 | Estimate | 2000 | Reconstruction |  | 14.4 | 1.62 | USD | 1.62 | 0.1125
Mexico | Latin America and Caribbean | P065779 | C1 | S1 | P065779C1S1 | Actual | 2007 | Reconstruction |  | 14.4 | 1.54 | USD | 1.54 | 0.10694
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S1 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 95.06% |  | 95.06% | 95.06%
Mexico | Latin America and Caribbean | P065779 | C1 | S10 | P065779C1S10 | Estimate | 2000 | Reconstruction |  | 11.9 | 2.16 | USD | 2.16 | 0.18151
Mexico | Latin America and Caribbean | P065779 | C1 | S10 | P065779C1S10 | Actual | 2007 | Reconstruction |  | 11.9 | 3.08 | USD | 3.08 | 0.25882
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S10 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 142.6% |  | 142.6% | 142.6%
Mexico | Latin America and Caribbean | P065779 | C1 | S11 | P065779C1S11 | Estimate | 2000 | Reconstruction |  | 3 | 0.54 | USD | 0.54 | 0.18
Mexico | Latin America and Caribbean | P065779 | C1 | S11 | P065779C1S11 | Actual | 2007 | Reconstruction |  | 3 | 0.74 | USD | 0.74 | 0.24667
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S11 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 137% |  | 137% | 137%
Mexico | Latin America and Caribbean | P065779 | C1 | S12 | P065779C1S12 | Estimate | 2000 | Reconstruction |  | 12.5 | 1.41 | USD | 1.41 | 0.1128
Mexico | Latin America and Caribbean | P065779 | C1 | S12 | P065779C1S12 | Actual | 2007 | Reconstruction |  | 12.5 | 1.2 | USD | 1.2 | 0.096
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S12 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 85.11% |  | 85.11% | 85.11%
Mexico | Latin America and Caribbean | P065779 | C1 | S13 | P065779C1S13 | Estimate | 2000 | Reconstruction |  | 9 | 1.15 | USD | 1.15 | 0.12778 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S13 | P065779C1S13 | Actual | 2007 | Reconstruction |  | 9 | 2.07 | USD | 2.07 | 0.23 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S13 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 180% |  | 180% | 180% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S14 | P065779C1S14 | Estimate | 2000 | Reconstruction |  | 4 | 0.6 | USD | 0.6 | 0.15 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S14 | P065779C1S14 | Actual | 2007 | Reconstruction |  | 3.4 | 1.53 | USD | 1.53 | 0.45 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S14 | Ratio | 2000 / 2007 | Reconstruction |  | 85% | 255% |  | 255% | 300% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S15 | P065779C1S15 | Estimate | 2000 | Reconstruction |  | 15.4 | 2.48 | USD | 2.48 | 0.16104
Mexico | Latin America and Caribbean | P065779 | C1 | S15 | P065779C1S15 | Actual | 2007 | Reconstruction |  | 15.4 | 1.91 | USD | 1.91 | 0.12403
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S15 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 77.02% |  | 77.02% | 77.02%
Mexico | Latin America and Caribbean | P065779 | C1 | S16 | P065779C1S16 | Estimate | 2000 | Reconstruction |  | 9.2 | 1.38 | USD | 1.38 | 0.15
Mexico | Latin America and Caribbean | P065779 | C1 | S16 | P065779C1S16 | Actual | 2007 | Reconstruction |  | 9.2 | 1.26 | USD | 1.26 | 0.13696
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S16 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 91.3% |  | 91.3% | 91.3%
Mexico | Latin America and Caribbean | P065779 | C1 | S17 | P065779C1S17 | Estimate | 2000 | Reconstruction |  | 25 | 2.81 | USD | 2.81 | 0.1124 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 | S17 | P065779C1S17 | Actual | 2007 | Reconstruction |  | 25 | 0.53 | USD | 0.53 | 0.0212 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S17 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 18.86% |  | 18.86% | 18.86% |  |  | x |  | x | Change of project scope; ; | lower costs were incurred as a result of the significant decrease in the reconstruction or major rehabilitation works due to the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S18 | P065779C1S18 | Estimate | 2000 | Reconstruction |  | 11 | 1.24 | USD | 1.24 | 0.11273
Mexico | Latin America and Caribbean | P065779 | C1 | S18 | P065779C1S18 | Actual | 2007 | Reconstruction |  | 11 | 1.55 | USD | 1.55 | 0.14091
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S18 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 125% |  | 125% | 125%
Mexico | Latin America and Caribbean | P065779 | C1 | S19 | P065779C1S19 | Estimate | 2000 | Reconstruction |  | 10.5 | 1.34 | USD | 1.34 | 0.12762 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S19 | P065779C1S19 | Actual | 2007 | Reconstruction |  | 10.5 | 2.05 | USD | 2.05 | 0.19524 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S19 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 153% |  | 153% | 153% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S2 | P065779C1S2 | Estimate | 2000 | Reconstruction |  | 11 | 1.24 | USD | 1.24 | 0.11273
Mexico | Latin America and Caribbean | P065779 | C1 | S2 | P065779C1S2 | Actual | 2007 | Reconstruction |  | 11 | 0.8 | USD | 0.8 | 0.072727
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S2 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 64.52% |  | 64.52% | 64.52%
Mexico | Latin America and Caribbean | P065779 | C1 | S20 | P065779C1S20 | Estimate | 2000 | Reconstruction |  | 21 | 3.78 | USD | 3.78 | 0.18
Mexico | Latin America and Caribbean | P065779 | C1 | S20 | P065779C1S20 | Actual | 2007 | Reconstruction |  | 21 | 4.94 | USD | 4.94 | 0.23524
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S20 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 130.7% |  | 130.7% | 130.7%
Mexico | Latin America and Caribbean | P065779 | C1 | S21 | P065779C1S21 | Estimate | 2000 | Reconstruction |  | 21.4 | 3.85 | USD | 3.85 | 0.17991 | x |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 | S21 | P065779C1S21 | Actual | 2007 | Asphalt Mix Resurfacing |  | 10 | 0.75 | USD | 0.75 | 0.075 | x |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S21 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 46.73% | 19.48% |  | 19.48% | 41.69% | x |  | x |  | x | Change of project scope; ; | less kilometers than those estimated in the PAD were rehabilitated or reconstructed due to a higher deterioration than expected in some roads and due to the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation ; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S22 | P065779C1S22 | Estimate | 2000 | Reconstruction |  | 12 | 2.16 | USD | 2.16 | 0.18
Mexico | Latin America and Caribbean | P065779 | C1 | S22 | P065779C1S22 | Actual | 2007 | Asphalt Mix Resurfacing |  | 12.1 | 1.4 | USD | 1.4 | 0.1157
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S22 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100.8% | 64.81% |  | 64.81% | 64.28%
Mexico | Latin America and Caribbean | P065779 | C1 | S23 | P065779C1S23 | Estimate | 2000 | Reconstruction |  | 4 | 0.6 | USD | 0.6 | 0.15
Mexico | Latin America and Caribbean | P065779 | C1 | S23 | P065779C1S23 | Actual | 2007 | Reconstruction |  | 4 | 0.55 | USD | 0.55 | 0.1375
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S23 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 91.67% |  | 91.67% | 91.67%
Mexico | Latin America and Caribbean | P065779 | C1 | S24 | P065779C1S24 | Estimate | 2000 | Reconstruction |  | 6.5 | 0.98 | USD | 0.98 | 0.15077
Mexico | Latin America and Caribbean | P065779 | C1 | S24 | P065779C1S24 | Actual | 2007 | Reconstruction |  | 6.5 | 0.7 | USD | 0.7 | 0.10769
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S24 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 71.43% |  | 71.43% | 71.43%
Mexico | Latin America and Caribbean | P065779 | C1 | S25 | P065779C1S25 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 15.8 | 0.49 | USD | 0.49 | 0.031013 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S25 | P065779C1S25 | Actual | 2007 | Asphalt Mix Resurfacing |  | 15.2 | 0.84 | USD | 0.84 | 0.055263 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S25 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 96.2% | 171.4% |  | 171.4% | 178.2% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S26 | P065779C1S26 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 30 | 0.63 | USD | 0.63 | 0.021
Mexico | Latin America and Caribbean | P065779 | C1 | S26 | P065779C1S26 | Actual | 2007 | Asphalt Mix Resurfacing |  | 30 | 0.8 | USD | 0.8 | 0.026667
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S26 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 127% |  | 127% | 127%
Mexico | Latin America and Caribbean | P065779 | C1 | S27 | P065779C1S27 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 17 | 0.55 | USD | 0.55 | 0.032353
Mexico | Latin America and Caribbean | P065779 | C1 | S27 | P065779C1S27 | Actual | 2007 | Asphalt Mix Resurfacing |  | 17 | 0.69 | USD | 0.69 | 0.040588
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S27 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 125.5% |  | 125.5% | 125.5%
Mexico | Latin America and Caribbean | P065779 | C1 | S28 | P065779C1S28 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 17.6 | 0.49 | USD | 0.49 | 0.027841 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S28 | P065779C1S28 | Actual | 2007 | Asphalt Mix Resurfacing |  | 17.6 | 1.17 | USD | 1.17 | 0.066477 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S28 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 238.8% |  | 238.8% | 238.8% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S29 | P065779C1S29 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 4 | 0.17 | USD | 0.17 | 0.0425 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S29 | P065779C1S29 | Actual | 2007 | Asphalt Mix Resurfacing |  | 4 | 0.34 | USD | 0.34 | 0.085 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S29 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 200% |  | 200% | 200% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S3 | P065779C1S3 | Estimate | 2000 | Reconstruction |  | 3 | 0.34 | USD | 0.34 | 0.11333
Mexico | Latin America and Caribbean | P065779 | C1 | S3 | P065779C1S3 | Actual | 2007 | Reconstruction |  | 3 | 0.17 | USD | 0.17 | 0.056667
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S3 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 50% |  | 50% | 50%
Mexico | Latin America and Caribbean | P065779 | C1 | S30 | P065779C1S30 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 4.5 | 0.17 | USD | 0.17 | 0.037778 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S30 | P065779C1S30 | Actual | 2007 | Asphalt Mix Resurfacing |  | 4.5 | 0.33 | USD | 0.33 | 0.073333 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S30 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 194.1% |  | 194.1% | 194.1% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S31 | P065779C1S31 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 3 | 0.06 | USD | 0.06 | 0.02
Mexico | Latin America and Caribbean | P065779 | C1 | S31 | P065779C1S31 | Actual | 2007 | Asphalt Mix Resurfacing |  | 3 | 0.07 | USD | 0.07 | 0.023333
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S31 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 116.7% |  | 116.7% | 116.7%
Mexico | Latin America and Caribbean | P065779 | C1 | S32 | P065779C1S32 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 30 | 1.08 | USD | 1.08 | 0.036 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 | S32 | P065779C1S32 | Actual | 2007 | Asphalt Mix Resurfacing |  | 30 | 0.48 | USD | 0.48 | 0.016 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S32 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 44.44% |  | 44.44% | 44.44% |  |  | x |  | x | Change of project scope; ; | lower costs were incurred as a result of the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S33 | P065779C1S33 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 22 | 0.71 | USD | 0.71 | 0.032273 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S33 | P065779C1S33 | Actual | 2007 | Asphalt Mix Resurfacing |  | 22 | 1.37 | USD | 1.37 | 0.062273 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S33 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 193% |  | 193% | 193% |  |  |  | x | x | Change of project scope; Capacity of counterpart (Procurement system); | widening of the scope of the program ; unforeseeable problems in the evaluation and awarding of bids;
Mexico | Latin America and Caribbean | P065779 | C1 | S34 | P065779C1S34 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 5 | 0.26 | USD | 0.26 | 0.052 |  | x |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S34 | P065779C1S34 | Actual | 2007 | Asphalt Mix Resurfacing |  | 8 | 0.84 | USD | 0.84 | 0.105 |  | x |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S34 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 160% | 323.1% |  | 323.1% | 201.9% |  | x |  | x | x | Capacity of counterpart ; Quality of estimates; Change of project scope | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ; extension of the road length and its scope due to the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation to prevent that the roads in fair condition deteriorated and fell into the poor condition category
Mexico | Latin America and Caribbean | P065779 | C1 | S35 | P065779C1S35 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 9 | 0.47 | USD | 0.47 | 0.052222 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S35 | P065779C1S35 | Actual | 2007 | Asphalt Mix Resurfacing |  | 9 | 1.41 | USD | 1.41 | 0.15667 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S35 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 300% |  | 300% | 300% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S36 | P065779C1S36 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 16 | 0.46 | USD | 0.46 | 0.02875 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S36 | P065779C1S36 | Actual | 2007 | Asphalt Mix Resurfacing |  | 17.5 | 1.61 | USD | 1.61 | 0.092 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S36 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 109.4% | 350% |  | 350% | 320% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S37 | P065779C1S37 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 31 | 1.33 | USD | 1.33 | 0.042903 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S37 | P065779C1S37 | Actual | 2007 | Asphalt Mix Resurfacing |  | 31 | 2 | USD | 2 | 0.064516 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S37 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 150.4% |  | 150.4% | 150.4% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S38 | P065779C1S38 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 31 | 1.6 | USD | 1.6 | 0.051613
Mexico | Latin America and Caribbean | P065779 | C1 | S38 | P065779C1S38 | Actual | 2007 | Asphalt Mix Resurfacing |  | 30.7 | 1.41 | USD | 1.41 | 0.045928
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S38 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 99.03% | 88.12% |  | 88.12% | 88.99%
Mexico | Latin America and Caribbean | P065779 | C1 | S39 | P065779C1S39 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 7 | 0.3 | USD | 0.3 | 0.042857 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S39 | P065779C1S39 | Actual | 2007 | Reconstruction |  | 7 | 2.25 | USD | 2.25 | 0.32143 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S39 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 750% |  | 750% | 750% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S4 | P065779C1S4 | Estimate | 2000 | Reconstruction |  | 9 | 1.01 | USD | 1.01 | 0.11222
Mexico | Latin America and Caribbean | P065779 | C1 | S4 | P065779C1S4 | Actual | 2007 | Reconstruction |  | 9 | 0.85 | USD | 0.85 | 0.094444
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S4 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 84.16% |  | 84.16% | 84.16%
Mexico | Latin America and Caribbean | P065779 | C1 | S40 | P065779C1S40 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 4 | 0.1 | USD | 0.1 | 0.025 |  | x |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S40 | P065779C1S40 | Actual | 2007 | Asphalt Mix Resurfacing |  | 16 | 0.66 | USD | 0.66 | 0.04125 |  | x |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S40 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 400% | 660% |  | 660% | 165% |  | x |  | x | x | Capacity of counterpart ; Quality of estimates; Change of project scope | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ; extension of the road length and its scope due to the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation to prevent that the roads in fair condition deteriorated and fell into the poor condition category
Mexico | Latin America and Caribbean | P065779 | C1 | S41 | P065779C1S41 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 30 | 1.29 | USD | 1.29 | 0.043 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S41 | P065779C1S41 | Actual | 2007 | Reconstruction |  | 30 | 2.9 | USD | 2.9 | 0.096667 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S41 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 224.8% |  | 224.8% | 224.8% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S42 | P065779C1S42 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 7 | 0.23 | USD | 0.23 | 0.032857 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S42 | P065779C1S42 | Actual | 2007 | Asphalt Mix Resurfacing |  | 7 | 0.47 | USD | 0.47 | 0.067143 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S42 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 204.3% |  | 204.3% | 204.3% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S43 | P065779C1S43 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 20 | 1.17 | USD | 1.17 | 0.0585
Mexico | Latin America and Caribbean | P065779 | C1 | S43 | P065779C1S43 | Actual | 2007 | Asphalt Mix Resurfacing |  | 20 | 1.3 | USD | 1.3 | 0.065
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S43 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 111.1% |  | 111.1% | 111.1%
Mexico | Latin America and Caribbean | P065779 | C1 | S44 | P065779C1S44 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 12 | 0.52 | USD | 0.52 | 0.043333 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S44 | P065779C1S44 | Actual | 2007 | Reconstruction |  | 11.5 | 3.6 | USD | 3.6 | 0.31304 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S44 | Ratio | 2000 / 2007 | Reconstruction |  | 95.83% | 692.3% |  | 692.3% | 722.4% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S45 | P065779C1S45 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 9 | 0.39 | USD | 0.39 | 0.043333
Mexico | Latin America and Caribbean | P065779 | C1 | S45 | P065779C1S45 | Actual | 2007 | Asphalt Mix Resurfacing |  | 9 | 0.35 | USD | 0.35 | 0.038889
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S45 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 89.74% |  | 89.74% | 89.74%
Mexico | Latin America and Caribbean | P065779 | C1 | S46 | P065779C1S46 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 9 | 0.28 | USD | 0.28 | 0.031111 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S46 | P065779C1S46 | Actual | 2007 | Asphalt Mix Resurfacing |  | 9 | 0.45 | USD | 0.45 | 0.05 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S46 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 160.7% |  | 160.7% | 160.7% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S47 | P065779C1S47 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 30 | 0.97 | USD | 0.97 | 0.032333 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S47 | P065779C1S47 | Actual | 2007 | Asphalt Mix Resurfacing |  | 23 | 1.13 | USD | 1.13 | 0.04913 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S47 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 76.67% | 116.5% |  | 116.5% | 151.9% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S48 | P065779C1S48 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 13 | 0.4 | USD | 0.4 | 0.030769 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S48 | P065779C1S48 | Actual | 2007 | Asphalt Mix Resurfacing |  | 13 | 1.2 | USD | 1.2 | 0.092308 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S48 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 300% |  | 300% | 300% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million; rehabilitation/reconstruction contracts were slightly higher than estimated ;
Mexico | Latin America and Caribbean | P065779 | C1 | S49 | P065779C1S49 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 9 | 0.75 | USD | 0.75 | 0.083333
Mexico | Latin America and Caribbean | P065779 | C1 | S49 | P065779C1S49 | Actual | 2007 | Asphalt Mix Resurfacing |  | 9.5 | 0.89 | USD | 0.89 | 0.093684
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S49 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 105.6% | 118.7% |  | 118.7% | 112.4%
Mexico | Latin America and Caribbean | P065779 | C1 | S5 | P065779C1S5 | Estimate | 2000 | Reconstruction |  | 16 | 1.8 | USD | 1.8 | 0.1125
Mexico | Latin America and Caribbean | P065779 | C1 | S5 | P065779C1S5 | Actual | 2007 | Reconstruction |  | 11 | 1.04 | USD | 1.04 | 0.094545
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S5 | Ratio | 2000 / 2007 | Reconstruction |  | 68.75% | 57.78% |  | 57.78% | 84.04%
Mexico | Latin America and Caribbean | P065779 | C1 | S50 | P065779C1S50 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 69 | 2.23 | USD | 2.23 | 0.032319
Mexico | Latin America and Caribbean | P065779 | C1 | S50 | P065779C1S50 | Actual | 2007 | Asphalt Mix Resurfacing |  | 69 | 3.26 | USD | 3.26 | 0.047246
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S50 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 146.2% |  | 146.2% | 146.2%
Mexico | Latin America and Caribbean | P065779 | C1 | S51 | P065779C1S51 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 20 | 1.38 | USD | 1.38 | 0.069
Mexico | Latin America and Caribbean | P065779 | C1 | S51 | P065779C1S51 | Actual | 2007 | Asphalt Mix Resurfacing |  | 14 | 0.74 | USD | 0.74 | 0.052857
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S51 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 70% | 53.62% |  | 53.62% | 76.6%
Mexico | Latin America and Caribbean | P065779 | C1 | S6 | P065779C1S6 | Estimate | 2000 | Reconstruction |  | 5 | 0.56 | USD | 0.56 | 0.112 |  | x |  |  | x
Mexico | Latin America and Caribbean | P065779 | C1 | S6 | P065779C1S6 | Actual | 2007 | Reconstruction |  | 10 | 1.54 | USD | 1.54 | 0.154 |  | x |  |  | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S6 | Ratio | 2000 / 2007 | Reconstruction |  | 200% | 275% |  | 275% | 137.5% |  | x |  |  | x | Change of project scope; ; | extension of the road length and its scope due to the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation to prevent that the roads in fair condition deteriorated and fell into the poor condition category; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S7 | P065779C1S7 | Estimate | 2000 | Reconstruction |  | 5 | 0.75 | USD | 0.75 | 0.15 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 | S7 | P065779C1S7 | Actual | 2007 | Asphalt Mix Resurfacing |  | 5 | 0.11 | USD | 0.11 | 0.022 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S7 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% | 14.67% |  | 14.67% | 14.67% |  |  | x |  | x | Change of project scope; ; | lower costs were incurred as a result of the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S8 | P065779C1S8 | Estimate | 2000 | Reconstruction |  | 17 | 2.55 | USD | 2.55 | 0.15 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 | S8 | P065779C1S8 | Actual | 2007 | Reconstruction |  | 17 | 1.16 | USD | 1.16 | 0.068235 |  |  | x |  | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S8 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 45.49% |  | 45.49% | 45.49% |  |  | x |  | x | Change of project scope; ; | lower costs were incurred as a result of the DGCC policy of giving priority to periodic maintenance over reconstruction / rehabilitation; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S9 | P065779C1S9 | Estimate | 2000 | Reconstruction |  | 10 | 1.5 | USD | 1.5 | 0.15 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 | S9 | P065779C1S9 | Actual | 2007 | Reconstruction |  | 10 | 3.91 | USD | 3.91 | 0.391 |  |  |  | x | x
Mexico | Latin America and Caribbean | P065779 | C1 |  | P065779C1S9 | Ratio | 2000 / 2007 | Reconstruction |  | 100% | 260.7% |  | 260.7% | 260.7% |  |  |  | x | x | Capacity of counterpart ; Quality of estimates; | cost overruns resulted from effectiveness delay ; total project cost was US$332.2 million versus the original US$309 million;
Moldova | Europe and Central Asia | P100929 | C1 |  | P100929C1 | Estimate | 2005 | Widening and Reconstruction |  | 180 | 44 | USD | 44 | 0.24444 | x |  |  | x | x
Moldova | Europe and Central Asia | P100929 | C1 |  | P100929C1 | Actual | 2013 | Widening and Reconstruction |  | 87.1 | 67.2 | USD | 67.2 | 0.77153 | x |  |  | x | x
Moldova | Europe and Central Asia | P100929 | C1 |  | P100929C1 | Ratio | 2005 / 2013 | Widening and Reconstruction |  | 48.39% | 152.7% |  | 152.7% | 315.6% | x |  |  | x | x | Procurement system; Change of project scope; Quality of estimates | Declaration of mis-procurement, which caused significant delays. Specifically, during the events leading to mis-procurement, SRA showed its reliability as a project implementation agency by bringing the political interference to the World Bank’s and other partners’ attention. Due to this and the progress made on the institutional component, the Bank and its partners were confident that project implementation could continue with SRA despite the partial credit/loan cancellations. However, to minimize the risk of further political intervention, EBRD and EIB did not start funding the cancelled sections until the political leadership suspected of interference changed two years after the declaration of mis-procurement. No changes were made to the anti-corruption guidelines or procedures which had worked as planned alerting stakeholders to the political interference. ; The original engineering solution was the application of a leveling course and a wearing course of asphalt concrete, after carrying out localized repairs on the base course. However, following more detailed surveys it was clear that in many cases full rehabilitation or reconstruction would be required to provide a long term solution. ; For the civil works that were eventually funded the amount of work required to bring the roads to good condition was significantly greater than anticipated at appraisal.
Mongolia | East Asia and Pacific | P056200 | C1 |  | P056200C1 | Estimate | 2001 | Upgrading |  | 356 | 38.2 | USD | 38.2 | 0.1073
Mongolia | East Asia and Pacific | P056200 | C1 |  | P056200C1 | Actual | 2008 | Upgrading |  | 433 | 40.83 | USD | 40.83 | 0.094296
Mongolia | East Asia and Pacific | P056200 | C1 |  | P056200C1 | Ratio | 2001 / 2008 | Upgrading |  | 121.6% | 106.9% |  | 106.9% | 87.88%
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1 | Estimate | 2004 | Reconstruction | 54 | 625 | 379.3 | MAD | 40.9611 | 0.065538 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1 | Actual | 2011 | Reconstruction | 69 | 520 | 451.9 | MAD | 54.1847 | 0.1042 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 83.2% | 119.1% |  | 132.3% | 159% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; | Higher costs were incurred due to unanticipated substantial increases in the costs of key inputs (specifically, oil-based and energy intensive inputs, including fuel, asphalt and cement) that occurred between appraisal and contracts signing; At the appraisal phase, only the roads sections that were going to be worked on during the first year of the project were clearly identified – as such, the estimation of the cost of the whole project was not exact;
Morocco | Middle East and North Africa | P082754 | C1 | S1 | P082754C1S1 | Estimate | 2004 | Reconstruction | 54 | 24 | 14.4 | MAD | 1.5551 | 0.064795
Morocco | Middle East and North Africa | P082754 | C1 | S1 | P082754C1S1 | Actual | 2011 | Reconstruction | 69 | 18.7 | 13.19 | MAD | 1.5815 | 0.084574
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S1 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 77.92% | 91.6% |  | 101.7% | 130.5%
Morocco | Middle East and North Africa | P082754 | C1 | S10 | P082754C1S10 | Estimate | 2004 | Reconstruction | 54 | 9 | 7.2 | MAD | 0.77754 | 0.086393 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 | S10 | P082754C1S10 | Actual | 2011 | Reconstruction | 69 | 8.8 | 12.04 | MAD | 1.4436 | 0.16405 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S10 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 97.78% | 167.2% |  | 185.7% | 189.9% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; | Higher costs were incurred due to unanticipated substantial increases in the costs of key inputs (specifically, oil-based and energy intensive inputs, including fuel, asphalt and cement) that occurred between appraisal and contracts signing; At the appraisal phase, only the roads sections that were going to be worked on during the first year of the project were clearly identified – as such, the estimation of the cost of the whole project was not exact;
Morocco | Middle East and North Africa | P082754 | C1 | S11 | P082754C1S11 | Estimate | 2004 | Reconstruction | 54 | 10 | 3.4 | MAD | 0.36717 | 0.036717 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 | S11 | P082754C1S11 | Actual | 2011 | Reconstruction | 69 | 9.5 | 7.98 | MAD | 0.95683 | 0.10072 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S11 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 95% | 234.7% |  | 260.6% | 274.3% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; | Higher costs were incurred due to unanticipated substantial increases in the costs of key inputs (specifically, oil-based and energy intensive inputs, including fuel, asphalt and cement) that occurred between appraisal and contracts signing; At the appraisal phase, only the roads sections that were going to be worked on during the first year of the project were clearly identified – as such, the estimation of the cost of the whole project was not exact;
Morocco | Middle East and North Africa | P082754 | C1 | S12 | P082754C1S12 | Estimate | 2004 | Reconstruction | 54 | 28 | 10.56 | MAD | 1.1404 | 0.040728
Morocco | Middle East and North Africa | P082754 | C1 | S12 | P082754C1S12 | Actual | 2011 | Reconstruction | 69 | 28.9 | 10.75 | MAD | 1.289 | 0.044601
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S12 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 103.2% | 101.8% |  | 113% | 109.5%
Morocco | Middle East and North Africa | P082754 | C1 | S2 | P082754C1S2 | Estimate | 2004 | Reconstruction | 54 | 27.5 | 24 | MAD | 2.5918 | 0.094247
Morocco | Middle East and North Africa | P082754 | C1 | S2 | P082754C1S2 | Actual | 2011 | Reconstruction | 69 | 27.6 | 26.22 | MAD | 3.1439 | 0.11391
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S2 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 100.4% | 109.2% |  | 121.3% | 120.9%
Morocco | Middle East and North Africa | P082754 | C1 | S3 | P082754C1S3 | Estimate | 2004 | Reconstruction | 54 | 7 | 4.4 | MAD | 0.47516 | 0.06788
Morocco | Middle East and North Africa | P082754 | C1 | S3 | P082754C1S3 | Actual | 2011 | Reconstruction | 69 | 7.7 | 5.98 | MAD | 0.71703 | 0.09312
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S3 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 110% | 135.9% |  | 150.9% | 137.2%
Morocco | Middle East and North Africa | P082754 | C1 | S4 | P082754C1S4 | Estimate | 2004 | Reconstruction | 54 | 14 | 8.8 | MAD | 0.95032 | 0.06788
Morocco | Middle East and North Africa | P082754 | C1 | S4 | P082754C1S4 | Actual | 2011 | Reconstruction | 69 | 13.7 | 9.55 | MAD | 1.1451 | 0.083583
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S4 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 97.86% | 108.5% |  | 120.5% | 123.1%
Morocco | Middle East and North Africa | P082754 | C1 | S5 | P082754C1S5 | Estimate | 2004 | Reconstruction | 54 | 10 | 8.32 | MAD | 0.89849 | 0.089849
Morocco | Middle East and North Africa | P082754 | C1 | S5 | P082754C1S5 | Actual | 2011 | Reconstruction | 69 | 10.1 | 7.37 | MAD | 0.88369 | 0.087494
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S5 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 101% | 88.58% |  | 98.35% | 97.38%
Morocco | Middle East and North Africa | P082754 | C1 | S6 | P082754C1S6 | Estimate | 2004 | Reconstruction | 54 | 20 | 12.32 | MAD | 1.3305 | 0.066523
Morocco | Middle East and North Africa | P082754 | C1 | S6 | P082754C1S6 | Actual | 2011 | Reconstruction | 69 | 18.5 | 15.22 | MAD | 1.8249 | 0.098645
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S6 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 92.5% | 123.5% |  | 137.2% | 148.3%
Morocco | Middle East and North Africa | P082754 | C1 | S7 | P082754C1S7 | Estimate | 2004 | Reconstruction | 54 | 13 | 8.32 | MAD | 0.89849 | 0.069114
Morocco | Middle East and North Africa | P082754 | C1 | S7 | P082754C1S7 | Actual | 2011 | Reconstruction | 69 | 11.5 | 7.82 | MAD | 0.93765 | 0.081535
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S7 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 88.46% | 93.99% |  | 104.4% | 118%
Morocco | Middle East and North Africa | P082754 | C1 | S8 | P082754C1S8 | Estimate | 2004 | Reconstruction | 54 | 13 | 8.32 | MAD | 0.89849 | 0.069114
Morocco | Middle East and North Africa | P082754 | C1 | S8 | P082754C1S8 | Actual | 2011 | Reconstruction | 69 | 11.2 | 7.82 | MAD | 0.93765 | 0.083719
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S8 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 86.15% | 93.99% |  | 104.4% | 121.1%
Morocco | Middle East and North Africa | P082754 | C1 | S9 | P082754C1S9 | Estimate | 2004 | Reconstruction | 54 | 9 | 5.76 | MAD | 0.62203 | 0.069114 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 | S9 | P082754C1S9 | Actual | 2011 | Reconstruction | 69 | 13 | 11.79 | MAD | 1.4137 | 0.10874 |  |  |  | x | x
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1S9 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 144.4% | 204.7% |  | 227.3% | 157.3% |  |  |  | x | x | Macroeconomic conditions; Quality of estimates; | Higher costs were incurred due to unanticipated substantial increases in the costs of key inputs (specifically, oil-based and energy intensive inputs, including fuel, asphalt and cement) that occurred between appraisal and contracts signing; At the appraisal phase, only the roads sections that were going to be worked on during the first year of the project were clearly identified – as such, the estimation of the cost of the whole project was not exact;
Morocco | Middle East and North Africa | AfDB loan number B/MRC/RTE/90/35 | C1 |  | AfDB loan number B/MRC/RTE/90/35C1 | Estimate | 1989 | Strengthening |  | 865 | 295.7506 | MAD | 34.8434 | 0.040281
Morocco | Middle East and North Africa | AfDB loan number B/MRC/RTE/90/35 | C1 |  | AfDB loan number B/MRC/RTE/90/35C1 | Actual | 1998 | Strengthening |  | 1184.88 | 287.0172 | MAD | 29.8852 | 0.025222
Morocco | Middle East and North Africa | AfDB loan number B/MRC/RTE/90/35 | C1 |  | AfDB loan number B/MRC/RTE/90/35C1 | Ratio | 1989 / 1998 | Strengthening |  | 137% | 97.05% |  | 85.77% | 62.61%
Mozambique | Sub-Saharan Africa | P001785 | C1 |  | P001785C1 | Estimate | 2001 | Reconstruction | 0.09424 | 1250 | 117.8 | USD | 117.8 | 0.09424 |  |  |  | x | x
Mozambique | Sub-Saharan Africa | P001785 | C1 |  | P001785C1 | Actual | 2007 | Reconstruction |  | 827 | 161 | USD | 161 | 0.19468 |  |  |  | x | x
Mozambique | Sub-Saharan Africa | P001785 | C1 |  | P001785C1 | Ratio | 2001 / 2007 | Reconstruction |  | 66.16% | 136.7% |  | 136.7% | 206.6% |  |  |  | x | x | Macroeconomic conditions ; Capacity of contractors; Capacity of counterpart | higher costs were incurred due to unanticipated increases in the costs of fuel, construction material (cement, steel, and asphalt), equipment and spare parts; the depreciation of the US dollar resulted in higher bid prices compared to the appraisal estimates; cost overruns of civil works contacts resulted from insufficient qualified staff and the poor performance of some contractors and consultants ; higher costs were incurred due to a 20% increase of bid prices which resulted from delays in the payment of VAT refunds to contractors
Namibia | Sub-Saharan Africa | AfDB loan number: F/NAM/ROD/92/1 | C1 |  | AfDB loan number: F/NAM/ROD/92/1 C1 | Estimate | 1991 | Upgrading |  | 75 | 58.481 | ZAR | 21.1811 | 0.28241
Namibia | Sub-Saharan Africa | AfDB loan number: F/NAM/ROD/92/1 | C1 |  | AfDB loan number: F/NAM/ROD/92/1 C1 | Actual | 1995 | Upgrading |  | 75 | 88.0347 | ZAR | 24.272 | 0.32363
Namibia | Sub-Saharan Africa | AfDB loan number: F/NAM/ROD/92/1 | C1 |  | AfDB loan number: F/NAM/ROD/92/1 C1 | Ratio | 1991 / 1995 | Upgrading |  | 100% | 150.5% |  | 114.6% | 114.6%
Nepal | South Asia | P045052 | C1 |  | P045052C1 | Estimate | 1999 | Surface Treatment Resurfacing |  | 160 | 6.15 | USD | 6.15 | 0.038437 |  | x |  | x | x
Nepal | South Asia | P045052 | C1 |  | P045052C1 | Actual | 2007 | Surface Treatment Resurfacing |  | 248 | 26.23 | USD | 26.23 | 0.10577 |  | x |  | x | x
Nepal | South Asia | P045052 | C1 |  | P045052C1 | Ratio | 1999 / 2007 | Surface Treatment Resurfacing |  | 155% | 426.5% |  | 426.5% | 275.2% |  | x |  | x | x | Political events; Quality of estimates ; Change of project scope | the Maoist insurgency in Nepal entailed unprecedented security problems which caused the termination of nineteen new road construcrion contracts; the unstable political environment and the high political influence negatively impacted the ability of the Roads Boards Nepal (RBN) to achieve its objective of raising and managing funds for road maintenance; the PDOs were adversely affected by the budget crisis faced by the public sector; the level of rock cutting and earthworks required were significantly underestimated during the design of engineering documents due to lack of sufficient data ; as a successful component, not affected by the security situation in the country, an additional 86 km of rehabilitation works were included in the project during the second restructuring
Nepal | South Asia | P045052 | C2 |  | P045052C2 | Estimate | 1999 | Surface Treatment Resurfacing |  | 470 | 5.63 | USD | 5.63 | 0.011979
Nepal | South Asia | P045052 | C2 |  | P045052C2 | Actual | 2007 | Surface Treatment Resurfacing |  | 661 | 11.06 | USD | 11.06 | 0.016732
Nepal | South Asia | P045052 | C1 |  | P045052C2 | Ratio | 1999 / 2007 | Surface Treatment Resurfacing |  | 140.6% | 196.4% |  | 196.4% | 139.7%
Nepal | South Asia | P083923 | C1 | S1 | P083923C1S1 | Estimate | 2005 | Upgrading | 17 | 800 | 16.8 | USD | 16.8 | 0.021 |  | x |  |  | x
Nepal | South Asia | P083923 | C1 | S1 | P083923C1S1 | Actual | 2014 | Upgrading |  | 1741 | 45.62 | USD | 45.62 | 0.026203 |  | x |  |  | x
Nepal | South Asia | P083923 | C1 |  | P083923C1S1 | Ratio | 2005 / 2014 | Upgrading |  | 217.6% | 271.5% |  | 271.5% | 124.8% |  | x |  |  | x | Change of project scope ; Macroeconomic conditions; Procurement system | The Government, too, recognized the opportunity for additional financing in the project at an early stage. The timely application for increased support facilitated the preparation of a substantial additional financing. The Mid Term Review was instrumental in improving implementation by articulating the case for additional financing to bridge the shortfall in original financing and to meet Government of Nepal’s request for expanding the scope of project coverage.; Significant increase in the value of US$ vis-à-vis NPR.; The project also received significant benefit in terms of savings, especially after the 2009 restructuring, in terms of lower-than-estimated prices for all-season road contracts (due to e-bidding).
Nepal | South Asia | P083923 | C1 | S2 | P083923C1S2 | Estimate | 2005 | Upgrading | 17 | 200 | 7 | USD | 7 | 0.035
Nepal | South Asia | P083923 | C1 | S2 | P083923C1S2 | Actual | 2014 | Upgrading |  | 140 | 5.32 | USD | 5.32 | 0.038
Nepal | South Asia | P083923 | C1 |  | P083923C1S2 | Ratio | 2005 / 2014 | Upgrading |  | 70% | 76% |  | 76% | 108.6%
Nepal | South Asia | P083923 | C1 | S3 | P083923C1S3 | Estimate | 2005 | Routine Maintenance |  | 3500 | 2.63 | USD | 2.63 | 0.00075143 |  |  |  | x | x
Nepal | South Asia | P083923 | C1 | S3 | P083923C1S3 | Actual | 2014 | Routine Maintenance |  | 4600 | 5.3 | USD | 5.3 | 0.0011522 |  |  |  | x | x
Nepal | South Asia | P083923 | C1 |  | P083923C1S3 | Ratio | 2005 / 2014 | Routine Maintenance |  | 131.4% | 201.5% |  | 201.5% | 153.3% |  |  |  | x | x | Quality of estimates; Political events; Capacity | The inadequacy of the original financing to meet the targets fixed at the time of appraisal suggests room for improvement with respect to cost estimates.; The implementation was hampered by abrupt changes of key government staff. For example, the sudden change of Project Coordinator in September 2012 had a significant negative impact on progress. After some months, the situation improved following the appointment of a new Project Coordinator in early 2013. ; The lack of capacity at DDC-level had adversely affected the dry-season roads sub-component in particular.
Nicaragua | Latin America and Caribbean | P068673 | C1 |  | P068673C1 | Estimate | 2000 | Partial Widening and Reconstruction |  | 155 | 36.4 | USD | 36.4 | 0.23484
Nicaragua | Latin America and Caribbean | P068673 | C1 |  | P068673C1 | Actual | 2007 | Partial Widening and Reconstruction |  | 152.9 | 39.7 | USD | 39.7 | 0.25965
Nicaragua | Latin America and Caribbean | P068673 | C1 |  | P068673C1 | Ratio | 2000 / 2007 | Partial Widening and Reconstruction |  | 98.65% | 109.1% |  | 109.1% | 110.6%
Nicaragua | Latin America and Caribbean | P068673 | C2 |  | P068673C2 | Estimate | 2000 | Upgrading |  | 300 | 24.9 | USD | 24.9 | 0.083
Nicaragua | Latin America and Caribbean | P068673 | C2 |  | P068673C2 | Actual | 2007 | Upgrading |  | 287 | 28.3 | USD | 28.3 | 0.098606
Nicaragua | Latin America and Caribbean | P068673 | C1 |  | P068673C2 | Ratio | 2000 / 2007 | Upgrading |  | 95.67% | 113.7% |  | 113.7% | 118.8%
Nicaragua | Latin America and Caribbean | P083952 | C1 |  | P083952C1 | Estimate | 2006 | Strengthening | 36 | 51 | 10.13 | USD | 10.13 | 0.19863
Nicaragua | Latin America and Caribbean | P083952 | C1 |  | P083952C1 | Actual | 2015 | Strengthening |  | 51.57 | 13.69 | USD | 13.69 | 0.26546
Nicaragua | Latin America and Caribbean | P083952 | C1 |  | P083952C1 | Ratio | 2006 / 2015 | Strengthening |  | 101.1% | 135.1% |  | 135.1% | 133.6%
Nicaragua | Latin America and Caribbean | P083952 | C2 |  | P083952C2 | Estimate | 2006 | Reconstruction | 48 | 320 | 41.87 | USD | 41.87 | 0.13084 |  |  |  | x | x
Nicaragua | Latin America and Caribbean | P083952 | C2 |  | P083952C2 | Actual | 2015 | Reconstruction |  | 361 | 86.73 | USD | 86.73 | 0.24025 |  |  |  | x | x
Nicaragua | Latin America and Caribbean | P083952 | C1 |  | P083952C2 | Ratio | 2006 / 2015 | Reconstruction |  | 112.8% | 207.1% |  | 207.1% | 183.6% |  |  |  | x | x | Macroeconomic conditions; Change of project scope; | The increase in construction costs in Nicaragua led to a project restructuring. A worldwide escalation of oil and commodity prices resulted in an increase in construction costs in Nicaragua following the project start-up.; The AF introduced several changes to the project structure. One of those chnages was partial adjustments to the road sections included under Component 2 to ensure the consistency of the overall package of works, as well as their economic, procurement, financial, social, and environmental viability. ;
Nicaragua | Latin America and Caribbean | P083952 | C3 |  | P083952C3 | Estimate | 2006 | Routine Maintenance |  | 2480 | 7.64 | USD | 7.64 | 0.0030806
Nicaragua | Latin America and Caribbean | P083952 | C3 |  | P083952C3 | Actual | 2015 | Routine Maintenance |  | 3200 | 12.26 | USD | 12.26 | 0.0038313
Nicaragua | Latin America and Caribbean | P083952 | C1 |  | P083952C3 | Ratio | 2006 / 2015 | Routine Maintenance |  | 129% | 160.5% |  | 160.5% | 124.4%
Niger | Sub-Saharan Africa | 0 | C1 |  | 0C1 | Estimate | 1989 | Surface Treatment Resurfacing |  | 147.9 | 3502.5858 | FCFA | 10.9799 | 0.074239
Niger | Sub-Saharan Africa | 0 | C1 |  | 0C1 | Actual | 1999 | Surface Treatment Resurfacing |  | 131.8 | 7898.2904 | FCFA | 12.8284 | 0.097332
Niger | Sub-Saharan Africa | 0 | C1 |  | 0C1 | Ratio | 1989 / 1999 | Surface Treatment Resurfacing |  | 89.11% | 225.5% |  | 116.8% | 131.1%
Nigeria | Sub-Saharan Africa | P074963 | C1 |  | P074963C1 | Estimate | 2002 | Strengthening |  | 660 | 98.5 | USD | 98.5 | 0.14924 |  |  |  | x | x
Nigeria | Sub-Saharan Africa | P074963 | C1 |  | P074963C1 | Actual | 2011 | Strengthening |  | 690.8 | 158.8 | USD | 158.8 | 0.22988 |  |  |  | x | x
Nigeria | Sub-Saharan Africa | P074963 | C1 |  | P074963C1 | Ratio | 2002 / 2011 | Strengthening |  | 104.7% | 161.2% |  | 161.2% | 154% |  |  |  | x | x | Macroeconomic conditions; ; | higher cost of road works were incurred due to an increase in the price of diesel and primium motor spirit ; ;
Nigeria | Sub-Saharan Africa | P074963 | C1 | S1 | P074963C1S1 | Estimate | 2002 | Asphalt Mix Resurfacing |  | 567 | 45.53 | USD | 45.53 | 0.0803
Nigeria | Sub-Saharan Africa | P074963 | C1 | S1 | P074963C1S1 | Actual | 2011 | Asphalt Mix Resurfacing |  | 567 | 47 | USD | 47 | 0.082892
Nigeria | Sub-Saharan Africa | P074963 | C1 |  | P074963C1S1 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 100% | 103.2% |  | 103.2% | 103.2%
Nigeria | Sub-Saharan Africa | P074963 | C1 | S2 | P074963C1S2 | Estimate | 2002 | Asphalt Mix Resurfacing |  | 93 | 46.17 | USD | 46.17 | 0.49645
Nigeria | Sub-Saharan Africa | P074963 | C1 | S2 | P074963C1S2 | Actual | 2011 | Asphalt Mix Resurfacing |  | 123.8 | 59.3 | USD | 59.3 | 0.479
Nigeria | Sub-Saharan Africa | P074963 | C1 |  | P074963C1S2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 133.1% | 128.4% |  | 128.4% | 96.48%
Pakistan | South Asia | P010556 | C1 | S10 | P010556C1S10 | Estimate | 2003 | Bituminous Pavement Preventive Treatment | 32 | 72 | 636 | PKR | 11.0417 | 0.15336 |  | x |  |  | x
Pakistan | South Asia | P010556 | C1 | S10 | P010556C1S10 | Actual | 2013 | Bituminous Pavement Preventive Treatment |  | 123 | 2235 | PKR | 20.8314 | 0.16936 |  | x |  |  | x
Pakistan | South Asia | P010556 | C1 |  | P010556C1S10 | Ratio | 2003 / 2013 | Bituminous Pavement Preventive Treatment |  | 170.8% | 351.4% |  | 188.7% | 110.4% |  | x |  |  | x | Change of project scope; Weather shocks; | An additional financing meant that the total loan amount went from USD 200 million to over USD 500 milllion; 2010 floods (the worst flooding in over 80 years in Pakistan) led to a revision in the scope of certain contracts;
Pakistan | South Asia | P010556 | C1 | S14 | P010556C1S14 | Estimate | 2003 | Bituminous Pavement Preventive Treatment | 32 | 62 | 376 | PKR | 6.5278 | 0.10529 |  | x |  |  | x
Pakistan | South Asia | P010556 | C1 | S14 | P010556C1S14 | Actual | 2013 | Bituminous Pavement Preventive Treatment |  | 111 | 1518 | PKR | 14.1486 | 0.12746 |  | x |  |  | x
Pakistan | South Asia | P010556 | C1 |  | P010556C1S14 | Ratio | 2003 / 2013 | Bituminous Pavement Preventive Treatment |  | 179% | 403.7% |  | 216.7% | 121.1% |  | x |  |  | x | Change of project scope; Weather shocks; | An additional financing meant that the total loan amount went from USD 200 million to over USD 500 milllion; 2010 floods (the worst flooding in over 80 years in Pakistan) led to a revision in the scope of certain contracts;
Pakistan | South Asia | P010556 | C1 | S15 | P010556C1S15 | Estimate | 2003 | Reconstruction | 48 | 68 | 604 | PKR | 10.4861 | 0.15421
Pakistan | South Asia | P010556 | C1 | S15 | P010556C1S15 | Actual | 2013 | Reconstruction |  | 68 | 1532 | PKR | 14.2791 | 0.20999
Pakistan | South Asia | P010556 | C1 |  | P010556C1S15 | Ratio | 2003 / 2013 | Reconstruction |  | 100% | 253.6% |  | 136.2% | 136.2%
Pakistan | South Asia | P010556 | C1 | S4 | P010556C1S4 | Estimate | 2003 | Reconstruction | 48 | 89 | 1310 | PKR | 22.7431 | 0.25554
Pakistan | South Asia | P010556 | C1 | S4 | P010556C1S4 | Actual | 2013 | Reconstruction |  | 86 | 1757 | PKR | 16.3762 | 0.19042
Pakistan | South Asia | P010556 | C1 |  | P010556C1S4 | Ratio | 2003 / 2013 | Reconstruction |  | 96.63% | 134.1% |  | 72.01% | 74.52%
Pakistan | South Asia | P010556 | C1 | S5 | P010556C1S5 | Estimate | 2003 | Reconstruction | 48 | 53.7 | 951 | PKR | 16.5104 | 0.30746
Pakistan | South Asia | P010556 | C1 | S5 | P010556C1S5 | Actual | 2013 | Reconstruction |  | 50 | 1557 | PKR | 14.5121 | 0.29024
Pakistan | South Asia | P010556 | C1 |  | P010556C1S5 | Ratio | 2003 / 2013 | Reconstruction |  | 93.11% | 163.7% |  | 87.9% | 94.4%
Pakistan | South Asia | P010556 | C1 | S6 | P010556C1S6 | Estimate | 2003 | Reconstruction | 48 | 46 | 750 | PKR | 13.0208 | 0.28306
Pakistan | South Asia | P010556 | C1 | S6 | P010556C1S6 | Actual | 2013 | Reconstruction |  | 47 | 1195 | PKR | 11.138 | 0.23698
Pakistan | South Asia | P010556 | C1 |  | P010556C1S6 | Ratio | 2003 / 2013 | Reconstruction |  | 102.2% | 159.3% |  | 85.54% | 83.72%
Pakistan | South Asia | P010556 | C1 | S7 | P010556C1S7 | Estimate | 2003 | Widening and Reconstruction | 48 | 100 | 4509 | PKR | 78.2812 | 0.78281
Pakistan | South Asia | P010556 | C1 | S7 | P010556C1S7 | Actual | 2013 | Widening and Reconstruction |  | 100 | 7657 | PKR | 71.3673 | 0.71367
Pakistan | South Asia | P010556 | C1 |  | P010556C1S7 | Ratio | 2003 / 2013 | Widening and Reconstruction |  | 100% | 169.8% |  | 91.17% | 91.17%
Pakistan | South Asia | P125584 | C1 | S1 | P125584C1S1 | Estimate | 2011 | Partial Widening and Reconstruction | 24 | 10.5 | 5.14 | USD | 5.14 | 0.48952
Pakistan | South Asia | P125584 | C1 | S1 | P125584C1S1 | Actual | 2016 | Partial Widening and Reconstruction | 24 | 15.5 | 7.4 | USD | 7.4 | 0.47742
Pakistan | South Asia | P125584 | C1 |  | P125584C1S1 | Ratio | 2011 / 2016 | Partial Widening and Reconstruction | 100% | 147.6% | 144% |  | 144% | 97.53%
Pakistan | South Asia | P128966 | C1 |  | P128966C1 | Estimate | 2012 | Upgrading |  | 50 | 13.5 | USD | 13.5 | 0.27
Pakistan | South Asia | P128966 | C1 |  | P128966C1 | Actual | 2016 | Upgrading | 31 | 50 | 13.44 | USD | 13.44 | 0.2688
Pakistan | South Asia | P128966 | C1 |  | P128966C1 | Ratio | 2012 / 2016 | Upgrading |  | 100% | 99.56% |  | 99.56% | 99.56%
Papua New Guinea | East Asia and Pacific | P054238 | C1 |  | P054238C1 | Estimate | 1999 | Reconstruction | 48 | 21 | 8.19 | USD | 8.19 | 0.39 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P054238 | C1 |  | P054238C1 | Actual | 2008 | Reconstruction | 91.3333 | 21 | 23.09 | USD | 23.09 | 1.0995 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P054238 | C1 |  | P054238C1 | Ratio | 1999 / 2008 | Reconstruction | 190.3% | 100% | 281.9% |  | 281.9% | 281.9% |  |  |  | x | x | Weather shocks ; Macroeconomic conditions ; Capacity of counterpart | unseasonal rainstorms ; overall inflation contributed to substantial cost increases ; bid prices exceeding engineers' estimates on many contracts; this was due to delays arising from counterpart and EU funding, difficulty in finding qualified contractors and design creep
Papua New Guinea | East Asia and Pacific | P004397 | C1 | S1 | P004397C1S1 | Estimate | 2002 | Routine Maintenance | 12 | 2200 | 5.86 | USD | 5.86 | 0.0026636 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P004397 | C1 | S1 | P004397C1S1 | Actual | 2012 | Routine Maintenance | 48 | 1788 | 23.7 | PGK | 11.5049 | 0.0064345 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P004397 | C1 |  | P004397C1S1 | Ratio | 2002 / 2012 | Routine Maintenance | 400% | 81.27% | 404.4% |  | 196.3% | 241.6% |  |  |  | x | x | Macroeconomic conditions; Weather shocks ; | limited availability of construction materials; adverse weather conditions (prolonged wet weather);
Papua New Guinea | East Asia and Pacific | P004397 | C1 | S2 | P004397C1S2 | Estimate | 2002 | Reconstruction |  | 440 | 16.66 | USD | 16.66 | 0.037864 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P004397 | C1 | S2 | P004397C1S2 | Actual | 2012 | Reconstruction | 48 | 622.4 | 187.36 | PGK | 90.9515 | 0.14613 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P004397 | C1 |  | P004397C1S2 | Ratio | 2002 / 2012 | Reconstruction |  | 141.5% | 1125% |  | 545.9% | 385.9% |  |  |  | x | x | Macroeconomic conditions; Weather shocks ; | limited availability of construction materials; adverse weather conditions (prolonged wet weather);
Papua New Guinea | East Asia and Pacific | P004397 | C2 | S1 | P004397C2S1 | Estimate | 2002 | Routine Maintenance | 12 | 900 | 2.97 | USD | 2.97 | 0.0033
Papua New Guinea | East Asia and Pacific | P004397 | C2 | S1 | P004397C2S1 | Actual | 2012 | Routine Maintenance | 48 | 664 | 3.8 | PGK | 1.8447 | 0.0027781
Papua New Guinea | East Asia and Pacific | P004397 | C1 |  | P004397C2S1 | Ratio | 2002 / 2012 | Routine Maintenance | 400% | 73.78% | 127.9% |  | 62.11% | 84.18%
Papua New Guinea | East Asia and Pacific | P004397 | C2 | S2 | P004397C2S2 | Estimate | 2002 | Reconstruction |  | 200 | 3.4 | USD | 3.4 | 0.017 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P004397 | C2 | S2 | P004397C2S2 | Actual | 2012 | Reconstruction | 48 | 156 | 32.2 | PGK | 15.6311 | 0.1002 |  |  |  | x | x
Papua New Guinea | East Asia and Pacific | P004397 | C1 |  | P004397C2S2 | Ratio | 2002 / 2012 | Reconstruction |  | 78% | 947.1% |  | 459.7% | 589.4% |  |  |  | x | x | Macroeconomic conditions; Weather shocks; | limited availability of construction materials; adverse weather conditions (prolonged wet weather);
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C1 | Estimate | 2006 | Strengthening |  | 968 | 43.45 | USD | 43.45 | 0.044886 |  |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C1 | Actual | 2016 | Strengthening |  | 623 | 73.47 | USD | 73.47 | 0.11793 |  |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C1 | Ratio | 2006 / 2016 | Strengthening |  | 64.36% | 169.1% |  | 169.1% | 262.7% |  |  |  | x | x | Quality of estimates; ; | estimated capital costs were higher than at appraisal due to the fact that initial designs dated from before the Project was approved and also the rate of deterioration of the pavement was greater than anticipated; ;
Paraguay | Latin America and Caribbean | P082026 | C1 | S1 | P082026C1S1 | Estimate | 2006 | Strengthening | 48 | 108 | 4.6 | USD | 4.6 | 0.042593
Paraguay | Latin America and Caribbean | P082026 | C1 | S1 | P082026C1S1 | Actual | 2016 | Strengthening | 48 | 108 | 5.47 | USD | 5.47 | 0.050648
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C1S1 | Ratio | 2006 / 2016 | Strengthening | 100% | 100% | 118.9% |  | 118.9% | 118.9%
Paraguay | Latin America and Caribbean | P082026 | C1 | S2 | P082026C1S2 | Estimate | 2006 | Strengthening | 48 | 381 | 10.3 | USD | 10.3 | 0.027034 |  |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 | S2 | P082026C1S2 | Actual | 2016 | Strengthening | 48 | 381 | 17.97 | USD | 17.97 | 0.047165 |  |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C1S2 | Ratio | 2006 / 2016 | Strengthening | 100% | 100% | 174.5% |  | 174.5% | 174.5% |  |  |  | x | x | Quality of estimates; ; | estimated capital costs were higher than at appraisal due to the fact that initial designs dated from before the Project was approved and also the rate of deterioration of the pavement was greater than anticipated; ;
Paraguay | Latin America and Caribbean | P082026 | C1 | S3 | P082026C1S3 | Estimate | 2006 | Strengthening | 20.9249 | 142 | 10.7 | USD | 10.7 | 0.075352 |  |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 | S3 | P082026C1S3 | Actual | 2016 | Strengthening | 36.1667 | 142 | 42.2217 | USD | 42.2217 | 0.29734 |  |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C1S3 | Ratio | 2006 / 2016 | Strengthening | 172.8% | 100% | 394.6% |  | 394.6% | 394.6% |  |  |  | x | x | Quality of estimates; ; | estimated capital costs were higher than at appraisal due to the fact that initial designs dated from before the Project was approved and also the rate of deterioration of the pavement was greater than anticipated; ;
Paraguay | Latin America and Caribbean | P082026 | C2 |  | P082026C2 | Estimate | 2006 | Reconstruction |  | 337.9 | 42.9 | USD | 42.9 | 0.12696 | x |  |  |  | x
Paraguay | Latin America and Caribbean | P082026 | C2 |  | P082026C2 | Actual | 2016 | Reconstruction |  | 143 | 26.34 | USD | 26.34 | 0.1842 | x |  |  |  | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C2 | Ratio | 2006 / 2016 | Reconstruction |  | 42.32% | 61.4% |  | 61.4% | 145.1% | x |  |  |  | x | Change of project scope; ; | a reduced works program was implemented than envisaged at appraisal with a total length improved was 140 km but at a capital cost of $24.6 mn as opposed to the initially planned 338km at a capital cost of $12.6 mn; ;
Paraguay | Latin America and Caribbean | P082026 | C2 | S1 | P082026C2S1 | Estimate | 2006 | Reconstruction | 15.04 | 121.6 | 4.9 | USD | 4.9 | 0.040296 | x |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C2 | S1 | P082026C2S1 | Actual | 2016 | Reconstruction | 18.8 | 35.7 | 6.87 | USD | 6.87 | 0.19244 | x |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C2S1 | Ratio | 2006 / 2016 | Reconstruction | 125% | 29.36% | 140.2% |  | 140.2% | 477.6% | x |  |  | x | x | Change of project scope; Quality of estimates; | a reduced works program was implemented than envisaged at appraisal with a total length improved was 140 km but at a capital cost of $24.6 mn as opposed to the initially planned 338km at a capital cost of $12.6 mn; final capital costs of the works were significantly higher than estimated ;
Paraguay | Latin America and Caribbean | P082026 | C2 | S2 | P082026C2S2 | Estimate | 2006 | Reconstruction | 20 | 113.4 | 4.2 | USD | 4.2 | 0.037037 | x |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C2 | S2 | P082026C2S2 | Actual | 2016 | Reconstruction | 21.3333 | 35.5 | 6.19 | USD | 6.19 | 0.17437 | x |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C2S2 | Ratio | 2006 / 2016 | Reconstruction | 106.7% | 31.31% | 147.4% |  | 147.4% | 470.8% | x |  |  | x | x | Quality of estimates; Change of project scope; | higher costs were incurred as a result of issues arising from involuntary resettlement; ; final capital costs of the works were significantly higher than estimated ; a reduced works program was implemented than envisaged at appraisal with a total length improved was 140 km but at a capital cost of $24.6 mn as opposed to the initially planned 338km at a capital cost of $12.6 mn;
Paraguay | Latin America and Caribbean | P082026 | C2 | S3 | P082026C2S3 | Estimate | 2006 | Reconstruction | 12.0526 | 102.9 | 3.5 | USD | 3.5 | 0.034014 | x |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C2 | S3 | P082026C2S3 | Actual | 2016 | Reconstruction | 22.8667 | 14.7 | 3.26 | USD | 3.26 | 0.22177 | x |  |  | x | x
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C2S3 | Ratio | 2006 / 2016 | Reconstruction | 189.7% | 14.29% | 93.14% |  | 93.14% | 652% | x |  |  | x | x | Change of project scope; Quality of estimates; | a reduced works program was implemented than envisaged at appraisal with a total length improved was 140 km but at a capital cost of $24.6 mn as opposed to the initially planned 338km at a capital cost of $12.6 mn; final capital costs of the works were significantly higher than estimated ;
Peru | Latin America and Caribbean | P044601 | C1 |  | P044601C1 | Estimate | 2001 | Reconstruction |  | 3575 | 61.7 | USD | 61.7 | 0.017259
Peru | Latin America and Caribbean | P044601 | C1 |  | P044601C1 | Actual | 2007 | Reconstruction |  | 4692 | 65.33 | USD | 65.33 | 0.013924
Peru | Latin America and Caribbean | P044601 | C1 |  | P044601C1 | Ratio | 2001 / 2007 | Reconstruction |  | 131.2% | 105.9% |  | 105.9% | 80.68%
Peru | Latin America and Caribbean | P044601 | C2 |  | P044601C2 | Estimate | 2001 | Routine Maintenance |  | 13495 | 51.8 | USD | 51.8 | 0.0038385
Peru | Latin America and Caribbean | P044601 | C2 |  | P044601C2 | Actual | 2007 | Routine Maintenance |  | 14750 | 38.59 | USD | 38.59 | 0.0026163
Peru | Latin America and Caribbean | P044601 | C1 |  | P044601C2 | Ratio | 2001 / 2007 | Routine Maintenance |  | 109.3% | 74.5% |  | 74.5% | 68.16%
Peru | Latin America and Caribbean | P078813 | C1 |  | P078813C1 | Estimate | 2005 | Reconstruction |  | 4900 | 138.84 | USD | 138.84 | 0.028335
Peru | Latin America and Caribbean | P078813 | C1 |  | P078813C1 | Actual | 2014 | Reconstruction |  | 5103 | 141.49 | USD | 141.49 | 0.027727
Peru | Latin America and Caribbean | P078813 | C1 |  | P078813C1 | Ratio | 2005 / 2014 | Reconstruction |  | 104.1% | 101.9% |  | 101.9% | 97.85%
Peru | Latin America and Caribbean | P078813 | C1 | S1 | P078813C1S1 | Estimate | 2005 | Reconstruction |  | 2200 | 110 | USD | 110 | 0.05
Peru | Latin America and Caribbean | P078813 | C1 | S1 | P078813C1S1 | Actual | 2014 | Reconstruction |  | 1562 | 102.36 | USD | 102.36 | 0.065531
Peru | Latin America and Caribbean | P078813 | C1 |  | P078813C1S1 | Ratio | 2005 / 2014 | Reconstruction |  | 71% | 93.05% |  | 93.05% | 131.1%
Peru | Latin America and Caribbean | P078813 | C1 | S2 | P078813C1S2 | Estimate | 2005 | Gravel Resurfacing |  | 2700 | 18.91 | USD | 18.91 | 0.0070037
Peru | Latin America and Caribbean | P078813 | C1 | S2 | P078813C1S2 | Actual | 2014 | Gravel Resurfacing |  | 3541 | 28.23 | USD | 28.23 | 0.0079723
Peru | Latin America and Caribbean | P078813 | C1 |  | P078813C1S2 | Ratio | 2005 / 2014 | Gravel Resurfacing |  | 131.1% | 149.3% |  | 149.3% | 113.8%
Peru | Latin America and Caribbean | P095570 | C1 |  | P095570C1 | Estimate | 2006 | Gravel Resurfacing |  | 16850 | 99.6 | USD | 99.6 | 0.005911 |  |  |  | x | x
Peru | Latin America and Caribbean | P095570 | C1 |  | P095570C1 | Actual | 2014 | Gravel Resurfacing |  | 13439 | 129.8 | USD | 129.8 | 0.0096585 |  |  |  | x | x
Peru | Latin America and Caribbean | P095570 | C1 |  | P095570C1 | Ratio | 2006 / 2014 | Gravel Resurfacing |  | 79.76% | 130.3% |  | 130.3% | 163.4% |  |  |  | x | x | Macroeconomic conditions; ; | The Project adapted rapidly to external cost pressures due to higher-than-expected economic growth. An unprecedented countrywide economic boom, unexpected at the time of Appraisal, drove up input costs considerably (e.g., materials, machinery, labor, technical expertise). A survey taken in 2010 found that rehabilitation and periodic maintenance costs had increased by 40 and 50 percent, respectively, from the estimates used in the PAD. This not only led to the 2010 project restructuring that updated project costs and output targets, but it also led Provias to diffuse bids more widely and change bid requirements to encourage more firms to compete. ; ;
Peru | Latin America and Caribbean | P095570 | C1 | S1 | P095570C1S1 | Estimate | 2006 | Reconstruction |  | 3000 | 47.7 | USD | 47.7 | 0.0159 |  |  |  | x | x
Peru | Latin America and Caribbean | P095570 | C1 | S1 | P095570C1S1 | Actual | 2014 | Reconstruction |  | 3277 | 81.374 | USD | 81.374 | 0.024832 |  |  |  | x | x
Peru | Latin America and Caribbean | P095570 | C1 |  | P095570C1S1 | Ratio | 2006 / 2014 | Reconstruction |  | 109.2% | 170.6% |  | 170.6% | 156.2% |  |  |  | x | x | Macroeconomic conditions; ; | The Project adapted rapidly to external cost pressures due to higher-than-expected economic growth. An unprecedented countrywide economic boom, unexpected at the time of Appraisal, drove up input costs considerably (e.g., materials, machinery, labor, technical expertise). A survey taken in 2010 found that rehabilitation and periodic maintenance costs had increased by 40 and 50 percent, respectively, from the estimates used in the PAD. This not only led to the 2010 project restructuring that updated project costs and output targets, but it also led Provias to diffuse bids more widely and change bid requirements to encourage more firms to compete. ; ;
Peru | Latin America and Caribbean | P095570 | C1 | S2 | P095570C1S2 | Estimate | 2006 | Gravel Resurfacing |  | 11200 | 31.4 | USD | 31.4 | 0.0028036 |  |  |  | x | x
Peru | Latin America and Caribbean | P095570 | C1 | S2 | P095570C1S2 | Actual | 2014 | Gravel Resurfacing |  | 7806 | 40.0024 | USD | 40.0024 | 0.0051246 |  |  |  | x | x
Peru | Latin America and Caribbean | P095570 | C1 |  | P095570C1S2 | Ratio | 2006 / 2014 | Gravel Resurfacing |  | 69.7% | 127.4% |  | 127.4% | 182.8% |  |  |  | x | x | Macroeconomic conditions; ; | The Project adapted rapidly to external cost pressures due to higher-than-expected economic growth. An unprecedented countrywide economic boom, unexpected at the time of Appraisal, drove up input costs considerably (e.g., materials, machinery, labor, technical expertise). A survey taken in 2010 found that rehabilitation and periodic maintenance costs had increased by 40 and 50 percent, respectively, from the estimates used in the PAD. This not only led to the 2010 project restructuring that updated project costs and output targets, but it also led Provias to diffuse bids more widely and change bid requirements to encourage more firms to compete. ; ;
Peru | Latin America and Caribbean | P095570 | C1 | S3 | P095570C1S3 | Estimate | 2006 | Reconstruction |  | 2650 | 5 | USD | 5 | 0.0018868
Peru | Latin America and Caribbean | P095570 | C1 | S3 | P095570C1S3 | Actual | 2014 | Reconstruction |  | 2356 | 6.3991 | USD | 6.3991 | 0.0027161
Peru | Latin America and Caribbean | P095570 | C1 |  | P095570C1S3 | Ratio | 2006 / 2014 | Reconstruction |  | 88.91% | 128% |  | 128% | 144%
Philippines | East Asia and Pacific | P039019 | C1 | S1 | P039019C1S1 | Estimate | 2000 | Upgrading |  | 85 | 27.9 | USD | 27.9 | 0.32824
Philippines | East Asia and Pacific | P039019 | C1 | S1 | P039019C1S1 | Actual | 2008 | Upgrading |  | 84.8 | 1038 | PHP | 23.2997 | 0.27476
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C1S1 | Ratio | 2000 / 2008 | Upgrading |  | 99.76% | 3720% |  | 83.51% | 83.71%
Philippines | East Asia and Pacific | P039019 | C1 | S2 | P039019C1S2 | Estimate | 2000 | Upgrading |  | 43 | 14.8 | USD | 14.8 | 0.34419
Philippines | East Asia and Pacific | P039019 | C1 | S2 | P039019C1S2 | Actual | 2008 | Upgrading |  | 48.3 | 1000 | PHP | 22.4467 | 0.46473
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C1S2 | Ratio | 2000 / 2008 | Upgrading |  | 112.3% | 6757% |  | 151.7% | 135%
Philippines | East Asia and Pacific | P039019 | C1 | S3 | P039019C1S3 | Estimate | 2000 | Upgrading |  | 46 | 9.88 | USD | 9.88 | 0.21478
Philippines | East Asia and Pacific | P039019 | C1 | S3 | P039019C1S3 | Actual | 2008 | Upgrading |  | 46.2 | 364 | PHP | 8.1706 | 0.17685
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C1S3 | Ratio | 2000 / 2008 | Upgrading |  | 100.4% | 3684% |  | 82.7% | 82.34%
Philippines | East Asia and Pacific | P039019 | C1 | S4 | P039019C1S4 | Estimate | 2000 | Upgrading |  | 142 | 10.9 | USD | 10.9 | 0.076761 | x |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C1 | S4 | P039019C1S4 | Actual | 2008 | Upgrading |  | 45.2 | 501 | PHP | 11.2458 | 0.2488 | x |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C1S4 | Ratio | 2000 / 2008 | Upgrading |  | 31.83% | 4596% |  | 103.2% | 324.1% | x |  |  | x | x | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks | slow procurement process and the mis-procurement of several documents; as a result some of the contracts were financed by the government - a 13% cost overrun is estimated resulted from the roads financed by the government; the road length is about 23% less than estimated at appraisal as a result of the fiscal crises experienced by the government ; actual unit costs more than double the appraisal estimates; typhoons
Philippines | East Asia and Pacific | P039019 | C1 | S5 | P039019C1S5 | Estimate | 2000 | Upgrading |  | 46 | 2.8 | USD | 2.8 | 0.06087 |  |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C1 | S5 | P039019C1S5 | Actual | 2008 | Upgrading |  | 52.6 | 534 | PHP | 11.9865 | 0.22788 |  |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C1S5 | Ratio | 2000 / 2008 | Upgrading |  | 114.3% | 19071% |  | 428.1% | 374.4% |  |  |  | x | x | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks | slow procurement process and the mis-procurement of several documents; as a result some of the contracts were financed by the government - a 13% cost overrun is estimated resulted from the roads financed by the government; actual unit costs more than double the appraisal estimates; typhoons
Philippines | East Asia and Pacific | P039019 | C1 | S8 | P039019C1S8 | Estimate | 2000 | Upgrading |  | 46 | 5 | USD | 5 | 0.1087 |  |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C1 | S8 | P039019C1S8 | Actual | 2008 | Upgrading |  | 46.1 | 412 | PHP | 9.248 | 0.20061 |  |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C1S8 | Ratio | 2000 / 2008 | Upgrading |  | 100.2% | 8240% |  | 185% | 184.6% |  |  |  | x | x | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks | slow procurement process and the mis-procurement of several documents; as a result some of the contracts were financed by the government - a 13% cost overrun is estimated resulted from the roads financed by the government; actual unit costs more than double the appraisal estimates; typhoons
Philippines | East Asia and Pacific | P039019 | C1 | S9 | P039019C1S9 | Estimate | 2000 | Upgrading |  | 59 | 12.63 | USD | 12.63 | 0.21407
Philippines | East Asia and Pacific | P039019 | C1 | S9 | P039019C1S9 | Actual | 2008 | Upgrading |  | 59.1 | 766 | PHP | 17.1942 | 0.29093
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C1S9 | Ratio | 2000 / 2008 | Upgrading |  | 100.2% | 6065% |  | 136.1% | 135.9%
Philippines | East Asia and Pacific | P039019 | C2 |  | P039019C2 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 900 | 112.29 | USD | 112.29 | 0.12477
Philippines | East Asia and Pacific | P039019 | C2 |  | P039019C2 | Actual | 2008 | Asphalt Mix Resurfacing |  | 721.3 | 99.53 | USD | 99.53 | 0.13799
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C2 | Ratio | 2000 / 2008 | Asphalt Mix Resurfacing |  | 80.14% | 88.64% |  | 88.64% | 110.6%
Philippines | East Asia and Pacific | P039019 | C3 |  | P039019C3 | Estimate | 2000 | Asphalt Mix Resurfacing |  | 231 | 9.96 | USD | 9.96 | 0.043117 |  |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C3 |  | P039019C3 | Actual | 2008 | Asphalt Mix Resurfacing |  | 254 | 20.65 | USD | 20.65 | 0.081299 |  |  |  | x | x
Philippines | East Asia and Pacific | P039019 | C1 |  | P039019C3 | Ratio | 2000 / 2008 | Asphalt Mix Resurfacing |  | 110% | 207.3% |  | 207.3% | 188.6% |  |  |  | x | x | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks | slow procurement process and the mis-procurement of several documents; as a result some of the contracts were financed by the government - a 13% cost overrun is estimated resulted from the roads financed by the government; actual unit costs more than double the appraisal estimates; typhoons
Philippines | East Asia and Pacific | P057731 | C1 | S1 | P057731C1S1 | Estimate | 2001 | Reconstruction | 18.5 | 3.69 | 1.17 | USD | 1.17 | 0.31707
Philippines | East Asia and Pacific | P057731 | C1 | S1 | P057731C1S1 | Actual | 2011 | Reconstruction |  | 3.69 | 1.12 | USD | 1.12 | 0.30352
Philippines | East Asia and Pacific | P057731 | C1 |  | P057731C1S1 | Ratio | 2001 / 2011 | Reconstruction |  | 100% | 95.73% |  | 95.73% | 95.73%
Philippines | East Asia and Pacific | P057731 | C1 | S2 | P057731C1S2 | Estimate | 2001 | Reconstruction | 16.1667 | 2.42 | 2.9 | USD | 2.9 | 1.1983
Philippines | East Asia and Pacific | P057731 | C1 | S2 | P057731C1S2 | Actual | 2011 | Reconstruction |  | 2.42 | 2.18 | USD | 2.18 | 0.90083
Philippines | East Asia and Pacific | P057731 | C1 |  | P057731C1S2 | Ratio | 2001 / 2011 | Reconstruction |  | 100% | 75.17% |  | 75.17% | 75.17%
Philippines | East Asia and Pacific | P057731 | C1 | S3 | P057731C1S3 | Estimate | 2001 | Reconstruction | 26.8333 | 27.2 | 4.67 | USD | 4.67 | 0.17169 |  |  |  | x | x
Philippines | East Asia and Pacific | P057731 | C1 | S3 | P057731C1S3 | Actual | 2011 | Reconstruction |  | 27.2 | 13.51 | USD | 13.51 | 0.49669 |  |  |  | x | x
Philippines | East Asia and Pacific | P057731 | C1 |  | P057731C1S3 | Ratio | 2001 / 2011 | Reconstruction |  | 100% | 289.3% |  | 289.3% | 289.3% |  |  |  | x | x | Procurement system; Quality of estimates; | higher costs were incurred as a result of the delayed procurement of civil works partly due to prolonged discussions on the harmonization of the Borrower’s and the Bank’s procurement guidelines; gross underestimation of costs in the PAD; price difference between the detailed design estimate and the actual contract price; inadequate investigation during the detailed design stage of the sub-soil conditions and deterioration of the road conditions as well as the adoption of new regulations/standards issued by MMDA;
Philippines | East Asia and Pacific | P057731 | C1 | S4 | P057731C1S4 | Estimate | 2001 | Reconstruction | 26.6 | 11.8 | 3.44 | USD | 3.44 | 0.29153 |  |  |  | x | x
Philippines | East Asia and Pacific | P057731 | C1 | S4 | P057731C1S4 | Actual | 2011 | Reconstruction |  | 11.8 | 12.77 | USD | 12.77 | 1.0822 |  |  |  | x | x
Philippines | East Asia and Pacific | P057731 | C1 |  | P057731C1S4 | Ratio | 2001 / 2011 | Reconstruction |  | 100% | 371.2% |  | 371.2% | 371.2% |  |  |  | x | x | Procurement system; Quality of estimates; | higher costs were incurred as a result of the delayed procurement of civil works partly due to prolonged discussions on the harmonization of the Borrower’s and the Bank’s procurement guidelines; gross underestimation of costs in the PAD; price difference between the detailed design estimate and the actual contract price; inadequate investigation during the detailed design stage of the sub-soil conditions and deterioration of the road conditions as well as the adoption of new regulations/standards issued by MMDA;
Poland | Europe and Central Asia | P096214 | C1 |  | P096214C1 | Estimate | 2006 | Asphalt Mix Resurfacing |  | 900 | 167 | USD | 167 | 0.18556
Poland | Europe and Central Asia | P096214 | C1 |  | P096214C1 | Actual | 2012 | Asphalt Mix Resurfacing |  | 1103 | 181.92 | USD | 181.92 | 0.16493
Poland | Europe and Central Asia | P096214 | C1 |  | P096214C1 | Ratio | 2006 / 2012 | Asphalt Mix Resurfacing |  | 122.6% | 108.9% |  | 108.9% | 88.89%
Poland | Europe and Central Asia | P078170 | C2 |  | P078170C2 | Estimate | 2004 | Concrete Pavement Restoration |  | 917 | 158.6 | USD | 158.6 | 0.17296
Poland | Europe and Central Asia | P078170 | C2 |  | P078170C2 | Actual | 2009 | Concrete Pavement Restoration |  | 917 | 133.3 | USD | 133.3 | 0.14537
Poland | Europe and Central Asia | P078170 | C1 |  | P078170C2 | Ratio | 2004 / 2009 | Concrete Pavement Restoration |  | 100% | 84.05% |  | 84.05% | 84.05%
Romania | Europe and Central Asia | P093812 | C1 |  | P093812C1 | Estimate | 2006 | Surface Treatment Resurfacing |  | 2909 | 112.5 | USD | 112.5 | 0.038673
Romania | Europe and Central Asia | P093812 | C1 |  | P093812C1 | Actual | 2010 | Surface Treatment Resurfacing |  | 2197 | 125.4 | USD | 125.4 | 0.057078
Romania | Europe and Central Asia | P093812 | C1 |  | P093812C1 | Ratio | 2006 / 2010 | Surface Treatment Resurfacing |  | 75.52% | 111.5% |  | 111.5% | 147.6%
Rwanda | Sub-Saharan Africa | P079414 | C1 | S1 | P079414C1S1 | Estimate | 2007 | Partial Widening and Reconstruction | 27 | 83 | 38 | USD | 38 | 0.45783
Rwanda | Sub-Saharan Africa | P079414 | C1 | S1 | P079414C1S1 | Actual | 2015 | Partial Widening and Reconstruction | 33 | 83 | 48.09 | USD | 48.09 | 0.5794
Rwanda | Sub-Saharan Africa | P079414 | C1 |  | P079414C1S1 | Ratio | 2007 / 2015 | Partial Widening and Reconstruction | 122.2% | 100% | 126.6% |  | 126.6% | 126.6%
Samoa | East Asia and Pacific | P075523 | C1 | S1 | P075523C1S1 | Estimate | 2003 | Surface Treatment Resurfacing | 15 | 32 | 2.8 | USD | 2.8 | 0.0875 |  |  |  | x | x
Samoa | East Asia and Pacific | P075523 | C1 | S1 | P075523C1S1 | Actual | 2014 | Surface Treatment Resurfacing | 19 | 30 | 10.18 | USD | 10.18 | 0.33933 |  |  |  | x | x
Samoa | East Asia and Pacific | P075523 | C1 |  | P075523C1S1 | Ratio | 2003 / 2014 | Surface Treatment Resurfacing | 126.7% | 93.75% | 363.6% |  | 363.6% | 387.8% |  |  |  | x | x | Capacity of counterpart; Weather shocks; Quality of estimates | The Government had to build capacity, which included due diligence in contracting an appropriate caliber of Component Managers in each implementing agency, establishing a qualified PMU (; An 8.0 magnitude earthquake struck Samoa in 2009, and there was a Hurricane in 2012. Both affected the project; significant under-estimation at both appraisal and during implementation of the costs of the largest works contracts,
Samoa | East Asia and Pacific | P075523 | C1 | S2 | P075523C1S2 | Estimate | 2003 | Widening | 24 | 3.4 | 2.48 | USD | 2.48 | 0.72941 |  |  |  | x | x
Samoa | East Asia and Pacific | P075523 | C1 | S2 | P075523C1S2 | Actual | 2014 | Widening | 24 | 3.4 | 10.93 | USD | 10.93 | 3.2147 |  |  |  | x | x
Samoa | East Asia and Pacific | P075523 | C1 |  | P075523C1S2 | Ratio | 2003 / 2014 | Widening | 100% | 100% | 440.7% |  | 440.7% | 440.7% |  |  |  | x | x | Capacity of counterpart; Weather shocks; Quality of estimates | The Government had to build capacity, which included due diligence in contracting an appropriate caliber of Component Managers in each implementing agency, establishing a qualified PMU (; An 8.0 magnitude earthquake struck Samoa in 2009, and there was a Hurricane in 2012. Both affected the project; significant under-estimation at both appraisal and during implementation of the costs of the largest works contracts,
Samoa | East Asia and Pacific | P075523 | C1 | S3 | P075523C1S3 | Estimate | 2003 | Upgrading | 12 | 3.9 | 0.6 | USD | 0.6 | 0.15385 |  |  |  | x | x
Samoa | East Asia and Pacific | P075523 | C1 | S3 | P075523C1S3 | Actual | 2014 | Upgrading | 4 | 3.93 | 2.32 | USD | 2.32 | 0.59033 |  |  |  | x | x
Samoa | East Asia and Pacific | P075523 | C1 |  | P075523C1S3 | Ratio | 2003 / 2014 | Upgrading | 33.33% | 100.8% | 386.7% |  | 386.7% | 383.7% |  |  |  | x | x | Capacity of counterpart; Weather shocks; Quality of estimates | The Government had to build capacity, which included due diligence in contracting an appropriate caliber of Component Managers in each implementing agency, establishing a qualified PMU (; An 8.0 magnitude earthquake struck Samoa in 2009, and there was a Hurricane in 2012. Both affected the project; significant under-estimation at both appraisal and during implementation of the costs of the largest works contracts,
Senegal | Sub-Saharan Africa | P055472 | C1 |  | P055472C1 | Estimate | 2000 | Reconstruction |  | 39 | 37.54 | USD | 37.54 | 0.96256 |  |  |  | x | x
Senegal | Sub-Saharan Africa | P055472 | C1 |  | P055472C1 | Actual | 2009 | Reconstruction |  | 27 | 87.74 | USD | 87.74 | 3.2496 |  |  |  | x | x
Senegal | Sub-Saharan Africa | P055472 | C1 |  | P055472C1 | Ratio | 2000 / 2009 | Reconstruction |  | 69.23% | 233.7% |  | 233.7% | 337.6% |  |  |  | x | x | Quality of estimates; Capacity of counterpart; | the cost of externalities was difficult to assess accurately due to methodological problems; as a result the actual cost of externalities turned out to be 32% higher than the estimated cost ; higher costs were incurred due to substantial delays resulting from the lack of counterpart funds;
Sierra Leone | Sub-Saharan Africa | P078389 | C1 |  | P078389C1 | Estimate | 2005 | Gravel Resurfacing |  | 506 | 21.05 | USD | 21.05 | 0.041601 |  |  |  | x | x
Sierra Leone | Sub-Saharan Africa | P078389 | C1 |  | P078389C1 | Actual | 2014 | Gravel Resurfacing |  | 376 | 26.28 | USD | 26.28 | 0.069894 |  |  |  | x | x
Sierra Leone | Sub-Saharan Africa | P078389 | C1 |  | P078389C1 | Ratio | 2005 / 2014 | Gravel Resurfacing |  | 74.31% | 124.8% |  | 124.8% | 168% |  |  |  | x | x | Political events; Competition; | The country was emerging from civil war anf the risk perceptions of potential bidders were not fully known. These were revealed overtime and through procurement process. ; The market assessment of the risk presented in two ways (i) low number of bids received (ii) high cost of bids which was incorporated as compensation for the risk. ;
South Sudan | Sub-Saharan Africa | P118579 | C1 | S1 | P118579C1S1 | Estimate | 2010 | Routine Maintenance |  | 363 | 7.76 | USD | 7.76 | 0.021377
South Sudan | Sub-Saharan Africa | P118579 | C1 | S1 | P118579C1S1 | Actual | 2013 | Routine Maintenance | 14 | 308 | 7.6363 | USD | 7.6363 | 0.024793
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S1 | Ratio | 2010 / 2013 | Routine Maintenance |  | 84.85% | 98.41% |  | 98.41% | 116%
South Sudan | Sub-Saharan Africa | P118579 | C1 | S2 | P118579C1S2 | Estimate | 2010 | Routine Maintenance |  | 160 | 4.25 | USD | 4.25 | 0.026562
South Sudan | Sub-Saharan Africa | P118579 | C1 | S2 | P118579C1S2 | Actual | 2013 | Routine Maintenance | 13 | 113 | 4.3112 | USD | 4.3112 | 0.038152
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S2 | Ratio | 2010 / 2013 | Routine Maintenance |  | 70.62% | 101.4% |  | 101.4% | 143.6%
South Sudan | Sub-Saharan Africa | P118579 | C1 | S3 | P118579C1S3 | Estimate | 2010 | Routine Maintenance |  | 190 | 4.05 | USD | 4.05 | 0.021316
South Sudan | Sub-Saharan Africa | P118579 | C1 | S3 | P118579C1S3 | Actual | 2013 | Routine Maintenance | 21 | 151 | 4.5263 | USD | 4.5263 | 0.029976
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S3 | Ratio | 2010 / 2013 | Routine Maintenance |  | 79.47% | 111.8% |  | 111.8% | 140.6%
South Sudan | Sub-Saharan Africa | P118579 | C1 | S4 | P118579C1S4 | Estimate | 2010 | Routine Maintenance |  | 245 | 5.4 | USD | 5.4 | 0.022041
South Sudan | Sub-Saharan Africa | P118579 | C1 | S4 | P118579C1S4 | Actual | 2013 | Routine Maintenance | 15 | 233 | 5.1731 | USD | 5.1731 | 0.022202
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S4 | Ratio | 2010 / 2013 | Routine Maintenance |  | 95.1% | 95.8% |  | 95.8% | 100.7%
South Sudan | Sub-Saharan Africa | P118579 | C1 | S5 | P118579C1S5 | Estimate | 2010 | Routine Maintenance |  | 96 | 2.17 | USD | 2.17 | 0.022604 | x |  |  | x | x
South Sudan | Sub-Saharan Africa | P118579 | C1 | S5 | P118579C1S5 | Actual | 2013 | Routine Maintenance | 9 | 43 | 1.6595 | USD | 1.6595 | 0.038593 | x |  |  | x | x
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S5 | Ratio | 2010 / 2013 | Routine Maintenance |  | 44.79% | 76.48% |  | 76.48% | 170.7% | x |  |  | x | x | Capacity of counterpart; Political events; | The freezing of recruitment of new civil servants by the government due to the economic crisis in 2009 limiting the capacity; There was a delay in the establishment of the authority and insufficient funds for road maintenance due to government budgetary constraints which remained a key impediment in operationalizing the authority, this was exacerbated by the delays and distruptions associated with the South Sudanese independence referendum period;
South Sudan | Sub-Saharan Africa | P118579 | C1 | S6 | P118579C1S6 | Estimate | 2010 | Routine Maintenance |  | 85 | 3.155 | USD | 3.155 | 0.037118
South Sudan | Sub-Saharan Africa | P118579 | C1 | S6 | P118579C1S6 | Actual | 2013 | Routine Maintenance | 12 | 85 | 3.0102 | USD | 3.0102 | 0.035414
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S6 | Ratio | 2010 / 2013 | Routine Maintenance |  | 100% | 95.41% |  | 95.41% | 95.41%
South Sudan | Sub-Saharan Africa | P118579 | C1 | S7 | P118579C1S7 | Estimate | 2010 | Routine Maintenance |  | 150 | 3.18 | USD | 3.18 | 0.0212
South Sudan | Sub-Saharan Africa | P118579 | C1 | S7 | P118579C1S7 | Actual | 2013 | Routine Maintenance | 12 | 140 | 3.6548 | USD | 3.6548 | 0.026106
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S7 | Ratio | 2010 / 2013 | Routine Maintenance |  | 93.33% | 114.9% |  | 114.9% | 123.1%
South Sudan | Sub-Saharan Africa | P118579 | C1 | S8 | P118579C1S8 | Estimate | 2010 | Routine Maintenance |  | 260 | 2.76 | USD | 2.76 | 0.010615 | x |  |  | x | x
South Sudan | Sub-Saharan Africa | P118579 | C1 | S8 | P118579C1S8 | Actual | 2013 | Routine Maintenance | 7 | 129 | 3.153 | USD | 3.153 | 0.024442 | x |  |  | x | x
South Sudan | Sub-Saharan Africa | P118579 | C1 |  | P118579C1S8 | Ratio | 2010 / 2013 | Routine Maintenance |  | 49.62% | 114.2% |  | 114.2% | 230.2% | x |  |  | x | x | Quality of estimates; Capacity of counterpart; Political events | PAD overestimated length of section 8 at 260 km instead of 150km; The freezing of recruitment of new civil servants by the government due to the economic crisis in 2009 limiting the capacity; There was a delay in the establishment of the authority and insufficient funds for road maintenance due to government budgetary constraints which remained a key impediment in operationalizing the authority, this was exacerbated by the delays and distruptions associated with the South Sudanese independence referendum period
Sri Lanka | South Asia | P086411 | C1 |  | P086411C1 | Estimate | 2005 | Upgrading |  | 635 | 10.04 | USD | 10.04 | 0.015811 | x |  |  | x | x
Sri Lanka | South Asia | P086411 | C1 |  | P086411C1 | Actual | 2016 | Upgrading |  | 157 | 13.07 | USD | 13.07 | 0.083248 | x |  |  | x | x
Sri Lanka | South Asia | P086411 | C1 |  | P086411C1 | Ratio | 2005 / 2016 | Upgrading |  | 24.72% | 130.2% |  | 130.2% | 526.5% | x |  |  | x | x | Macroeconomic conditions; Quality of estimates; | A worldwide escalation of oil and commodity prices resulted in an increase in construction costs in Sri Lanka following the Project start-up.; Bid prices were 6.8 percent above estimated prices at a time in which a construction boom brought about by reconstruction works after the end of the civil war, and rebuilding after the tsunami of December 2004 resulted in shortages of resources that affected the cost and pace of implementation.;
Sri Lanka | South Asia | P086411 | C2 |  | P086411C2 | Estimate | 2005 | Widening |  | 620 | 112.51 | USD | 112.51 | 0.18147 |  |  |  | x | x
Sri Lanka | South Asia | P086411 | C2 |  | P086411C2 | Actual | 2016 | Widening |  | 617 | 239 | USD | 239 | 0.38736 |  |  |  | x | x
Sri Lanka | South Asia | P086411 | C1 |  | P086411C2 | Ratio | 2005 / 2016 | Widening |  | 99.52% | 212.4% |  | 212.4% | 213.5% |  |  |  | x | x | Macroeconomic conditions; Change of project scope; Quality of estimates | A worldwide escalation of oil and commodity prices resulted in an increase in construction costs in Sri Lanka following the Project start-up.; The use of higher standards for national highways to improve the safety environment as stipulated in the National Road Master Plan (NRMP) adopted in December 2007. Under the Project, this new policy of the Ministry of Highways and Road Development necessitated widening of roads to 6.2 meter national standards with a 0.65 meter hard shoulder on the inside of the numerous bends. As a result of the change in width of carriageway, all culverts had to be extended and other related matters addressed. ; Bid prices were 6.8 percent above estimated prices at a time in which a construction boom brought about by reconstruction works after the end of the civil war, and rebuilding after the tsunami of December 2004 resulted in shortages of resources that affected the cost and pace of implementation.
Sri Lanka | South Asia | P107847 | C1 | S1 | P107847C1S1 | Estimate | 2009 | Partial Widening and Reconstruction | 60 | 150 | 35.3 | USD | 35.3 | 0.23533 |  |  |  | x | x
Sri Lanka | South Asia | P107847 | C1 | S1 | P107847C1S1 | Actual | 2015 | Partial Widening and Reconstruction | 59 | 117.29 | 50 | USD | 50 | 0.42629 |  |  |  | x | x
Sri Lanka | South Asia | P107847 | C1 |  | P107847C1S1 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction | 98.33% | 78.19% | 141.6% |  | 141.6% | 181.1% |  |  |  | x | x | Quality of estimates; Macroeconomic conditions; Weather shocks | Incorrect cost estimation because designs were not detailed enough at time of bidding (esp. for Uva Province’s mountainous roads) necessitating preparation of detailed designs; Significant increase in the cost of construction materials, esp. concrete, bitumen and fuel, which was amplified because Sri Lanka needed to import all materials; Due to extreme climatic conditions in Dec 2014 / Jan 2015 4 locations on hilly project roads in Uva suffered from landslides and several locations had slope failures
Sri Lanka | South Asia | P107847 | C1 | S2 | P107847C1S2 | Estimate | 2009 | Partial Widening and Reconstruction | 60 | 100 | 14 | USD | 14 | 0.14 |  |  |  | x | x
Sri Lanka | South Asia | P107847 | C1 | S2 | P107847C1S2 | Actual | 2015 | Partial Widening and Reconstruction | 59 | 59.15 | 20 | USD | 20 | 0.33812 |  |  |  | x | x
Sri Lanka | South Asia | P107847 | C1 |  | P107847C1S2 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction | 98.33% | 59.15% | 142.9% |  | 142.9% | 241.5% |  |  |  | x | x | Macroeconomic conditions; Capacity of counterpart; | Significant increase in the cost of construction materials, esp. concrete, bitumen and fuel, which was amplified because Sri Lanka needed to import all materials; Supervision consultants had limited capacity for design review, which caused delays with the start of works, and not sufficient professional staff for supervision;
Sri Lanka | South Asia | P107847 | C1 | S3 | P107847C1S3 | Estimate | 2009 | Partial Widening and Reconstruction | 60 | 100 | 14 | USD | 14 | 0.14 |  |  |  | x | x
Sri Lanka | South Asia | P107847 | C1 | S3 | P107847C1S3 | Actual | 2015 | Partial Widening and Reconstruction | 59 | 55.72 | 20 | USD | 20 | 0.35894 |  |  |  | x | x
Sri Lanka | South Asia | P107847 | C1 |  | P107847C1S3 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction | 98.33% | 55.72% | 142.9% |  | 142.9% | 256.4% |  |  |  | x | x | Macroeconomic conditions; Capacity of contractors; | Significant increase in the cost of construction materials, esp. concrete, bitumen and fuel, which was amplified because Sri Lanka needed to import all materials; Due to delays in implementation, 2 contracts in Northern Province were terminated and re-awarded;
Sudan | Sub-Saharan Africa | P095081 | C1 | S1 | P095081C1S1 | Estimate | 2006 | Upgrading |  | 250 | 20.16 | USD | 20.16 | 0.08064 |  |  |  | x | x
Sudan | Sub-Saharan Africa | P095081 | C1 | S1 | P095081C1S1 | Actual | 2013 | Upgrading |  | 170 | 29.43 | USD | 29.43 | 0.17312 |  |  |  | x | x
Sudan | Sub-Saharan Africa | P095081 | C1 |  | P095081C1S1 | Ratio | 2006 / 2013 | Upgrading |  | 68% | 146% |  | 146% | 214.7% |  |  |  | x | x | Capacity; Change of project scope; Political events | Claims submitted by the contractors due to delays. The primary reason for those delays was lack of full access to the facilities being rehabilitated during the start of implementation that resulted in extension of time. Then the design and supervision consultant (Project Manager) for the project abandoned their services in April 2009 citing non-payment of their services. This resulted in lack of and/or delayed instructions to the contractors as the MHPP was not fully capable of performing the role of the Project Manager in the interim. ; The other reasons that resulted in extension of time for all the ERWJ contracts included relocation of the Water Care Works, revised specifications of new pumps for the urban water supply, accommodation of variation orders and delays in issuance of drawings.; Insecurity and landmines. Some project sites especially roads experienced security issues at the time of project implementation. This often resulted in delays which mainly affected the Faraksika –Yambio road rehabilitation project. There was also danger of landmines in the roads projects which affected both civil works and feasibility studies. In the case of the civil works the roads had to be demined in order to enable activities to proceed.
Sudan | Sub-Saharan Africa | P095081 | C1 | S2 | P095081C1S2 | Estimate | 2006 | Asphalt Mix Resurfacing |  | 100 | 11.85 | USD | 11.85 | 0.1185 |  | x |  |  | x
Sudan | Sub-Saharan Africa | P095081 | C1 | S2 | P095081C1S2 | Actual | 2013 | Asphalt Mix Resurfacing |  | 285 | 17.85 | USD | 17.85 | 0.062632 |  | x |  |  | x
Sudan | Sub-Saharan Africa | P095081 | C1 |  | P095081C1S2 | Ratio | 2006 / 2013 | Asphalt Mix Resurfacing |  | 285% | 150.6% |  | 150.6% | 52.85% |  | x |  |  | x | Change of project scope; ; | Road length was revised. Specifically, the baseline target road length to be rehabilitated, repaired and maintained at approval was 1,170 km (broken down as 250, 100 and 820 km respectively), not 1913 as reported in the ISRs and Aide Memoires during implementation. At time of first amendment to GLA, the road length to rehabilitate, repair and maintain was revised to 1,092 km (broken down as 250, 263 and 579 km respectively). During MTR the road length was further revised to 1,010 km (broken down as 168, 263, and 579 km respectively). The actual total length of 1,034 km of road network have been rehabilitated, repaired and maintained. These include 170 km rehabilitated, 285 km repaired and 579 km maintained. Despite all the above revisions, no formal recording was done through project restructuring.; ;
Sudan | Sub-Saharan Africa | P095081 | C1 | S3 | P095081C1S3 | Estimate | 2006 | Gravel Resurfacing |  | 820 | 3.54 | USD | 3.54 | 0.0043171 |  |  |  | x | x
Sudan | Sub-Saharan Africa | P095081 | C1 | S3 | P095081C1S3 | Actual | 2013 | Gravel Resurfacing |  | 579 | 6.08 | USD | 6.08 | 0.010501 |  |  |  | x | x
Sudan | Sub-Saharan Africa | P095081 | C1 |  | P095081C1S3 | Ratio | 2006 / 2013 | Gravel Resurfacing |  | 70.61% | 171.8% |  | 171.8% | 243.2% |  |  |  | x | x | Capacity; Change of project scope; Political events | Claims submitted by the contractors due to delays. The primary reason for those delays was lack of full access to the facilities being rehabilitated during the start of implementation that resulted in extension of time. Then the design and supervision consultant (Project Manager) for the project abandoned their services in April 2009 citing non-payment of their services. This resulted in lack of and/or delayed instructions to the contractors as the MHPP was not fully capable of performing the role of the Project Manager in the interim. ; The other reasons that resulted in extension of time for all the ERWJ contracts included relocation of the Water Care Works, revised specifications of new pumps for the urban water supply, accommodation of variation orders and delays in issuance of drawings.; Insecurity and landmines. Some project sites especially roads experienced security issues at the time of project implementation. This often resulted in delays which mainly affected the Faraksika –Yambio road rehabilitation project. There was also danger of landmines in the roads projects which affected both civil works and feasibility studies. In the case of the civil works the roads had to be demined in order to enable activities to proceed.
Sudan | Sub-Saharan Africa | P098837 | C1 |  | P098837C1 | Estimate | 2011 | Upgrading |  | 298 | 89.27 | USD | 89.27 | 0.29956 | x |  |  | x | x
Sudan | Sub-Saharan Africa | P098837 | C1 |  | P098837C1 | Actual | 2013 | Upgrading |  | 131 | 101.91 | USD | 101.91 | 0.77794 | x |  |  | x | x
Sudan | Sub-Saharan Africa | P098837 | C1 |  | P098837C1 | Ratio | 2011 / 2013 | Upgrading |  | 43.96% | 114.2% |  | 114.2% | 259.7% | x |  |  | x | x | Change of project scope; Political events; Capacity of Counterpart | The project initially sought to reestablish basic transport services in the war affected areas through spot improvement and maintenance of the existing roads. However, because of heavy deterioration on Damazin - Kurmuk road, spot improvement was no longer the preferred option, and required upgrading of the road to a higher standard which caused delays in the startup of the operation and excessively increasing the cost. ; Insecurity and clearing of landmines: ; Delays in release of counterpart fund: The financing arrangement being joint between the GoNU and the MDTF has also affected implementation as the Government was unable to meet its obligation of availing counterpart funds on a timely manner. Timely release of counterpart funds was a challenge throughout project implementation negatively affecting progress, and at times, was put as a condition by contractors for completing outstanding works.
Swaziland | Sub-Saharan Africa | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6 | C1 |  | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6C1 | Estimate | 1988 | Strengthening | 24 | 106 | 19.0779 | SZL | 8.3933 | 0.079182 | x |  | x
Swaziland | Sub-Saharan Africa | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6 | C1 |  | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6C1 | Actual | 1994 | Strengthening | 24 | 106 | 115.2798 | SZL | 32.4732 | 0.30635 | x |  | x
Swaziland | Sub-Saharan Africa | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6 | C1 |  | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6C1 | Ratio | 1988 / 1994 | Strengthening | 100% | 100% | 604.3% |  | 386.9% | 386.9% | x |  | x | Change of project scope; Capacity of Counterpart | Major delay occurred during the precontract services, which was mainly attributable to: i) design review leading to substantial modifications in the original design, and ii) lack of familiarity of Bank procurement rules. As a result of the design review, the original project designs, especially the pavement and bridge structures, were significantly modified to accommodate the prevailing traffic loading. | ; ; Change of project scope; Capacity of Counterpart | ; ; Major delay occurred during the precontract services, which was mainly attributable to: i) design review leading to substantial modifications in the original design, and ii) lack of familiarity of Bank procurement rules. As a result of the design review, the original project designs, especially the pavement and bridge structures, were significantly modified to accommodate the prevailing traffic loading.
Tanzania | Sub-Saharan Africa | P078387 | C1 | S1 | P078387C1S1 | Estimate | 2004 | Upgrading |  | 110 | 55.73 | USD | 55.73 | 0.50664
Tanzania | Sub-Saharan Africa | P078387 | C1 | S1 | P078387C1S1 | Actual | 2010 | Upgrading |  | 115.4 | 55.01 | USD | 55.01 | 0.47669
Tanzania | Sub-Saharan Africa | P078387 | C1 |  | P078387C1S1 | Ratio | 2004 / 2010 | Upgrading |  | 104.9% | 98.71% |  | 98.71% | 94.09%
Tanzania | Sub-Saharan Africa | P078387 | C1 | S2 | P078387C1S2 | Estimate | 2004 | Upgrading | 18 | 57 | 14.3 | USD | 14.3 | 0.25088
Tanzania | Sub-Saharan Africa | P078387 | C1 | S2 | P078387C1S2 | Actual | 2010 | Upgrading | 36 | 56 | 16.28 | USD | 16.28 | 0.29071
Tanzania | Sub-Saharan Africa | P078387 | C1 |  | P078387C1S2 | Ratio | 2004 / 2010 | Upgrading | 200% | 98.25% | 113.8% |  | 113.8% | 115.9%
Thailand | East Asia and Pacific | P075173 | C2 |  | P075173C2 | Estimate | 2003 | Widening | 24 | 73 | 50.32 | USD | 50.32 | 0.68932
Thailand | East Asia and Pacific | P075173 | C2 |  | P075173C2 | Actual | 2013 | Widening | 24 | 86.27 | 40.54 | USD | 40.54 | 0.46992
Thailand | East Asia and Pacific | P075173 | C1 |  | P075173C2 | Ratio | 2003 / 2013 | Widening | 100% | 118.2% | 80.56% |  | 80.56% | 68.17%
Uganda | Sub-Saharan Africa | P074079 | C1 | S1 | P074079C1S1 | Estimate | 2004 | Upgrading |  | 125 | 47 | USD | 47 | 0.376 |  |  |  | x | x
Uganda | Sub-Saharan Africa | P074079 | C1 | S1 | P074079C1S1 | Actual | 2012 | Upgrading | 34 | 123 | 103.51 | USD | 103.51 | 0.84154 |  |  |  | x | x
Uganda | Sub-Saharan Africa | P074079 | C1 |  | P074079C1S1 | Ratio | 2004 / 2012 | Upgrading |  | 98.4% | 220.2% |  | 220.2% | 223.8% |  |  |  | x | x | Macroeconomic conditions; Political events ; Quality of estimates | fluctuations in the prices of inputs as a result of the global economic crisis; fuel supply shortage resulting from the temporary closure of the refinery at Mombasa, followed by an intermittent break down of operations of the oil pipeline from Mombasa to Eldoret and the political crisis in Kenya at the of end 2007 to early 2008 ; the political crisis in Kenya at the of end 2007 to early 2008 contributed to a shortage of fuel supply; the substantial discrepancy between estimated and actual costs resulted from the fact that engineer’s estimates did not adequately address the issues affecting the cost of road construction contracts
Uganda | Sub-Saharan Africa | P074079 | C1 | S2 | P074079C1S2 | Estimate | 2004 | Upgrading |  | 68 | 31.18 | USD | 31.18 | 0.45853 | x |  |  | x | x
Uganda | Sub-Saharan Africa | P074079 | C1 | S2 | P074079C1S2 | Actual | 2012 | Upgrading | 39 | 15 | 57.72 | USD | 57.72 | 3.848 | x |  |  | x | x
Uganda | Sub-Saharan Africa | P074079 | C1 |  | P074079C1S2 | Ratio | 2004 / 2012 | Upgrading |  | 22.06% | 185.1% |  | 185.1% | 839.2% | x |  |  | x | x | Macroeconomic conditions; Political events ; Quality of estimates | fluctuations in the prices of inputs following the global economic crisis; fuel supply shortage resulting from the temporary closure of the refinery at Mombasa, followed by an intermittent break down of operations of the oil pipeline from Mombasa to Eldoret and the political crisis in Kenya at the of end 2007 to early 2008 ; the political crisis in Kenya at the of end 2007 to early 2008 contributed to a fuel supply shortage; the substantial discrepancy between estimated and actual costs resulted from the fact that engineer’s estimates did not adequately address the issues affecting the cost of road construction contracts
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1 | Estimate | 2001 | Strengthening |  | 271 | 72.47 | USD | 72.47 | 0.26742
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1 | Actual | 2009 | Strengthening |  | 271 | 84.63 | USD | 84.63 | 0.31229
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1 | Ratio | 2001 / 2009 | Strengthening |  | 100% | 116.8% |  | 116.8% | 116.8%
Uganda | Sub-Saharan Africa | P065436 | C1 | S1 | P065436C1S1 | Estimate | 2001 | Upgrading | 36 | 62.5 | 14.2 | USD | 14.2 | 0.2272
Uganda | Sub-Saharan Africa | P065436 | C1 | S1 | P065436C1S1 | Actual | 2009 | Upgrading | 40 | 62.5 | 17.53 | USD | 17.53 | 0.28048
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1S1 | Ratio | 2001 / 2009 | Upgrading | 111.1% | 100% | 123.5% |  | 123.5% | 123.5%
Uganda | Sub-Saharan Africa | P065436 | C1 | S2 | P065436C1S2 | Estimate | 2001 | Upgrading | 36 | 45.55 | 16.73 | USD | 16.73 | 0.36729
Uganda | Sub-Saharan Africa | P065436 | C1 | S2 | P065436C1S2 | Actual | 2009 | Upgrading | 32 | 45.55 | 18.48 | USD | 18.48 | 0.40571
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1S2 | Ratio | 2001 / 2009 | Upgrading | 88.89% | 100% | 110.5% |  | 110.5% | 110.5%
Uganda | Sub-Saharan Africa | P065436 | C1 | S3 | P065436C1S3 | Estimate | 2001 | Strengthening | 24 | 55.2 | 13.14 | USD | 13.14 | 0.23804
Uganda | Sub-Saharan Africa | P065436 | C1 | S3 | P065436C1S3 | Actual | 2009 | Strengthening | 48 | 55.2 | 15.84 | USD | 15.84 | 0.28696
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1S3 | Ratio | 2001 / 2009 | Strengthening | 200% | 100% | 120.5% |  | 120.5% | 120.5%
Uganda | Sub-Saharan Africa | P065436 | C1 | S4 | P065436C1S4 | Estimate | 2001 | Strengthening | 24 | 53 | 13.15 | USD | 13.15 | 0.24811
Uganda | Sub-Saharan Africa | P065436 | C1 | S4 | P065436C1S4 | Actual | 2009 | Strengthening | 33 | 53 | 16.86 | USD | 16.86 | 0.31811
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1S4 | Ratio | 2001 / 2009 | Strengthening | 137.5% | 100% | 128.2% |  | 128.2% | 128.2%
Ukraine | Europe and Central Asia | P100580 | C1 |  | P100580C1 | Estimate | 2009 | Reconstruction | 25 | 120 | 1728.32 | UAH | 224.4571 | 1.8705
Ukraine | Europe and Central Asia | P100580 | C1 |  | P100580C1 | Actual | 2015 | Reconstruction | 31 | 150.6 | 2579 | UAH | 171.2483 | 1.1371
Ukraine | Europe and Central Asia | P100580 | C1 |  | P100580C1 | Ratio | 2009 / 2015 | Reconstruction | 124% | 125.5% | 149.2% |  | 76.29% | 60.79%
Uruguay | Latin America and Caribbean | P057481 |  |  | P057481 | Estimate | 2005 | Routine Maintenance | 24 | 9000 | 20 | USD | 20 | 0.0022222
Uruguay | Latin America and Caribbean | P057481 |  |  | P057481 | Actual | 2012 | Routine Maintenance | 24 | 9000 | 26.9143 | USD | 26.9143 | 0.0029905
Uruguay | Latin America and Caribbean | P057481 | C1 |  | P057481 | Ratio | 2005 / 2012 | Routine Maintenance | 100% | 100% | 134.6% |  | 134.6% | 134.6%
Uruguay | Latin America and Caribbean | P057481 | C1 | S1 | P057481C1S1 | Estimate | 2007 | Reconstruction |  | 15 | 3.592 | USD | 3.592 | 0.23947 |  |  |  | x | x
Uruguay | Latin America and Caribbean | P057481 | C1 | S1 | P057481C1S1 | Actual | 2012 | Reconstruction |  | 15 | 5.69 | USD | 5.69 | 0.37933 |  |  |  | x | x
Uruguay | Latin America and Caribbean | P057481 | C1 |  | P057481C1S1 | Ratio | 2007 / 2012 | Reconstruction |  | 100% | 158.4% |  | 158.4% | 158.4% |  |  |  | x | x | Quality of estimates; ; | Cost estimates established at the time of project preparation turned out to be underestimated; ;
Uruguay | Latin America and Caribbean | P057481 | C1 | S2 | P057481C1S2 | Estimate | 2007 | Reconstruction |  | 12.5 | 2.4 | USD | 2.4 | 0.192
Uruguay | Latin America and Caribbean | P057481 | C1 | S2 | P057481C1S2 | Actual | 2012 | Reconstruction |  | 12.5 | 3.5 | USD | 3.5 | 0.28
Uruguay | Latin America and Caribbean | P057481 | C1 |  | P057481C1S2 | Ratio | 2007 / 2012 | Reconstruction |  | 100% | 145.8% |  | 145.8% | 145.8%
Uruguay | Latin America and Caribbean | P057481 | C1 | S3 | P057481C1S3 | Estimate | 2007 | Reconstruction |  | 22 | 3.74 | USD | 3.74 | 0.17 |  |  |  | x | x
Uruguay | Latin America and Caribbean | P057481 | C1 | S3 | P057481C1S3 | Actual | 2012 | Reconstruction |  | 22 | 13.257 | USD | 13.257 | 0.60259 |  |  |  | x | x
Uruguay | Latin America and Caribbean | P057481 | C1 |  | P057481C1S3 | Ratio | 2007 / 2012 | Reconstruction |  | 100% | 354.5% |  | 354.5% | 354.5% |  |  |  | x | x | Change of project scope; Quality of estimates; | A heavier and more expensive pavement rehabilitation solution was adopted, including platform widening; Cost estimates established at the time of project preparation turned out to be underestimated;
Vietnam | East Asia and Pacific | P042927 | C1 |  | P042927C1 | Estimate | 2000 | Widening | 52 | 180 | 76.21 | USD | 76.21 | 0.42339 |  |  |  | x | x
Vietnam | East Asia and Pacific | P042927 | C1 |  | P042927C1 | Actual | 2011 | Widening | 60 | 180 | 130.93 | USD | 130.93 | 0.72739 |  |  |  | x | x
Vietnam | East Asia and Pacific | P042927 | C1 |  | P042927C1 | Ratio | 2000 / 2011 | Widening | 115.4% | 100% | 171.8% |  | 171.8% | 171.8% |  |  |  | x | x | Capacity of counterpart; Macroeconomic conditions ; | delays to civil works implementation contributed to cost escalations; cost escalations resulted also from continuous challenges to identify suitable road segments for upgrading under the Mekong Delta Network Improvement (MDNI) sub-component; the final resettlement costs were more than double the appraisal estimates; this was the result of increasing compensation rates following inflationary pressures, coupled with increases in right-of-way acquisition for design changes that required road widening ;
Vietnam | East Asia and Pacific | P075407 | C1 |  | P075407C1 | Estimate | 2006 | Surface Treatment Resurfacing |  | 3150 | 127.47 | USD | 127.47 | 0.040467 |  |  |  | x | x
Vietnam | East Asia and Pacific | P075407 | C1 |  | P075407C1 | Actual | 2014 | Surface Treatment Resurfacing |  | 3283 | 244.07 | USD | 244.07 | 0.074344 |  |  |  | x | x
Vietnam | East Asia and Pacific | P075407 | C1 |  | P075407C1 | Ratio | 2006 / 2014 | Surface Treatment Resurfacing |  | 104.2% | 191.5% |  | 191.5% | 183.7% |  |  |  | x | x | Macroeconomic conditions ; Change of project scope ; Quality of estimates | extreme inflationary increases in the price of the bitumen (48% cost increase in bituminous roads over the period 2005-2008); additional cost of construction was incurred following the government’s determination that sealed surfaces would be more sustainable than gravel surfaces in rural areas ; unduly low initial cost estimates
Vietnam | East Asia and Pacific | P075407 | C2 |  | P075407C2 | Estimate | 2006 | Routine Maintenance | 30 | 12000 | 12.38 | USD | 12.38 | 0.0010317 |  | x |  | x | x
Vietnam | East Asia and Pacific | P075407 | C2 |  | P075407C2 | Actual | 2014 | Routine Maintenance | 30 | 19902 | 39.39 | USD | 39.39 | 0.0019792 |  | x |  | x | x
Vietnam | East Asia and Pacific | P075407 | C1 |  | P075407C2 | Ratio | 2006 / 2014 | Routine Maintenance | 100% | 165.9% | 318.2% |  | 318.2% | 191.8% |  | x |  | x | x | Macroeconomic conditions ; Change of project scope; Quality of estimates | extreme inflationary increases in the price of the bitumen (48% cost increase in bituminous roads over the period 2005-2008); additional financing resulted in a greater actual length that underwent routine maintenance compared to the estimated length ; unduly low initial cost estimates
Vietnam | East Asia and Pacific | P083588 | C1 |  | P083588 C1 | Estimate | 2007 | Widening and Reconstruction | 36 | 98 | 74.58 | USD | 74.58 | 0.76102 |  |  |  | x | x
Vietnam | East Asia and Pacific | P083588 | C1 |  | P083588 C1 | Actual | 2017 | Widening and Reconstruction | 79 | 61 | 75.5 | USD | 75.5 | 1.2377 |  |  |  | x | x
Vietnam | East Asia and Pacific | P083588 | C1 |  | P083588 C1 | Ratio | 2007 / 2017 | Widening and Reconstruction | 219.4% | 62.24% | 101.2% |  | 101.2% | 162.6% |  |  |  | x | x | Macroeconomic conditions; Capacity of Counterpart ; | National inflation, which had been steadily hovering around 7-8 percent per annum during the Project preparation phase, increased from 8.3 percent in 2007 to 23.1 percent in 2008 and once again from 8.9 percent in 2010 to 18.7 percent in 2011, during the critical first few years of project implementation. ; Insufficient allocation of counterpart funds for resettlement compensation presented a critical barrier to progress throughout project implementation. Delays in resettlement progress caused increased compensation payments to affected households over the course of the project. The need for an unforeseen increase of US$52M in counterpart funds was flagged in late 2015 to cover additional resettlement costs. ;
Vietnam | East Asia and Pacific | P059663 | C1 | S1 | P059663C1S1 | Estimate | 2003 | Asphalt Mix Resurfacing | 28 | 1100 | 97.2 | USD | 97.2 | 0.088364
Vietnam | East Asia and Pacific | P059663 | C1 | S1 | P059663C1S1 | Actual | 2012 | Asphalt Mix Resurfacing | 36.4 | 842 | 90.48 | USD | 90.48 | 0.10746
Vietnam | East Asia and Pacific | P059663 | C1 |  | P059663C1S1 | Ratio | 2003 / 2012 | Asphalt Mix Resurfacing | 130% | 76.55% | 93.09% |  | 93.09% | 121.6%
Vietnam | East Asia and Pacific | P059663 | C1 | S2 | P059663C1S2 | Estimate | 2003 | Asphalt Mix Resurfacing | 16 | 430 | 7 | USD | 7 | 0.016279 |  |  |  | x | x
Vietnam | East Asia and Pacific | P059663 | C1 | S2 | P059663C1S2 | Actual | 2012 | Asphalt Mix Resurfacing | 36 | 302 | 23.55 | USD | 23.55 | 0.07798 |  |  |  | x | x
Vietnam | East Asia and Pacific | P059663 | C1 |  | P059663C1S2 | Ratio | 2003 / 2012 | Asphalt Mix Resurfacing | 225% | 70.23% | 336.4% |  | 336.4% | 479% |  |  |  | x | x | Macroeconomic conditions; Procurement system; | steep, volatile price increases—particularly on fuel and bitumen—had a significant impact on appraised cost estimates; inflation averaged more than 11 percent between 2003 and 2011, peaking at 23.1 percent in 2008 and reaching nearly 20 percent again in 2011; Project activities encountered delays during a high-profile incident related to media reports of alleged corruption of several individuals from PMU that were brought to light in December 2005; the incident interrupted all ODA (Official Development Assistance) project activities implemented by MOT (Ministry of Transport) for more than two years;;
Vietnam | East Asia and Pacific | P059663 | C2 |  | P059663C2 | Estimate | 2003 | Widening and Reconstruction | 40 | 600 | 144.93 | USD | 144.93 | 0.24155 | x |  |  | x | x
Vietnam | East Asia and Pacific | P059663 | C2 |  | P059663C2 | Actual | 2012 | Widening and Reconstruction | 64 | 265 | 212.74 | USD | 212.74 | 0.80279 | x |  |  | x | x
Vietnam | East Asia and Pacific | P059663 | C1 |  | P059663C2 | Ratio | 2003 / 2012 | Widening and Reconstruction | 160% | 44.17% | 146.8% |  | 146.8% | 332.4% | x |  |  | x | x | Macroeconomic conditions; Quality of estimates; Procurement system | steep, volatile price increases—particularly on fuel and bitumen—had a significant impact on appraised cost estimates; inflation averaged more than 11 percent between 2003 and 2011, peaking at 23.1 percent in 2008 and reaching nearly 20 percent again in 2011; There had been systemic non-compliance with the Resettlement Policy Framework (RPF) and Resettlement Action Plan on several aspects and entitlements; Project activities encountered delays during a high-profile incident related to media reports of alleged corruption of several individuals from PMU that were brought to light in December 2005; the incident interrupted all ODA (Official Development Assistance) project activities implemented by MOT (Ministry of Transport) for more than two years;
Vietnam | East Asia and Pacific | P059864 | C1 |  | P059864C1 | Estimate | 1999 | Gravel Resurfacing | 60 | 10000 | 129.2 | USD | 129.2 | 0.01292
Vietnam | East Asia and Pacific | P059864 | C1 |  | P059864C1 | Actual | 2007 | Gravel Resurfacing | 60 | 7599 | 139.38 | USD | 139.38 | 0.018342
Vietnam | East Asia and Pacific | P059864 | C1 |  | P059864C1 | Ratio | 1999 / 2007 | Gravel Resurfacing | 100% | 75.99% | 107.9% |  | 107.9% | 142%
Yemen, Rep. | East Asia and Pacific | P070391 | C1 |  | P070391C1 | Estimate | 2001 | Reconstruction |  | 114 | 12.24 | USD | 12.24 | 0.10737 |  | x | x |  | x
Yemen, Rep. | East Asia and Pacific | P070391 | C1 |  | P070391C1 | Actual | 2007 | Reconstruction |  | 229 | 10.55 | USD | 10.55 | 0.04607 |  | x | x |  | x
Yemen, Rep. | East Asia and Pacific | P070391 | C1 |  | P070391C1 | Ratio | 2001 / 2007 | Reconstruction |  | 200.9% | 86.19% |  | 86.19% | 42.91% |  | x | x |  | x | Macroeconomic conditions ; Quality of estimates ; Change of project scope | the steady appreciation of the SDR resulted in lower unit costs than expected; overestimation of the costs of road works (approximately US$157,000 per km with reference to the PAD’s cost table, versus US$115,443 actual cost); almost all civil works contracts for road improvement experienced cost overruns as a result of large variation orders and contract amendments; contract unit prices turned out to be much lower compared to the ones estimated during project appraisal; the change in the length of the civil works was made possible because of the very low cost of the rehabilitation of the first 114 km which resulted from: design optimization during the detailed design stage, contract unit prices being much lower than estimated during project appraisal, and efficient use of resource materials during project implementation, whereby the application of leveling course material was limited to the minimum
Yemen, Rep. | East Asia and Pacific | P070391 | C2 |  | P070391C2 | Estimate | 2001 | Upgrading |  | 244 | 31.6 | USD | 31.6 | 0.12951 |  | x |  |  | x
Yemen, Rep. | East Asia and Pacific | P070391 | C2 |  | P070391C2 | Actual | 2007 | Upgrading |  | 397 | 43.68 | USD | 43.68 | 0.11003 |  | x |  |  | x
Yemen, Rep. | East Asia and Pacific | P070391 | C1 |  | P070391C2 | Ratio | 2001 / 2007 | Upgrading |  | 162.7% | 138.2% |  | 138.2% | 84.96% |  | x |  |  | x | Macroeconomic conditions ; Quality of estimates ; | the change in the length of the civil works was enabled because of the gradual increase in the US$ amount of the Credit throughout project implementation due to the steady appreciation of the SDR; the change in the length of the civil works was enabled because of an overestimation of the costs of road works (approximately US$157,000 per km with reference to the PAD’s cost table, versus US$115,443 actual cost);
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S1 | P075207C1S1 | Estimate | 2004 | Reconstruction | 11 | 20.9 | 2.2 | USD | 2.2 | 0.10526 |  |  |  | x | x
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S1 | P075207C1S1 | Actual | 2013 | Reconstruction |  | 20.9 | 4.17 | USD | 4.17 | 0.19952 |  |  |  | x | x
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 |  | P075207C1S1 | Ratio | 2004 / 2013 | Reconstruction |  | 100% | 189.5% |  | 189.5% | 189.5% |  |  |  | x | x | Quality of estimates; Capacity of counterpart; | there was a systemic weaknesses in the engineering design process, namely: (i) very poor guidelines in the design Terms of Reference (TORs); (ii) insufficient surveys of existing road conditions, drainage systems, bridges, and culverts,; Project experienced slow progress during the first 2 years of implementation, because there were 3 different Project Coordinators and a continuous shortage of capacity within the counterpart agency;
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S2 | P075207C1S2 | Estimate | 2004 | Reconstruction | 11 | 18.8 | 1.9 | USD | 1.9 | 0.10106 |  |  |  | x | x
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S2 | P075207C1S2 | Actual | 2013 | Reconstruction |  | 18.8 | 3.43 | USD | 3.43 | 0.18245 |  |  |  | x | x
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 |  | P075207C1S2 | Ratio | 2004 / 2013 | Reconstruction |  | 100% | 180.5% |  | 180.5% | 180.5% |  |  |  | x | x | Quality of estimates; Capacity of counterpart; | there was a systemic weaknesses in the engineering design process, namely: (i) very poor guidelines in the design Terms of Reference (TORs); (ii) insufficient surveys of existing road conditions, drainage systems, bridges, and culverts,; Project experienced slow progress during the first 2 years of implementation, because there were 3 different Project Coordinators and a continuous shortage of capacity within the counterpart agency;
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S3 | P075207C1S3 | Estimate | 2004 | Reconstruction | 11 | 10.3 | 2.6 | USD | 2.6 | 0.25243
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S3 | P075207C1S3 | Actual | 2013 | Reconstruction |  | 10.3 | 3.72 | USD | 3.72 | 0.36117
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 |  | P075207C1S3 | Ratio | 2004 / 2013 | Reconstruction |  | 100% | 143.1% |  | 143.1% | 143.1%
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S4 | P075207C1S4 | Estimate | 2004 | Reconstruction | 18 | 33.9 | 6 | USD | 6 | 0.17699
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S4 | P075207C1S4 | Actual | 2013 | Reconstruction |  | 33.9 | 4.5 | USD | 4.5 | 0.13274
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 |  | P075207C1S4 | Ratio | 2004 / 2013 | Reconstruction |  | 100% | 75% |  | 75% | 75%
Zambia | Sub-Saharan Africa | P071985 | C1 | S1 | P071985C1S1 | Estimate | 2004 | Asphalt Mix Resurfacing | 37 | 40 | 12.1 | USD | 12.1 | 0.3025
Zambia | Sub-Saharan Africa | P071985 | C1 | S1 | P071985C1S1 | Actual | 2015 | Asphalt Mix Resurfacing | 33 | 40 | 10.29 | USD | 10.29 | 0.25725
Zambia | Sub-Saharan Africa | P071985 | C1 |  | P071985C1S1 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing | 89.19% | 100% | 85.04% |  | 85.04% | 85.04%
Zambia | Sub-Saharan Africa | P071985 | C1 | S2 | P071985C1S2 | Estimate | 2004 | Asphalt Mix Resurfacing | 18 | 45 | 9.1 | USD | 9.1 | 0.20222
Zambia | Sub-Saharan Africa | P071985 | C1 | S2 | P071985C1S2 | Actual | 2015 | Asphalt Mix Resurfacing | 18 | 45 | 7.3 | USD | 7.3 | 0.16222
Zambia | Sub-Saharan Africa | P071985 | C1 |  | P071985C1S2 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing | 100% | 100% | 80.22% |  | 80.22% | 80.22%
Zambia | Sub-Saharan Africa | P071985 | C1 | S3 | P071985C1S3 | Estimate | 2004 | Asphalt Mix Resurfacing | 23 | 34 | 17.5 | USD | 17.5 | 0.51471 |  |  | x |  | x
Zambia | Sub-Saharan Africa | P071985 | C1 | S3 | P071985C1S3 | Actual | 2015 | Asphalt Mix Resurfacing | 27 | 34 | 8.03 | USD | 8.03 | 0.23618 |  |  | x |  | x
Zambia | Sub-Saharan Africa | P071985 | C1 |  | P071985C1S3 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing | 117.4% | 100% | 45.89% |  | 45.89% | 45.89% |  |  | x |  | x | Quality of estimates; ; | project costs for road works were lower than estimated; ;
Zambia | Sub-Saharan Africa | P071985 | C1 | S4 | P071985C1S4 | Estimate | 2004 | Asphalt Mix Resurfacing |  | 20 | 17.2 | USD | 17.2 | 0.86
Zambia | Sub-Saharan Africa | P071985 | C1 | S4 | P071985C1S4 | Actual | 2015 | Asphalt Mix Resurfacing |  | 20 | 10.7 | USD | 10.7 | 0.535
Zambia | Sub-Saharan Africa | P071985 | C1 |  | P071985C1S4 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing |  | 100% | 62.21% |  | 62.21% | 62.21%
Zambia | Sub-Saharan Africa | AfDB project - P –Z1-DB0 -063 | C1 |  | AfDB project - P –Z1-DB0 -063 C1 | Estimate | 2010 | Reconstruction | 24 | 114.7 | 79.3724 | USD | 79.3724 | 0.692
Zambia | Sub-Saharan Africa | AfDB project - P –Z1-DB0 -063 | C1 |  | AfDB project - P –Z1-DB0 -063 C1 | Actual | 2017 | Reconstruction | 26 | 114.7 | 74.555 | USD | 74.555 | 0.65
Zambia | Sub-Saharan Africa | AfDB project - P –Z1-DB0 -063 | C1 |  | AfDB project - P –Z1-DB0 -063 C1 | Ratio | 2010 / 2017 | Reconstruction | 108.3% | 100% | 93.93% |  | 93.93% | 93.93%

## All Ratios
This tab just shows the ratios (actual/estimate) for the projects where we have complete data. Data comes directly from previous "printout" tab
Country | Region | Project ID | Component | Section | Code | Cost Type | Year | Work Type | Duration | Length (km) | Cost (M) | CCY | Cost (M; USD) | Unit Cost | Agg check | Length_outlier_over | Length_outlier_under | cost_outlier_over | cost_outlier_under | Macroeconomic conditions | Political events | Weather shocks | Procurement system | Administrative processes | Capacity of counterpart | Capacity of contractors | Competition | Quality of estimates | Change of project scope | Outlier Categories
Mozambique | Sub-Saharan Africa | P001785 | C1 |  | P001785C1 | Ratio | 2001 / 2007 | Reconstruction |  | 66.16% | 136.7% |  | 136.7% | 206.6% | x | 0 | 0 | 1 | 0 | 1 |  |  |  |  | 1 | 1 |  |  |  | Macroeconomic conditions ; Capacity of contractors; Capacity of counterpart
Chad | Sub-Saharan Africa | P035672 | C1 | S1 | P035672C1S1 | Ratio | 2000 / 2009 | Strengthening |  | 100% | 109.7% |  | 109.7% | 109.7% |  | 0 | 0 | 0 | 0
Chad | Sub-Saharan Africa | P035672 | C1 | S2 | P035672C1S2 | Ratio | 2000 / 2009 | Upgrading |  | 100% | 173.5% |  | 173.5% | 173.5% | x | 0 | 0 | 1 | 0 | 1 | [5 empty] | 1 |  |  | 1 | Change of project scope ; Capacity of contractors; Macroeconomic conditions
Chad | Sub-Saharan Africa | P035672 | C2 |  | P035672C2 | Ratio | 2000 / 2009 | Routine Maintenance | 118.8% | 100% | 143.1% |  | 143.1% | 143.1% |  | 0 | 0 | 0 | 0
Estonia | Europe and Central Asia | P035775 | C1 |  | P035775C1 | Ratio | 2000 / 2005 | Reconstruction |  | 136.4% | 113.8% |  | 113.8% | 83.48% |  | 0 | 0 | 0 | 0
Georgia | Europe and Central Asia | P040556 | C1 |  | P040556C1 | Ratio | 2000 / 2006 | Strengthening |  | 103.1% | 101.1% |  | 101.1% | 98.11% |  | 0 | 0 | 0 | 0
Vietnam | East Asia and Pacific | P042927 | C1 |  | P042927C1 | Ratio | 2000 / 2011 | Widening | 115.4% | 100% | 171.8% |  | 171.8% | 171.8% | x | 0 | 0 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  |  | Capacity of counterpart; Macroeconomic conditions ;
Croatia | Europe and Central Asia | P043195 | C3 |  | P043195C3 | Ratio | 2003 / 2013 | New 4L Expressway | 130% | 97.85% | 133.7% |  | 133.7% | 136.7% |  | 0 | 0 | 0 | 0
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S1 | P044613C1S1 | Ratio | 2003 / 2010 | Upgrading | 141.7% | 100% | 142% |  | 142% | 142% |  | 0 | 0 | 0 | 0
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S2 | P044613C1S2 | Ratio | 2003 / 2010 | Asphalt Mix Resurfacing | 113.9% | 100% | 150.5% |  | 150.5% | 150.5% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions ; ;
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S3 | P044613C1S3 | Ratio | 2003 / 2010 | Upgrading | 116.7% | 100% | 138.2% |  | 138.2% | 138.2% |  | 0 | 0 | 0 | 0
Ethiopia | Sub-Saharan Africa | P044613 | C1 | S4 | P044613C1S4 | Ratio | 2003 / 2010 | Upgrading | 155.6% | 100% | 176.8% |  | 176.8% | 176.8% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions ; ;
Ethiopia | Sub-Saharan Africa | P044613 | C2 |  | P044613C2 | Ratio | 2003 / 2010 | New 1L Road | 116.7% | 82.91% | 67.79% |  | 67.79% | 81.76% |  | 0 | 0 | 0 | 0
Nepal | South Asia | P045052 | C1 |  | P045052C1 | Ratio | 1999 / 2007 | Surface Treatment Resurfacing |  | 155% | 426.5% |  | 426.5% | 275.2% | x | 1 | 0 | 1 | 0 |  | 1 | [6 empty] | 1 | 1 | Political events; Quality of estimates ; Change of project scope
Nepal | South Asia | P045052 | C2 |  | P045052C2 | Ratio | 1999 / 2007 | Surface Treatment Resurfacing |  | 140.6% | 196.4% |  | 196.4% | 139.7% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P045915 | C1 |  | P045915C1 | Ratio | 2000 / 2008 | New 6L Expressway | 100% | 100% | 111.1% |  | 111.1% | 111.1% |  | 0 | 0 | 0 | 0
Papua New Guinea | East Asia and Pacific | P054238 | C1 |  | P054238C1 | Ratio | 1999 / 2008 | Reconstruction | 190.3% | 100% | 281.9% |  | 281.9% | 281.9% | x | 0 | 0 | 1 | 0 | 1 |  | 1 |  |  | 1 |  |  |  |  | Weather shocks ; Macroeconomic conditions ; Capacity of counterpart
Brazil | Latin America and Caribbean | P055954 | C1 |  | P055954C1 | Ratio | 2001 / 2006 | Surface Treatment Resurfacing |  | 83.33% | 124.1% |  | 124.1% | 148.9% |  | 0 | 0 | 0 | 0
Brazil | Latin America and Caribbean | P055954 | C2 |  | P055954C2 | Ratio | 2001 / 2006 | Asphalt Mix Resurfacing |  | 90% | 93.77% |  | 93.77% | 104.2% |  | 0 | 0 | 0 | 0
Mongolia | East Asia and Pacific | P056200 | C1 |  | P056200C1 | Ratio | 2001 / 2008 | Upgrading |  | 121.6% | 106.9% |  | 106.9% | 87.88% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P056596 | C1 |  | P056596 C1 | Ratio | 2001 / 2009 | Widening |  | 131.9% | 120.1% |  | 120.1% | 91.03% |  | 0 | 0 | 0 | 0
Congo, Dem. Rep. | Sub-Saharan Africa | P057296 | C1 |  | P057296C1 | Ratio | 2007 / 2010 | Strengthening | 342.9% | 83.36% | 143.8% |  | 143.8% | 172.4% | x | 0 | 0 | 1 | 0 |  | 1 |  |  |  | 1 |  |  | 1 |  | Political events ; Quality of estimates ; Capacity of counterpart
China | East Asia and Pacific | P058843 | C1 |  | P058843C1 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing | 125% | 97.92% | 85.7% |  | 85.7% | 87.52% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P058845 | C1 | S1 | P058845C1S1 | Ratio | 2001 / 2007 | New 4L Expressway |  | 98.46% | 68.26% |  | 68.26% | 69.33% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P058845 | C2 |  | P058845C2 | Ratio | 2001 / 2007 | Upgrading |  | 101.1% | 79.17% |  | 79.17% | 78.3% |  | 0 | 0 | 0 | 0
Bhutan | South Asia | P059481 | C1 |  | P059481C1 | Ratio | 1999 / 2006 | New 1L Road | 123.3% | 105.5% | 100.8% |  | 100.8% | 95.51% |  | 0 | 0 | 0 | 0
Burundi | Sub-Saharan Africa | P064876 | C1 |  | P064876C1 | Ratio | 2004 / 2016 | Reconstruction |  | 100% | 145.3% |  | 145.3% | 145.3% |  | 0 | 0 | 0 | 0
Burundi | Sub-Saharan Africa | P064876 | C2 |  | P064876C2 | Ratio | 2004 / 2016 | Gravel Resurfacing |  | 101.4% | 85.26% |  | 85.26% | 84.06% |  | 0 | 0 | 0 | 0
India | South Asia | P067606 | C1 |  | P067606C1 | Ratio | 2002 / 2011 | Upgrading | 125% | 70.55% | 75.87% |  | 75.87% | 107.6% |  | 0 | 0 | 0 | 0
India | South Asia | P067606 | C2 |  | P067606C2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing | 125% | 76% | 120.3% |  | 120.3% | 158.3% | x | 0 | 0 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  |  | Capacity of counterpart; Capacity of counterpart ; Macroeconomic conditions
Nicaragua | Latin America and Caribbean | P068673 | C1 |  | P068673C1 | Ratio | 2000 / 2007 | Partial Widening and Reconstruction |  | 98.65% | 109.1% |  | 109.1% | 110.6% |  | 0 | 0 | 0 | 0
Nicaragua | Latin America and Caribbean | P068673 | C2 |  | P068673C2 | Ratio | 2000 / 2007 | Upgrading |  | 95.67% | 113.7% |  | 113.7% | 118.8% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P068853 | C1 | S1 | P068853C1S1 | Ratio | 1999 / 2004 | Routine Maintenance |  | 55.91% | 137% |  | 137% | 245% | x | 0 | 0 | 1 | 0 | 1 |  | 1 |  |  | 1 |  |  |  |  | Capacity of counterpart ; Weather shocks; Macroeconomic conditions
Albania | Europe and Central Asia | P068853 | C1 | S2 | P068853C1S2 | Ratio | 1999 / 2004 | Routine Maintenance |  | 57.31% | 126.2% |  | 126.2% | 220.2% | x | 0 | 0 | 1 | 0 | 1 |  | 1 |  |  | 1 |  |  |  |  | Capacity of counterpart ; Weather shocks; Macroeconomic conditions
Albania | Europe and Central Asia | P068853 | C1 | S3 | P068853C1S3 | Ratio | 1999 / 2004 | Asphalt Mix Resurfacing | 26.67% | 96.67% | 9.895% |  | 9.895% | 10.24% | x | 0 | 0 | 0 | 1 | 1 |  | 1 |  |  | 1 |  |  |  |  | Capacity of counterpart ; Weather shocks; Macroeconomic conditions
Albania | Europe and Central Asia | P068853 | C1 | S4 | P068853C1S4 | Ratio | 1999 / 2004 | Routine Maintenance | 53.33% | 87.14% | 111.3% |  | 111.3% | 127.7% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P068853 | C1 | S5 | P068853C1S5 | Ratio | 1999 / 2004 | Asphalt Mix Resurfacing | 293.3% | 79% | 118% |  | 118% | 149.3% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P068853 | C1 | S6 | P068853C1S6 | Ratio | 1999 / 2004 | Routine Maintenance | 26.67% | 6.25% | 12.17% |  | 12.17% | 194.7% | x | 0 | 1 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  |  | Capacity of counterpart ; Capacity of counterpart ; Macroeconomic conditions
India | South Asia | P069889 | C1 |  | P069889C1 | Ratio | 2007 / 2011 | Widening and Reconstruction |  | 94.57% | 238.3% |  | 238.3% | 252% | x | 0 | 0 | 1 | 0 | 1 |  | 1 |  |  |  | 1 |  |  |  | Capacity of contractors; Weather shocks ; Macroeconomic conditions
India | South Asia | P069889 | C2 |  | P069889C2 | Ratio | 2007 / 2011 | Surface Treatment Resurfacing |  | 57.69% | 64.55% |  | 64.55% | 111.9% |  | 0 | 0 | 0 | 0
Yemen, Rep. | East Asia and Pacific | P070391 | C1 |  | P070391C1 | Ratio | 2001 / 2007 | Reconstruction |  | 200.9% | 86.19% |  | 86.19% | 42.91% | x | 1 | 0 | 0 | 1 | 1 | [7 empty] | 1 | 1 | Macroeconomic conditions ; Quality of estimates ; Change of project scope
Yemen, Rep. | East Asia and Pacific | P070391 | C2 |  | P070391C2 | Ratio | 2001 / 2007 | Upgrading |  | 162.7% | 138.2% |  | 138.2% | 84.96% | x | 1 | 0 | 0 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions ; Quality of estimates ;
China | East Asia and Pacific | P070519 | C1 | S1 | P070519C1S1 | Ratio | 2005 / 2013 | New 6L Expressway |  | 100% | 205.7% |  | 205.7% | 205.7% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions ; Quality of estimates;
China | East Asia and Pacific | P070519 | C1 | S2 | P070519C1S2 | Ratio | 2005 / 2013 | New 4L Expressway |  | 100% | 105% |  | 105% | 105% |  | 0 | 0 | 0 | 0
India | South Asia | P071244 | C1 |  | P071244C1 | Ratio | 2001 / 2009 | Widening |  | 99.23% | 112.4% |  | 112.4% | 113.2% |  | 0 | 0 | 0 | 0
Bangladesh | South Asia | P071435 | C1 |  | P071435C1 | Ratio | 2003 / 2013 | Partial Widening |  | 101.4% | 136% |  | 95.6% | 94.31% |  | 0 | 0 | 0 | 0
Bangladesh | South Asia | P071435 | C2 |  | P071435C2 | Ratio | 2003 / 2013 | Upgrading |  | 103% | 154.4% |  | 108.5% | 105.4% |  | 0 | 0 | 0 | 0
Bangladesh | South Asia | P071435 | C3 |  | P071435C3 | Ratio | 2003 / 2013 | Asphalt Mix Resurfacing |  | 141.3% | 152.7% |  | 107.4% | 76% |  | 0 | 0 | 0 | 0
Madagascar | Sub-Saharan Africa | P073689 | C1 |  | P073689C1 | Ratio | 2002 / 2013 | Reconstruction |  | 46.67% | 93.33% |  | 93.33% | 200% | x | 0 | 1 | 1 | 0 | [9 empty] | 1 | Change of project scope ; ;
India | South Asia | P073776 | C1 |  | P073776C1 | Ratio | 2003 / 2010 | New 4L Expressway | 262.5% | 100.1% | 125.4% |  | 125.4% | 125.2% |  | 0 | 0 | 0 | 0
Uganda | Sub-Saharan Africa | P074079 | C1 | S1 | P074079C1S1 | Ratio | 2004 / 2012 | Upgrading |  | 98.4% | 220.2% |  | 220.2% | 223.8% | x | 0 | 0 | 1 | 0 | 1 | 1 | [6 empty] | 1 |  | Macroeconomic conditions; Political events ; Quality of estimates
Uganda | Sub-Saharan Africa | P074079 | C1 | S2 | P074079C1S2 | Ratio | 2004 / 2012 | Upgrading |  | 22.06% | 185.1% |  | 185.1% | 839.2% | x | 0 | 1 | 1 | 0 | 1 | 1 | [6 empty] | 1 |  | Macroeconomic conditions; Political events ; Quality of estimates
Cameroon | Sub-Saharan Africa | P074490 | C1 |  | P074490C1 | Ratio | 2002 / 2010 | Widening and Reconstruction |  | 117.4% | 116.8% |  | 116.8% | 99.47% |  | 0 | 0 | 0 | 0
Thailand | East Asia and Pacific | P075173 | C2 |  | P075173C2 | Ratio | 2003 / 2013 | Widening | 100% | 118.2% | 80.56% |  | 80.56% | 68.17% |  | 0 | 0 | 0 | 0
Vietnam | East Asia and Pacific | P075407 | C1 |  | P075407C1 | Ratio | 2006 / 2014 | Surface Treatment Resurfacing |  | 104.2% | 191.5% |  | 191.5% | 183.7% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 | 1 | Macroeconomic conditions ; Change of project scope ; Quality of estimates
Vietnam | East Asia and Pacific | P075407 | C2 |  | P075407C2 | Ratio | 2006 / 2014 | Routine Maintenance | 100% | 165.9% | 318.2% |  | 318.2% | 191.8% | x | 1 | 0 | 1 | 0 | 1 | [7 empty] | 1 | 1 | Macroeconomic conditions ; Change of project scope; Quality of estimates
Lesotho | Sub-Saharan Africa | P075566 | C1 |  | P075566C1 | Ratio | 2006 / 2015 | Strengthening |  | 207.5% | 300.5% |  | 300.5% | 144.8% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
China | East Asia and Pacific | P076714 | C1 |  | P076714C1 | Ratio | 2003 / 2009 | New 4L Expressway | 92.86% | 99.97% | 84.81% |  | 102.6% | 102.6% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P076714 | C1 | S1 | P076714C1S1 | Ratio | 2003 / 2009 | New 4L Expressway |  | 114.2% | 113.5% |  | 137.2% | 120.2% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P076714 | C1 | S2 | P076714C1S2 | Ratio | 2003 / 2009 | New 4L Expressway |  | 84.37% | 107.9% |  | 130.5% | 154.6% | x | 0 | 0 | 1 | 0 | 1 | [6 empty] | 1 |  |  | Macroeconomic conditions ; Competition;
China | East Asia and Pacific | P076714 | C1 | S3 | P076714C1S3 | Ratio | 2003 / 2009 | New 4L Expressway |  | 95.58% | 29.47% |  | 35.65% | 37.29% | x | 0 | 0 | 0 | 1 | [8 empty] | 1 |  | Quality of estimates; ;
China | East Asia and Pacific | P076714 | C2 |  | P076714C2 | Ratio | 2003 / 2009 | Upgrading |  | 96.09% | 72.1% |  | 87.2% | 90.74% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P076714 | C2 | S1 | P076714C2S1 | Ratio | 2003 / 2009 | Upgrading |  | 100.1% | 66.42% |  | 80.33% | 80.22% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P076714 | C2 | S2 | P076714C2S2 | Ratio | 2003 / 2009 | Upgrading |  | 111.4% | 94.86% |  | 114.7% | 103% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P076714 | C2 | S3 | P076714C2S3 | Ratio | 2003 / 2009 | Upgrading |  | 82.73% | 84.55% |  | 102.2% | 123.6% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P076714 | C2 | S4 | P076714C2S4 | Ratio | 2003 / 2009 | Upgrading |  | 86.05% | 72.67% |  | 87.88% | 102.1% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P076714 | C2 | S5 | P076714C2S5 | Ratio | 2003 / 2009 | Upgrading |  | 98.65% | 53.85% |  | 65.12% | 66.01% |  | 0 | 0 | 0 | 0
India | South Asia | P077856 | C1 |  | P077856C1 | Ratio | 2004 / 2012 | Widening | 175% | 67.7% | 99.66% |  | 99.66% | 147.2% |  | 0 | 0 | 0 | 0
Sierra Leone | Sub-Saharan Africa | P078389 | C1 |  | P078389C1 | Ratio | 2005 / 2014 | Gravel Resurfacing |  | 74.31% | 124.8% |  | 124.8% | 168% | x | 0 | 0 | 1 | 0 |  | 1 | [5 empty] | 1 |  |  | Political events; Competition;
Albania | Europe and Central Asia | P078949 | C1 | S1 | P078949C1S1 | Ratio | 2007 / 2011 | New 4L Expressway | 222.7% | 100% | 117.5% |  | 117.5% | 117.5% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P078949 | C1 | S2 | P078949C1S2 | Ratio | 2007 / 2011 | New 4L Expressway | 372.7% | 100% | 96.63% |  | 96.63% | 96.63% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P078949 | C1 | S3 | P078949C1S3 | Ratio | 2007 / 2011 | New 4L Expressway | 218.8% | 100% | 103.3% |  | 103.3% | 103.3% |  | 0 | 0 | 0 | 0
Rwanda | Sub-Saharan Africa | P079414 | C1 | S1 | P079414C1S1 | Ratio | 2007 / 2015 | Partial Widening and Reconstruction | 122.2% | 100% | 126.6% |  | 126.6% | 126.6% |  | 0 | 0 | 0 | 0
Mali | Sub-Saharan Africa | P079749_2 | C1 | S2 | P079749_2C1S2 | Ratio | 2008 / 2015 | Asphalt Mix Resurfacing |  | 129.2% | 690% |  | 690% | 534% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 |  | Quality of estimates; ;
China | East Asia and Pacific | P081749 | C1 |  | P081749C1 | Ratio | 2004 / 2010 | New 4L Expressway | 100% | 101.2% | 167.8% |  | 167.8% | 165.7% | x | 0 | 0 | 1 | 0 |  |  | 1 | [5 empty] | 1 |  | Weather shocks; Quality of estimates;
China | East Asia and Pacific | P081749 | C2 | S1 | P081749C2S1 | Ratio | 2004 / 2010 | Upgrading | 100% | 99.28% | 84.55% |  | 102.5% | 103.3% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 |  | P082754C1 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 83.2% | 119.1% |  | 132.3% | 159% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Morocco | Middle East and North Africa | P082754 | C1 | S1 | P082754C1S1 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 77.92% | 91.6% |  | 101.7% | 130.5% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S10 | P082754C1S10 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 97.78% | 167.2% |  | 185.7% | 189.9% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Morocco | Middle East and North Africa | P082754 | C1 | S11 | P082754C1S11 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 95% | 234.7% |  | 260.6% | 274.3% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Morocco | Middle East and North Africa | P082754 | C1 | S12 | P082754C1S12 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 103.2% | 101.8% |  | 113% | 109.5% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S2 | P082754C1S2 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 100.4% | 109.2% |  | 121.3% | 120.9% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S3 | P082754C1S3 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 110% | 135.9% |  | 150.9% | 137.2% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S4 | P082754C1S4 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 97.86% | 108.5% |  | 120.5% | 123.1% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S5 | P082754C1S5 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 101% | 88.58% |  | 98.35% | 97.38% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S6 | P082754C1S6 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 92.5% | 123.5% |  | 137.2% | 148.3% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S7 | P082754C1S7 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 88.46% | 93.99% |  | 104.4% | 118% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S8 | P082754C1S8 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 86.15% | 93.99% |  | 104.4% | 121.1% |  | 0 | 0 | 0 | 0
Morocco | Middle East and North Africa | P082754 | C1 | S9 | P082754C1S9 | Ratio | 2004 / 2011 | Reconstruction | 127.8% | 144.4% | 204.7% |  | 227.3% | 157.3% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Madagascar | Sub-Saharan Africa | P082806 | C1 | S1 | P082806C1S1 | Ratio | 2003 / 2013 | Asphalt Mix Resurfacing | 162.5% | 126.3% | 637.9% |  | 637.9% | 505.1% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [7 empty] | ; Weather shocks; Macroeconomic conditions
Madagascar | Sub-Saharan Africa | P082806 | C1 | S2 | P082806C1S2 | Ratio | 2003 / 2013 | Asphalt Mix Resurfacing | 100% | 48.78% | 190.1% |  | 190.1% | 389.7% | x | 0 | 1 | 1 | 0 | 1 |  | 1 | [6 empty] | 1 | Weather shocks; Change of project scope; Macroeconomic conditions
Madagascar | Sub-Saharan Africa | P082806 | C1 | S3 | P082806C1S3 | Ratio | 2003 / 2013 | Gravel Resurfacing | 27.78% | 101.1% | 9.88% |  | 9.88% | 9.772% | x | 0 | 0 | 0 | 1 | [9 empty] | 1 | ; Change of project scope;
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S1 | P082998C1S1 | Ratio | 2004 / 2012 | Upgrading |  | 77.85% | 316.8% |  | 316.8% | 406.9% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 | 1 | Quality of estimates; Change of project scope;
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S2 | P082998C1S2 | Ratio | 2004 / 2012 | Upgrading |  | 100% | 243.4% |  | 243.4% | 243.4% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 | 1 | Quality of estimates; Change of project scope;
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S3 | P082998C1S3 | Ratio | 2004 / 2012 | Upgrading |  | 100% | 316.5% |  | 316.5% | 316.5% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 | 1 | Quality of estimates; Change of project scope;
Ethiopia | Sub-Saharan Africa | P082998 | C1 | S4 | P082998C1S4 | Ratio | 2004 / 2007 | Upgrading | 175% | 100% | 427.5% |  | 427.5% | 427.5% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 | 1 | Quality of estimates; Change of project scope;
Ethiopia | Sub-Saharan Africa | P082998 | C2 | S1 | P082998C2S1 | Ratio | 2004 / 2012 | New 2L Highway |  | 100% | 265.7% |  | 265.7% | 265.7% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 | 1 | Quality of estimates; Change of project scope;
Ethiopia | Sub-Saharan Africa | P082998 | C2 | S2 | P082998C2S2 | Ratio | 2004 / 2012 | New 2L Highway |  | 100% | 395.1% |  | 395.1% | 395.1% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 | 1 | Quality of estimates; Change of project scope;
Vietnam | East Asia and Pacific | P083588 | C1 |  | P083588 C1 | Ratio | 2007 / 2017 | Widening and Reconstruction | 219.4% | 62.24% | 101.2% |  | 101.2% | 162.6% | x | 0 | 0 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  |  | Macroeconomic conditions; Capacity of Counterpart ;
Nepal | South Asia | P083923 | C1 | S1 | P083923C1S1 | Ratio | 2005 / 2014 | Upgrading |  | 217.6% | 271.5% |  | 271.5% | 124.8% | x | 1 | 0 | 0 | 0 | 1 |  |  | 1 | [5 empty] | 1 | Change of project scope ; Macroeconomic conditions; Procurement system
Nepal | South Asia | P083923 | C1 | S2 | P083923C1S2 | Ratio | 2005 / 2014 | Upgrading |  | 70% | 76% |  | 76% | 108.6% |  | 0 | 0 | 0 | 0
Nepal | South Asia | P083923 | C1 | S3 | P083923C1S3 | Ratio | 2005 / 2014 | Routine Maintenance |  | 131.4% | 201.5% |  | 201.5% | 153.3% | x | 0 | 0 | 1 | 0 |  | 1 | [6 empty] | 1 |  | Quality of estimates; Political events; Capacity
Nicaragua | Latin America and Caribbean | P083952 | C1 |  | P083952C1 | Ratio | 2006 / 2015 | Strengthening |  | 101.1% | 135.1% |  | 135.1% | 133.6% |  | 0 | 0 | 0 | 0
Nicaragua | Latin America and Caribbean | P083952 | C2 |  | P083952C2 | Ratio | 2006 / 2015 | Reconstruction |  | 112.8% | 207.1% |  | 207.1% | 183.6% | x | 0 | 0 | 1 | 0 | 1 | [8 empty] | 1 | Macroeconomic conditions; Change of project scope;
Nicaragua | Latin America and Caribbean | P083952 | C3 |  | P083952C3 | Ratio | 2006 / 2015 | Routine Maintenance |  | 129% | 160.5% |  | 160.5% | 124.4% |  | 0 | 0 | 0 | 0
Sri Lanka | South Asia | P086411 | C1 |  | P086411C1 | Ratio | 2005 / 2016 | Upgrading |  | 24.72% | 130.2% |  | 130.2% | 526.5% | x | 0 | 1 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Sri Lanka | South Asia | P086411 | C2 |  | P086411C2 | Ratio | 2005 / 2016 | Widening |  | 99.52% | 212.4% |  | 212.4% | 213.5% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 | 1 | Macroeconomic conditions; Change of project scope; Quality of estimates
Mali | Sub-Saharan Africa | P090075 | C1 |  | P090075C1 | Ratio | 2007 / 2016 | Gravel Resurfacing |  | 115.6% | 94.78% |  | 94.78% | 82% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P091020 | C1 |  | P091020C1 | Ratio | 2006 / 2015 | New 4L Expressway |  | 100% | 158.7% |  | 158.7% | 158.7% | x | 0 | 0 | 1 | 0 |  | 1 | 1 | [7 empty] | Weather shocks; Political events; Capacity
China | East Asia and Pacific | P091020 | C2 |  | P091020C2 | Ratio | 2006 / 2015 | Strengthening |  | 243.7% | 269.6% |  | 355.1% | 145.7% | x | 1 | 0 | 0 | 0 | [10 empty] | Capacity; ;
China | East Asia and Pacific | P091020 | C2 | S1 | P091020C2S1 | Ratio | 2006 / 2015 | Strengthening |  | 359.1% | 528.3% |  | 696.1% | 193.9% | x | 1 | 0 | 1 | 0 | [9 empty] | 1 | Change of project scope; ;
China | East Asia and Pacific | P091020 | C2 | S2 | P091020C2S2 | Ratio | 2006 / 2015 | Strengthening |  | 219.9% | 202.5% |  | 266.7% | 121.3% | x | 1 | 0 | 0 | 0 | [10 empty] | Capacity; ;
China | East Asia and Pacific | P091020 | C2 | S3 | P091020C2S3 | Ratio | 2006 / 2015 | Strengthening |  | 168% | 179% |  | 235.8% | 140.4% | x | 1 | 0 | 0 | 0 | [10 empty] | Capacity; ;
China | East Asia and Pacific | P091020 | C2 | S4 | P091020C2S4 | Ratio | 2006 / 2015 | Strengthening |  | 282.8% | 305.5% |  | 402.6% | 142.4% | x | 1 | 0 | 0 | 0 | [10 empty] | Capacity; ;
China | East Asia and Pacific | P091020 | C2 | S5 | P091020C2S5 | Ratio | 2006 / 2015 | Strengthening |  | 217.3% | 237.2% |  | 312.5% | 143.8% | x | 1 | 0 | 0 | 0 | [10 empty] | Capacity; ;
China | East Asia and Pacific | P091020 | C2 | S6 | P091020C2S6 | Ratio | 2006 / 2015 | Strengthening |  | 487% | 588.8% |  | 775.7% | 159.3% | x | 1 | 0 | 1 | 0 | [9 empty] | 1 | Change of project scope; ;
China | East Asia and Pacific | P091020 | C2 | S7 | P091020C2S7 | Ratio | 2006 / 2015 | Strengthening |  | 136.3% | 138% |  | 181.9% | 133.5% |  | 0 | 0 | 0 | 0
Macedonia, FYR | Europe and Central Asia | P091723 | C1 |  | P091723C1 | Ratio | 2007 / 2012 | Widening | 126.9% | 100% | 138.4% |  | 138.4% | 138.4% |  | 0 | 0 | 0 | 0
Bulgaria | Europe and Central Asia | P094018 | C1 |  | P094018C1 | Ratio | 2007 / 2014 | New 4L Expressway | 136.8% | 100% | 114% |  | 114% | 114% |  | 0 | 0 | 0 | 0
Sudan | Sub-Saharan Africa | P095081 | C1 | S1 | P095081C1S1 | Ratio | 2006 / 2013 | Upgrading |  | 68% | 146% |  | 146% | 214.7% | x | 0 | 0 | 1 | 0 |  | 1 | [7 empty] | 1 | Capacity; Change of project scope; Political events
Sudan | Sub-Saharan Africa | P095081 | C1 | S2 | P095081C1S2 | Ratio | 2006 / 2013 | Asphalt Mix Resurfacing |  | 285% | 150.6% |  | 150.6% | 52.85% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
Sudan | Sub-Saharan Africa | P095081 | C1 | S3 | P095081C1S3 | Ratio | 2006 / 2013 | Gravel Resurfacing |  | 70.61% | 171.8% |  | 171.8% | 243.2% | x | 0 | 0 | 1 | 0 |  | 1 | [7 empty] | 1 | Capacity; Change of project scope; Political events
Brazil | Latin America and Caribbean | P095460 | C1 |  | P095460C1 | Ratio | 2006 / 2014 | Asphalt Mix Resurfacing |  | 59.8% | 138% |  | 138% | 230.8% | x | 0 | 0 | 1 | 0 | 1 |  |  |  |  | 1 |  |  | 1 |  | Macroeconomic conditions; Quality of estimates; Capacity of Counterpart
Poland | Europe and Central Asia | P096214 | C1 |  | P096214C1 | Ratio | 2006 / 2012 | Asphalt Mix Resurfacing |  | 122.6% | 108.9% |  | 108.9% | 88.89% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P099112 | C1 |  | P099112C1 | Ratio | 2008 / 2012 | Strengthening | 91.67% | 94.95% | 117.4% |  | 117.4% | 123.7% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P099112 | C2 |  | P099112C2 | Ratio | 2008 / 2012 | Upgrading |  | 100.2% | 129.1% |  | 129.1% | 128.9% |  | 0 | 0 | 0 | 0
Argentina | Latin America and Caribbean | P099585 | C1 |  | P099585C1 | Ratio | 2006 / 2014 | Strengthening |  | 71.73% | 119.7% |  | 119.7% | 166.9% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Quality of estimates; Macroeconomic conditions;
Argentina | Latin America and Caribbean | P099585 | C2 |  | P099585C2 | Ratio | 2006 / 2014 | Strengthening |  | 32.29% | 122.9% |  | 122.9% | 380.6% | x | 0 | 1 | 1 | 0 | 1 | 1 | [6 empty] | 1 |  | Quality of estimates; Macroeconomic conditions; Political events
China | East Asia and Pacific | P099992 | C1 |  | P099992C1 | Ratio | 2006 / 2014 | Widening and Reconstruction |  | 59.78% | 48.85% |  | 48.85% | 81.72% |  | 0 | 0 | 0 | 0
Ukraine | Europe and Central Asia | P100580 | C1 |  | P100580C1 | Ratio | 2009 / 2015 | Reconstruction | 124% | 125.5% | 149.2% |  | 76.29% | 60.79% |  | 0 | 0 | 0 | 0
Moldova | Europe and Central Asia | P100929 | C1 |  | P100929C1 | Ratio | 2005 / 2013 | Widening and Reconstruction |  | 48.39% | 152.7% |  | 152.7% | 315.6% | x | 0 | 1 | 1 | 0 |  |  |  | 1 |  |  |  |  | 1 | 1 | Procurement system; Change of project scope; Quality of estimates
Brazil | Latin America and Caribbean | P106663 | C1 |  | P106663C1 | Ratio | 2009 / 2015 | Reconstruction |  | 206.7% | 211.8% |  | 211.8% | 102.4% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | ; Change of project scope;
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 | S1 | P107608C1S1 | Ratio | 2009 / 2015 | Upgrading | 108.3% | 106.7% | 93.45% |  | 93.45% | 87.61% |  | 0 | 0 | 0 | 0
Kyrgyz Republic | Europe and Central Asia | P107608 | C1 | S2 | P107608C1S2 | Ratio | 2015 / 2011 | Upgrading |  | 100.6% | 109.8% |  | 109.8% | 109.2% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C1 | S1 | P107833C1S1 | Ratio | 2008 / 2013 | Reconstruction | 240% | 100% | 73.97% |  | 73.97% | 73.97% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C1 | S2 | P107833C1S2 | Ratio | 2008 / 2013 | Reconstruction | 150% | 100% | 97.57% |  | 97.57% | 97.57% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C1 | S3 | P107833C1S3 | Ratio | 2008 / 2013 | Reconstruction | 120% | 100% | 83.27% |  | 83.27% | 83.27% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S1 | P107833C2S1 | Ratio | 2008 / 2013 | Reconstruction | 109.1% | 100% | 58.7% |  | 58.7% | 58.7% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S2 | P107833C2S2 | Ratio | 2008 / 2013 | Reconstruction | 200% | 100% | 88.13% |  | 88.13% | 88.13% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S3 | P107833C2S3 | Ratio | 2008 / 2013 | Reconstruction | 92.31% | 100% | 89.21% |  | 89.21% | 89.21% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S4 | P107833C2S4 | Ratio | 2008 / 2013 | Reconstruction | 171.4% | 100% | 139.7% |  | 139.7% | 139.7% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S5 | P107833C2S5 | Ratio | 2008 / 2013 | Reconstruction | 100% | 100% | 109% |  | 109% | 109% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S6 | P107833C2S6 | Ratio | 2008 / 2013 | Reconstruction | 120% | 100% | 64.31% |  | 64.31% | 64.31% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S7 | P107833C2S7 | Ratio | 2008 / 2013 | Reconstruction | 150% | 100% | 95.63% |  | 95.63% | 95.63% |  | 0 | 0 | 0 | 0
Albania | Europe and Central Asia | P107833 | C2 | S8 | P107833C2S8 | Ratio | 2008 / 2013 | Reconstruction | 200% | 100% | 69.35% |  | 69.35% | 69.35% |  | 0 | 0 | 0 | 0
Armenia | Europe and Central Asia | P115486 | C1 |  | P115486C1 | Ratio | 2009 / 2014 | Reconstruction | 614.3% | 446.9% | 430.3% |  | 430.3% | 96.28% | x | 1 | 0 | 0 | 0 | [6 empty] | 1 |  |  | 1 | Capacity of contractors; Change of project scope;
Papua New Guinea | East Asia and Pacific | P004397 | C1 | S1 | P004397C1S1 | Ratio | 2002 / 2012 | Routine Maintenance | 400% | 81.27% |  |  | 196.3% | 241.6% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [7 empty] | Macroeconomic conditions; Weather shocks ;
Papua New Guinea | East Asia and Pacific | P004397 | C1 | S2 | P004397C1S2 | Ratio | 2002 / 2012 | Reconstruction |  | 141.5% |  |  | 545.9% | 385.9% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [7 empty] | Macroeconomic conditions; Weather shocks ;
Papua New Guinea | East Asia and Pacific | P004397 | C2 | S1 | P004397C2S1 | Ratio | 2002 / 2012 | Routine Maintenance | 400% | 73.78% |  |  | 62.11% | 84.18% |  | 0 | 0 | 0 | 0
Papua New Guinea | East Asia and Pacific | P004397 | C2 | S2 | P004397C2S2 | Ratio | 2002 / 2012 | Reconstruction |  | 78% |  |  | 459.7% | 589.4% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [7 empty] | Macroeconomic conditions; Weather shocks;
India | South Asia | P009972 | C1 | S1 | P009972C1S1 | Ratio | 2000 / 2008 | Widening and Reconstruction | 183.3% | 100% |  |  | 72.25% | 72.25% |  | 0 | 0 | 0 | 0
India | South Asia | P009972 | C1 | S2 | P009972C1S2 | Ratio | 2000 / 2008 | Widening and Reconstruction | 232.5% | 100% |  |  | 62.41% | 62.41% |  | 0 | 0 | 0 | 0
India | South Asia | P009972 | C1 | S3 | P009972C1S3 | Ratio | 2000 / 2008 | Widening and Reconstruction | 127.8% | 100% |  |  | 76.8% | 76.8% |  | 0 | 0 | 0 | 0
India | South Asia | P009972 | C1 | S4 | P009972C1S4 | Ratio | 2000 / 2008 | Widening and Reconstruction | 212.8% | 100% |  |  | 73.48% | 73.48% |  | 0 | 0 | 0 | 0
India | South Asia | P009972 | C1 | S5 | P009972C1S5 | Ratio | 2000 / 2008 | Widening and Reconstruction | 175% | 112.5% |  |  | 72.63% | 64.56% |  | 0 | 0 | 0 | 0
India | South Asia | P009972 | C1 | S6 | P009972C1S6 | Ratio | 2000 / 2008 | Widening and Reconstruction | 158.3% | 88.89% |  |  | 71.59% | 80.54% |  | 0 | 0 | 0 | 0
India | South Asia | P009972 | C1 | S7 | P009972C1S7 | Ratio | 2000 / 2008 | Widening and Reconstruction | 200% | 100% |  |  | 77.6% | 77.6% |  | 0 | 0 | 0 | 0
Pakistan | South Asia | P010556 | C1 | S10 | P010556C1S10 | Ratio | 2003 / 2013 | Bituminous Pavement Preventive Treatment |  | 170.8% |  |  | 188.7% | 110.4% | x | 1 | 0 | 0 | 0 |  |  | 1 | [6 empty] | 1 | Change of project scope; Weather shocks;
Pakistan | South Asia | P010556 | C1 | S14 | P010556C1S14 | Ratio | 2003 / 2013 | Bituminous Pavement Preventive Treatment |  | 179% |  |  | 216.7% | 121.1% | x | 1 | 0 | 0 | 0 |  |  | 1 | [6 empty] | 1 | Change of project scope; Weather shocks;
Pakistan | South Asia | P010556 | C1 | S15 | P010556C1S15 | Ratio | 2003 / 2013 | Reconstruction |  | 100% |  |  | 136.2% | 136.2% |  | 0 | 0 | 0 | 0
Pakistan | South Asia | P010556 | C1 | S4 | P010556C1S4 | Ratio | 2003 / 2013 | Reconstruction |  | 96.63% |  |  | 72.01% | 74.52% |  | 0 | 0 | 0 | 0
Pakistan | South Asia | P010556 | C1 | S5 | P010556C1S5 | Ratio | 2003 / 2013 | Reconstruction |  | 93.11% |  |  | 87.9% | 94.4% |  | 0 | 0 | 0 | 0
Pakistan | South Asia | P010556 | C1 | S6 | P010556C1S6 | Ratio | 2003 / 2013 | Reconstruction |  | 102.2% |  |  | 85.54% | 83.72% |  | 0 | 0 | 0 | 0
Pakistan | South Asia | P010556 | C1 | S7 | P010556C1S7 | Ratio | 2003 / 2013 | Widening and Reconstruction |  | 100% |  |  | 91.17% | 91.17% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P039019 | C1 | S1 | P039019C1S1 | Ratio | 2000 / 2008 | Upgrading |  | 99.76% |  |  | 83.51% | 83.71% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P039019 | C1 | S2 | P039019C1S2 | Ratio | 2000 / 2008 | Upgrading |  | 112.3% |  |  | 151.7% | 135% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P039019 | C1 | S3 | P039019C1S3 | Ratio | 2000 / 2008 | Upgrading |  | 100.4% |  |  | 82.7% | 82.34% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P039019 | C1 | S4 | P039019C1S4 | Ratio | 2000 / 2008 | Upgrading |  | 31.83% |  |  | 103.2% | 324.1% | x | 0 | 1 | 1 | 0 |  |  | 1 | 1 |  | 1 |  |  | 1 |  | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks
Philippines | East Asia and Pacific | P039019 | C1 | S5 | P039019C1S5 | Ratio | 2000 / 2008 | Upgrading |  | 114.3% |  |  | 428.1% | 374.4% | x | 0 | 0 | 1 | 0 |  |  | 1 | 1 |  | 1 |  |  | 1 |  | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks
Philippines | East Asia and Pacific | P039019 | C1 | S8 | P039019C1S8 | Ratio | 2000 / 2008 | Upgrading |  | 100.2% |  |  | 185% | 184.6% | x | 0 | 0 | 1 | 0 |  |  | 1 | 1 |  | 1 |  |  | 1 |  | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks
Philippines | East Asia and Pacific | P039019 | C1 | S9 | P039019C1S9 | Ratio | 2000 / 2008 | Upgrading |  | 100.2% |  |  | 136.1% | 135.9% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P039019 | C2 |  | P039019C2 | Ratio | 2000 / 2008 | Asphalt Mix Resurfacing |  | 80.14% |  |  | 88.64% | 110.6% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P039019 | C3 |  | P039019C3 | Ratio | 2000 / 2008 | Asphalt Mix Resurfacing |  | 110% |  |  | 207.3% | 188.6% | x | 0 | 0 | 1 | 0 |  |  | 1 | 1 |  | 1 |  |  | 1 |  | Capacity of counterpart (Procurement system); Quality of estimates; Weather shocks
Belize | Latin America and Caribbean | P040150 | C1 | S1 | P040150C1S1 | Ratio | 2000 / 2006 | Upgrading |  | 100% |  |  | 127.6% | 127.6% |  | 0 | 0 | 0 | 0
Indonesia | East Asia and Pacific | P040578 | C1 | S1 | P040578C1S1 | Ratio | 2001 / 2006 | Asphalt Mix Resurfacing |  | 111.1% |  |  | 112.4% | 101.2% |  | 0 | 0 | 0 | 0
Indonesia | East Asia and Pacific | P040578 | C1 | S2 | P040578C1S2 | Ratio | 2001 / 2006 | Reconstruction |  | 136.4% |  |  | 140.3% | 102.9% |  | 0 | 0 | 0 | 0
Azerbaijan | Europe and Central Asia | P040716 | C1 | S1 | P040716C1S1 | Ratio | 2001 / 2009 | Reconstruction |  | 100% |  |  | 83.24% | 83.24% |  | 0 | 0 | 0 | 0
Azerbaijan | Europe and Central Asia | P040716 | C1 | S2 | P040716C1S2 | Ratio | 2001 / 2009 | Reconstruction |  | 100% |  |  | 89.46% | 89.46% |  | 0 | 0 | 0 | 0
Peru | Latin America and Caribbean | P044601 | C1 |  | P044601C1 | Ratio | 2001 / 2007 | Reconstruction |  | 131.2% |  |  | 105.9% | 80.68% |  | 0 | 0 | 0 | 0
Peru | Latin America and Caribbean | P044601 | C2 |  | P044601C2 | Ratio | 2001 / 2007 | Routine Maintenance |  | 109.3% |  |  | 74.5% | 68.16% |  | 0 | 0 | 0 | 0
Armenia | Europe and Central Asia | P044829 | C1 |  | P044829C1 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 64.73% |  |  | 124.3% | 192% | x | 0 | 0 | 1 | 0 |  | 1 | [8 empty] | Political events ; ;
Armenia | Europe and Central Asia | P044829 | C1 | S1 | P044829C1S1 | Ratio | 2000 / 2005 | Surface Treatment Resurfacing |  | 100% |  |  | 100.8% | 100.8% |  | 0 | 0 | 0 | 0
Armenia | Europe and Central Asia | P044829 | C1 | S2 | P044829C1S2 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% |  |  | 117.7% | 117.7% |  | 0 | 0 | 0 | 0
Armenia | Europe and Central Asia | P044829 | C1 | S3 | P044829C1S3 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% |  |  | 113.6% | 113.6% |  | 0 | 0 | 0 | 0
Armenia | Europe and Central Asia | P044829 | C1 | S4 | P044829C1S4 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% |  |  | 92.67% | 92.67% |  | 0 | 0 | 0 | 0
Armenia | Europe and Central Asia | P044829 | C1 | S5 | P044829C1S5 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% |  |  | 108.7% | 108.7% |  | 0 | 0 | 0 | 0
Armenia | Europe and Central Asia | P044829 | C1 | S6 | P044829C1S6 | Ratio | 2000 / 2005 | Asphalt Mix Resurfacing |  | 100% |  |  | 90.32% | 90.32% |  | 0 | 0 | 0 | 0
India | South Asia | P050649 | C1 |  | P050649C1 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 96.53% |  |  | 120.2% | 124.5% |  | 0 | 0 | 0 | 0
India | South Asia | P050649 | C1 | S1 | P050649C1S1 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 94.41% |  |  | 96.37% | 102.1% |  | 0 | 0 | 0 | 0
India | South Asia | P050649 | C1 | S2 | P050649C1S2 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 102.2% |  |  | 160.8% | 157.2% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [5 empty] | 1 |  | Macroeconomic conditions ; Weather shocks; Quality of estimates
India | South Asia | P050649 | C1 | S3 | P050649C1S3 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 100% |  |  | 201% | 201% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [5 empty] | 1 |  | Macroeconomic conditions ; Weather shocks; Quality of estimates
India | South Asia | P050649 | C1 | S4 | P050649C1S4 | Ratio | 2003 / 2012 | Widening and Reconstruction |  | 97.12% |  |  | 177.3% | 182.6% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [5 empty] | 1 |  | Macroeconomic conditions ; Weather shocks; Quality of estimates
India | South Asia | P050649 | C2 |  | P050649C2 | Ratio | 2003 / 2012 | Reconstruction |  | 66.5% |  |  | 95.9% | 144.2% |  | 0 | 0 | 0 | 0
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 |  | P050719C1 | Ratio | 2000 / 2006 | Strengthening |  | 107.1% |  |  | 94.9% | 88.57% |  | 0 | 0 | 0 | 0
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S1 | P050719C1S1 | Ratio | 2000 / 2006 | Strengthening |  | 111.1% |  |  | 92.73% | 83.45% |  | 0 | 0 | 0 | 0
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S2 | P050719C1S2 | Ratio | 2000 / 2006 | Strengthening |  | 100% |  |  | 101.5% | 101.5% |  | 0 | 0 | 0 | 0
Kyrgyz Republic | Europe and Central Asia | P050719 | C1 | S3 | P050719C1S3 | Ratio | 2000 / 2006 | Strengthening |  | 91.67% |  |  | 99.47% | 108.5% |  | 0 | 0 | 0 | 0
Madagascar | Sub-Saharan Africa | P052208 | C1 | S1 | P052208C1S1 | Ratio | 2000 / 2006 | Surface Treatment Resurfacing |  | 100% |  |  | 222.3% | 222.3% | x | 0 | 0 | 1 | 0 | 1 | 1 | 1 | [7 empty] | Political events ; Weather shocks ; Macroeconomic conditions
Senegal | Sub-Saharan Africa | P055472 | C1 |  | P055472C1 | Ratio | 2000 / 2009 | Reconstruction |  | 69.23% |  |  | 233.7% | 337.6% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Quality of estimates; Capacity of counterpart;
Uruguay | Latin America and Caribbean | P057481 |  |  | P057481 | Ratio | 2005 / 2012 | Routine Maintenance | 100% | 100% |  |  | 134.6% | 134.6% |  | 0 | 0 | 0 | 0
Uruguay | Latin America and Caribbean | P057481 | C1 | S1 | P057481C1S1 | Ratio | 2007 / 2012 | Reconstruction |  | 100% |  |  | 158.4% | 158.4% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 |  | Quality of estimates; ;
Uruguay | Latin America and Caribbean | P057481 | C1 | S2 | P057481C1S2 | Ratio | 2007 / 2012 | Reconstruction |  | 100% |  |  | 145.8% | 145.8% |  | 0 | 0 | 0 | 0
Uruguay | Latin America and Caribbean | P057481 | C1 | S3 | P057481C1S3 | Ratio | 2007 / 2012 | Reconstruction |  | 100% |  |  | 354.5% | 354.5% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 | 1 | Change of project scope; Quality of estimates;
Honduras | Latin America and Caribbean | P057538 | C1 | S1 | P057538C1S1 | Ratio | 2000 / 2007 | Strengthening |  | 59.52% |  |  | 106.2% | 178.5% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Honduras | Latin America and Caribbean | P057538 | C1 | S2 | P057538C1S2 | Ratio | 2000 / 2007 | Strengthening |  | 100% |  |  | 160.3% | 160.3% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Honduras | Latin America and Caribbean | P057538 | C1 | S3 | P057538C1S3 | Ratio | 2000 / 2007 | Upgrading |  | 100.2% |  |  | 102.8% | 102.6% |  | 0 | 0 | 0 | 0
Honduras | Latin America and Caribbean | P057538 | C1 | S4 | P057538C1S4 | Ratio | 2000 / 2007 | Upgrading |  | 100% |  |  | 107.4% | 107.4% |  | 0 | 0 | 0 | 0
Honduras | Latin America and Caribbean | P057538 | C2 |  | P057538C2 | Ratio | 2000 / 2007 | Reconstruction |  | 102% |  |  | 57.65% | 56.52% |  | 0 | 0 | 0 | 0
Honduras | Latin America and Caribbean | P057538 | C3 |  | P057538C3 | Ratio | 2000 / 2007 | Routine Maintenance |  | 185.6% |  |  | 195% | 105.1% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
Philippines | East Asia and Pacific | P057731 | C1 | S1 | P057731C1S1 | Ratio | 2001 / 2011 | Reconstruction |  | 100% |  |  | 95.73% | 95.73% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P057731 | C1 | S2 | P057731C1S2 | Ratio | 2001 / 2011 | Reconstruction |  | 100% |  |  | 75.17% | 75.17% |  | 0 | 0 | 0 | 0
Philippines | East Asia and Pacific | P057731 | C1 | S3 | P057731C1S3 | Ratio | 2001 / 2011 | Reconstruction |  | 100% |  |  | 289.3% | 289.3% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  |  |  |  | 1 |  | Procurement system; Quality of estimates;
Philippines | East Asia and Pacific | P057731 | C1 | S4 | P057731C1S4 | Ratio | 2001 / 2011 | Reconstruction |  | 100% |  |  | 371.2% | 371.2% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  |  |  |  | 1 |  | Procurement system; Quality of estimates;
China | East Asia and Pacific | P058844 | C1 |  | P058844C1 | Ratio | 2000 / 2007 | New 4L Expressway | 148% | 100% |  |  | 90.74% | 90.74% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P058844 | C2 |  | P058844C2 | Ratio | 2000 / 2007 | Upgrading |  | 93.25% |  |  | 88.61% | 95.02% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P058847 | C1 |  | P058847C1 | Ratio | 2002 / 2010 | Widening and Reconstruction |  | 100% |  |  | 131.8% | 131.8% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P058847 | C2 |  | P058847C2 | Ratio | 2002 / 2010 | Upgrading |  | 103.3% |  |  | 124% | 120% |  | 0 | 0 | 0 | 0
Vietnam | East Asia and Pacific | P059663 | C1 | S1 | P059663C1S1 | Ratio | 2003 / 2012 | Asphalt Mix Resurfacing | 130% | 76.55% |  |  | 93.09% | 121.6% |  | 0 | 0 | 0 | 0
Vietnam | East Asia and Pacific | P059663 | C1 | S2 | P059663C1S2 | Ratio | 2003 / 2012 | Asphalt Mix Resurfacing | 225% | 70.23% |  |  | 336.4% | 479% | x | 0 | 0 | 1 | 0 | 1 |  |  | 1 | [6 empty] | Macroeconomic conditions; Procurement system;
Vietnam | East Asia and Pacific | P059663 | C2 |  | P059663C2 | Ratio | 2003 / 2012 | Widening and Reconstruction | 160% | 44.17% |  |  | 146.8% | 332.4% | x | 0 | 1 | 1 | 0 | 1 |  |  | 1 |  |  |  |  | 1 |  | Macroeconomic conditions; Quality of estimates; Procurement system
Vietnam | East Asia and Pacific | P059864 | C1 |  | P059864C1 | Ratio | 1999 / 2007 | Gravel Resurfacing | 100% | 75.99% |  |  | 107.9% | 142% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S1 | P064821C1S1 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 197.3% |  |  | 109.5% | 55.48% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
Lao PDR | East Asia and Pacific | P064821 | C1 | S10 | P064821C1S10 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% |  |  | 82.05% | 82.05% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S11 | P064821C1S11 | Ratio | 2001 / 2005 | Gravel Resurfacing |  | 100% |  |  | 83.64% | 83.64% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S2 | P064821C1S2 | Ratio | 2001 / 2005 | Routine Maintenance |  | 164.1% |  |  | 42.65% | 25.99% | x | 1 | 0 | 0 | 1 |  |  |  | 1 |  | 1 |  |  | 1 | 1 | Capacity of counterpart (Procurement system); Quality of estimates; Change of project scope
Lao PDR | East Asia and Pacific | P064821 | C1 | S3 | P064821C1S3 | Ratio | 2001 / 2005 | Gravel Resurfacing |  | 100% |  |  | 82.93% | 82.93% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S4 | P064821C1S4 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% |  |  | 92.86% | 92.86% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S5 | P064821C1S5 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% |  |  | 82.56% | 82.56% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S6 | P064821C1S6 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% |  |  | 82.65% | 82.65% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S7 | P064821C1S7 | Ratio | 2001 / 2005 | Gravel Resurfacing |  | 100% |  |  | 84.09% | 84.09% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S8 | P064821C1S8 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% |  |  | 82.76% | 82.76% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P064821 | C1 | S9 | P064821C1S9 | Ratio | 2001 / 2005 | Bituminous Pavement Preventive Treatment |  | 100% |  |  | 79.49% | 79.49% |  | 0 | 0 | 0 | 0
Guinea | Sub-Saharan Africa | P065127 | C1 |  | P065127C1 | Ratio | 2004 / 2013 | Upgrading |  | 62.99% |  |  | 79.5% | 126.2% |  | 0 | 0 | 0 | 0
Uganda | Sub-Saharan Africa | P065436 | C1 |  | P065436C1 | Ratio | 2001 / 2009 | Strengthening |  | 100% |  |  | 116.8% | 116.8% |  | 0 | 0 | 0 | 0
Uganda | Sub-Saharan Africa | P065436 | C1 | S1 | P065436C1S1 | Ratio | 2001 / 2009 | Upgrading | 111.1% | 100% |  |  | 123.5% | 123.5% |  | 0 | 0 | 0 | 0
Uganda | Sub-Saharan Africa | P065436 | C1 | S2 | P065436C1S2 | Ratio | 2001 / 2009 | Upgrading | 88.89% | 100% |  |  | 110.5% | 110.5% |  | 0 | 0 | 0 | 0
Uganda | Sub-Saharan Africa | P065436 | C1 | S3 | P065436C1S3 | Ratio | 2001 / 2009 | Strengthening | 200% | 100% |  |  | 120.5% | 120.5% |  | 0 | 0 | 0 | 0
Uganda | Sub-Saharan Africa | P065436 | C1 | S4 | P065436C1S4 | Ratio | 2001 / 2009 | Strengthening | 137.5% | 100% |  |  | 128.2% | 128.2% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S1 | P065779C1S1 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 95.06% | 95.06% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S10 | P065779C1S10 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 142.6% | 142.6% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S11 | P065779C1S11 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 137% | 137% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S12 | P065779C1S12 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 85.11% | 85.11% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S13 | P065779C1S13 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 180% | 180% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S14 | P065779C1S14 | Ratio | 2000 / 2007 | Reconstruction |  | 85% |  |  | 255% | 300% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S15 | P065779C1S15 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 77.02% | 77.02% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S16 | P065779C1S16 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 91.3% | 91.3% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S17 | P065779C1S17 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 18.86% | 18.86% | x | 0 | 0 | 0 | 1 | [9 empty] | 1 | Change of project scope; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S18 | P065779C1S18 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 125% | 125% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S19 | P065779C1S19 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 153% | 153% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S2 | P065779C1S2 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 64.52% | 64.52% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S20 | P065779C1S20 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 130.7% | 130.7% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S21 | P065779C1S21 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 46.73% |  |  | 19.48% | 41.69% | x | 0 | 1 | 0 | 1 | [9 empty] | 1 | Change of project scope; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S22 | P065779C1S22 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100.8% |  |  | 64.81% | 64.28% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S23 | P065779C1S23 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 91.67% | 91.67% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S24 | P065779C1S24 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 71.43% | 71.43% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S25 | P065779C1S25 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 96.2% |  |  | 171.4% | 178.2% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S26 | P065779C1S26 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 127% | 127% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S27 | P065779C1S27 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 125.5% | 125.5% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S28 | P065779C1S28 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 238.8% | 238.8% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S29 | P065779C1S29 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 200% | 200% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S3 | P065779C1S3 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 50% | 50% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S30 | P065779C1S30 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 194.1% | 194.1% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S31 | P065779C1S31 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 116.7% | 116.7% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S32 | P065779C1S32 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 44.44% | 44.44% | x | 0 | 0 | 0 | 1 | [9 empty] | 1 | Change of project scope; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S33 | P065779C1S33 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 193% | 193% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  | 1 |  |  |  | 1 | Change of project scope; Capacity of counterpart (Procurement system);
Mexico | Latin America and Caribbean | P065779 | C1 | S34 | P065779C1S34 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 160% |  |  | 323.1% | 201.9% | x | 1 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 | 1 | Capacity of counterpart ; Quality of estimates; Change of project scope
Mexico | Latin America and Caribbean | P065779 | C1 | S35 | P065779C1S35 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 300% | 300% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S36 | P065779C1S36 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 109.4% |  |  | 350% | 320% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S37 | P065779C1S37 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 150.4% | 150.4% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S38 | P065779C1S38 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 99.03% |  |  | 88.12% | 88.99% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S39 | P065779C1S39 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 750% | 750% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S4 | P065779C1S4 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 84.16% | 84.16% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S40 | P065779C1S40 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 400% |  |  | 660% | 165% | x | 1 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 | 1 | Capacity of counterpart ; Quality of estimates; Change of project scope
Mexico | Latin America and Caribbean | P065779 | C1 | S41 | P065779C1S41 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 224.8% | 224.8% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S42 | P065779C1S42 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 204.3% | 204.3% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S43 | P065779C1S43 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 111.1% | 111.1% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S44 | P065779C1S44 | Ratio | 2000 / 2007 | Reconstruction |  | 95.83% |  |  | 692.3% | 722.4% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S45 | P065779C1S45 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 89.74% | 89.74% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S46 | P065779C1S46 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 160.7% | 160.7% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S47 | P065779C1S47 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 76.67% |  |  | 116.5% | 151.9% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S48 | P065779C1S48 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 300% | 300% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
Mexico | Latin America and Caribbean | P065779 | C1 | S49 | P065779C1S49 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 105.6% |  |  | 118.7% | 112.4% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S5 | P065779C1S5 | Ratio | 2000 / 2007 | Reconstruction |  | 68.75% |  |  | 57.78% | 84.04% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S50 | P065779C1S50 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 146.2% | 146.2% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S51 | P065779C1S51 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 70% |  |  | 53.62% | 76.6% |  | 0 | 0 | 0 | 0
Mexico | Latin America and Caribbean | P065779 | C1 | S6 | P065779C1S6 | Ratio | 2000 / 2007 | Reconstruction |  | 200% |  |  | 275% | 137.5% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S7 | P065779C1S7 | Ratio | 2000 / 2007 | Asphalt Mix Resurfacing |  | 100% |  |  | 14.67% | 14.67% | x | 0 | 0 | 0 | 1 | [9 empty] | 1 | Change of project scope; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S8 | P065779C1S8 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 45.49% | 45.49% | x | 0 | 0 | 0 | 1 | [9 empty] | 1 | Change of project scope; ;
Mexico | Latin America and Caribbean | P065779 | C1 | S9 | P065779C1S9 | Ratio | 2000 / 2007 | Reconstruction |  | 100% |  |  | 260.7% | 260.7% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of counterpart ; Quality of estimates;
China | East Asia and Pacific | P068752 | C1 |  | P068752C1 | Ratio | 2005 / 2011 | Widening and Reconstruction | 83.33% | 101% |  |  | 124.2% | 123% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P068752 | C2 |  | P068752C2 | Ratio | 2005 / 2011 | Upgrading |  | 160.1% |  |  | 228.1% | 142.5% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
China | East Asia and Pacific | P068752 | C2 | S1 | P068752C2S1 | Ratio | 2005 / 2011 | Upgrading | 100% | 105.2% |  |  | 138.6% | 131.7% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P068752 | C2 | S2 | P068752C2S2 | Ratio | 2005 / 2011 | Upgrading | 100% | 98.48% |  |  | 108.5% | 110.2% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P068752 | C2 | S3 | P068752C2S3 | Ratio | 2005 / 2011 | Upgrading | 166.7% | 114.6% |  |  | 297.6% | 259.7% | x | 0 | 0 | 1 | 0 |  |  | 1 | [5 empty] | 1 |  | Weather shocks ; Quality of estimates;
China | East Asia and Pacific | P068752 | C2 | S4 | P068752C2S4 | Ratio | 2005 / 2011 | Upgrading | 100% | 99.03% |  |  | 181.1% | 182.9% | x | 0 | 0 | 1 | 0 |  |  | 1 | [5 empty] | 1 |  | Weather shocks ; Quality of estimates;
China | East Asia and Pacific | P068752 | C2 | S5 | P068752C2S5 | Ratio | 2005 / 2011 | Upgrading | 100% | 111.4% |  |  | 117.5% | 105.5% |  | 0 | 0 | 0 | 0
Bolivia | Latin America and Caribbean | P068968 | C1 |  | P068968C1 | Ratio | 2002 / 2011 | Reconstruction |  | 100% |  |  | 116.8% | 116.8% |  | 0 | 0 | 0 | 0
Bolivia | Latin America and Caribbean | P068968 | C2 |  | P068968C2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 44.33% |  |  | 56.48% | 127.4% | x | 0 | 1 | 0 | 0 | 1 |  | 1 | [6 empty] | 1 | Macroeconomic conditions; Weather shocks ; Change of project scope
China | East Asia and Pacific | P069852 | C2 |  | P069852C2 | Ratio | 2004 / 2010 | Reconstruction |  | 95.29% |  |  | 142.8% | 149.9% |  | 0 | 0 | 0 | 0
Djibouti | Middle East and North Africa | P069930 | C1 |  | P069930C1 | Ratio | 2000 / 2006 | Reconstruction | 150% | 96.08% |  |  | 114.2% | 118.8% |  | 0 | 0 | 0 | 0
Djibouti | Middle East and North Africa | P069930 | C2 |  | P069930C2 | Ratio | 2000 / 2006 | Asphalt Mix Resurfacing | 100% | 102.3% |  |  | 147.5% | 144.1% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 |  | P070421C1 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 87.4% |  |  | 131.5% | 150.5% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; Capacity of contractor;
India | South Asia | P070421 | C1 | S1 | P070421C1S1 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 142.3% | 142.3% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 | S10 | P070421C1S10 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 197.9% | 197.9% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; Capacity of contractor;
India | South Asia | P070421 | C1 | S11 | P070421C1S11 | Ratio | 2001 / 2008 | New 2L Highway |  | 100% |  |  | 17.23% | 17.23% | x | 0 | 0 | 0 | 1 | [8 empty] | 1 |  | Quality of estimates; ;
India | South Asia | P070421 | C1 | S2 | P070421C1S2 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 114.9% | 114.9% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 | S3 | P070421C1S3 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 109% | 109% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 | S4 | P070421C1S4 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 80.65% | 80.65% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 | S5 | P070421C1S5 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 116% | 116% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 | S6 | P070421C1S6 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 93.72% | 93.72% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 | S7 | P070421C1S7 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 57.2% | 57.2% |  | 0 | 0 | 0 | 0
India | South Asia | P070421 | C1 | S8 | P070421C1S8 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 38.76% | 38.76% | x | 0 | 0 | 0 | 1 | [8 empty] | 1 |  | Quality of estimates; ;
India | South Asia | P070421 | C1 | S9 | P070421C1S9 | Ratio | 2001 / 2008 | Widening and Reconstruction |  | 100% |  |  | 988.3% | 988.3% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Capacity of contractor; Macroeconomic conditions;
India | South Asia | P070421 | C2 |  | P070421C2 | Ratio | 2001 / 2008 | Asphalt Mix Resurfacing |  | 96.15% |  |  | 174.1% | 181.1% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Capacity of contractor; Macroeconomic conditions;
China | East Asia and Pacific | P070441 | C1 |  | P070441C1 | Ratio | 2002 / 2008 | New 4L Expressway | 100% | 100% |  |  | 158.7% | 158.7% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Quality of estimates; Macroeconomic conditions; Capacity of contractor
China | East Asia and Pacific | P070441 | C2 |  | P070441C2 | Ratio | 2002 / 2008 | Upgrading |  | 100% |  |  | 63.44% | 63.44% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P070459 | C1 |  | P070459C1 | Ratio | 2002 / 2008 | New 4L Expressway |  | 100% |  |  | 90.99% | 90.99% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P070459 | C2 |  | P070459C2 | Ratio | 2002 / 2008 | Upgrading |  | 193.6% |  |  | 133.6% | 69.03% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
China | East Asia and Pacific | P070459 | C2 | S1 | P070459C2S1 | Ratio | 2002 / 2008 | Upgrading |  | 100% |  |  | 95.73% | 95.73% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P070459 | C2 | S2 | P070459C2S2 | Ratio | 2002 / 2008 | Upgrading |  | 100% |  |  | 79.83% | 79.83% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P070459 | C2 | S3 | P070459C2S3 | Ratio | 2002 / 2008 | Upgrading |  | 100% |  |  | 51.32% | 51.32% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P070459 | C2 | S4 | P070459C2S4 | Ratio | 2002 / 2008 | Upgrading |  | 100% |  |  | 98.52% | 98.52% |  | 0 | 0 | 0 | 0
Cambodia | East Asia and Pacific | P071207 | C1 | S1 | P071207C1S1 | Ratio | 2003 / 2012 | Upgrading |  | 90.83% |  |  | 90.45% | 99.59% |  | 0 | 0 | 0 | 0
Cambodia | East Asia and Pacific | P071207 | C1 | S10 | P071207C1S10 | Ratio | 2003 / 2012 | Upgrading |  | 74.07% |  |  | 107.7% | 145.4% |  | 0 | 0 | 0 | 0
Cambodia | East Asia and Pacific | P071207 | C1 | S2 | P071207C1S2 | Ratio | 2003 / 2012 | Upgrading |  | 101.7% |  |  | 140.2% | 137.9% |  | 0 | 0 | 0 | 0
Cambodia | East Asia and Pacific | P071207 | C1 | S3 | P071207C1S3 | Ratio | 2003 / 2012 | Upgrading |  | 151.7% |  |  | 161% | 106.2% | x | 1 | 0 | 0 | 0 | [5 empty] | 1 |  |  |  | 1 | Change of project scope; Capacity of counterpart;
Cambodia | East Asia and Pacific | P071207 | C1 | S4 | P071207C1S4 | Ratio | 2003 / 2012 | Upgrading |  | 83.52% |  |  | 81.54% | 97.63% |  | 0 | 0 | 0 | 0
Cambodia | East Asia and Pacific | P071207 | C1 | S5 | P071207C1S5 | Ratio | 2003 / 2012 | Upgrading |  | 101.3% |  |  | 106.5% | 105.1% |  | 0 | 0 | 0 | 0
Cambodia | East Asia and Pacific | P071207 | C1 | S6 | P071207C1S6 | Ratio | 2003 / 2012 | Upgrading |  | 100.5% |  |  | 136.7% | 136% |  | 0 | 0 | 0 | 0
Cambodia | East Asia and Pacific | P071207 | C1 | S7 | P071207C1S7 | Ratio | 2003 / 2012 | Upgrading |  | 162.9% |  |  | 189.7% | 116.4% | x | 1 | 0 | 0 | 0 | [5 empty] | 1 |  |  |  | 1 | Change of project scope; Capacity of counterpart;
Cambodia | East Asia and Pacific | P071207 | C1 | S8 | P071207C1S8 | Ratio | 2003 / 2012 | Upgrading |  | 99.21% |  |  | 169% | 170.4% | x | 0 | 0 | 1 | 0 |  |  |  | 1 | [5 empty] | 1 | Change of project scope; Procurement system;
Cambodia | East Asia and Pacific | P071207 | C1 | S9 | P071207C1S9 | Ratio | 2003 / 2012 | Reconstruction |  | 101.8% |  |  | 175% | 171.9% | x | 0 | 0 | 1 | 0 |  |  |  | 1 | [5 empty] | 1 | Change of project scope; Procurement system;
Zambia | Sub-Saharan Africa | P071985 | C1 | S1 | P071985C1S1 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing | 89.19% | 100% |  |  | 85.04% | 85.04% |  | 0 | 0 | 0 | 0
Zambia | Sub-Saharan Africa | P071985 | C1 | S2 | P071985C1S2 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 80.22% | 80.22% |  | 0 | 0 | 0 | 0
Zambia | Sub-Saharan Africa | P071985 | C1 | S3 | P071985C1S3 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing | 117.4% | 100% |  |  | 45.89% | 45.89% | x | 0 | 0 | 0 | 1 | [8 empty] | 1 |  | Quality of estimates; ;
Zambia | Sub-Saharan Africa | P071985 | C1 | S4 | P071985C1S4 | Ratio | 2004 / 2015 | Asphalt Mix Resurfacing |  | 100% |  |  | 62.21% | 62.21% |  | 0 | 0 | 0 | 0
India | South Asia | P072539 | C1 |  | P072539C1 | Ratio | 2002 / 2011 | Widening and Reconstruction |  | 43.87% |  |  | 71.92% | 164% | x | 0 | 1 | 1 | 0 |  |  |  | 1 |  | 1 |  |  | 1 | 1 | Capacity of counterpart (Procurement system); Change of project scope; Quality of estimates
India | South Asia | P072539 | C2 |  | P072539C2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 114.6% |  |  | 239.3% | 208.8% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  | 1 |  |  | 1 |  | Capacity of counterpart (Procurement system); Quality of estimates;
Burkina Faso | Sub-Saharan Africa | P074030 | C1 |  | P074030C1 | Ratio | 2003 / 2014 | Reconstruction |  | 37.95% |  |  | 100.6% | 265.2% | x | 0 | 1 | 1 | 0 | 1 |  | 1 | [6 empty] | 1 | Macroeconomic conditions; Weather shocks ; Change of project scope
Indonesia | East Asia and Pacific | P074290 | C1 |  | P074290C1 | Ratio | 2004 / 2012 | Reconstruction | 100% | 49.47% |  |  | 116.2% | 234.9% | x | 0 | 1 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  | 1 | Macroeconomic conditions; Capacity of counterpart; Change of project scope
Indonesia | East Asia and Pacific | P074290 | C1 | S1 | P074290C1S1 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 38.03% |  |  | 75.98% | 199.8% | x | 0 | 1 | 1 | 0 | [5 empty] | 1 |  |  |  | 1 | Capacity of counterpart; Change of project scope;
Indonesia | East Asia and Pacific | P074290 | C1 | S2 | P074290C1S2 | Ratio | 2004 / 2012 | Reconstruction |  | 434.8% |  |  | 853.3% | 196.2% | x | 1 | 0 | 1 | 0 | 1 | [8 empty] | 1 | Macroeconomic conditions; Change of project scope; Change of project scope
Indonesia | East Asia and Pacific | P074290 | C1 | S3 | P074290C1S3 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 88.7% |  |  | 125.5% | 141.5% |  | 0 | 0 | 0 | 0
Indonesia | East Asia and Pacific | P074290 | C1 | S4 | P074290C1S4 | Ratio | 2004 / 2012 | Reconstruction |  | 38.24% |  |  | 86.57% | 226.4% | x | 0 | 1 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  | 1 | Macroeconomic conditions; Capacity of counterpart; Change of project scope
Indonesia | East Asia and Pacific | P074290 | C1 | S5 | P074290C1S5 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 32.37% |  |  | 47.02% | 145.3% | x | 0 | 1 | 0 | 0 | 1 |  |  |  |  | 1 |  |  |  | 1 | Macroeconomic conditions; Capacity of counterpart; Change of project scope
Indonesia | East Asia and Pacific | P074290 | C1 | S6 | P074290C1S6 | Ratio | 2004 / 2012 | Reconstruction |  | 40.9% |  |  | 76.98% | 188.2% | x | 0 | 1 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  | 1 | Macroeconomic conditions; Capacity of counterpart; Change of project scope
Indonesia | East Asia and Pacific | P074290 | C1 | S7 | P074290C1S7 | Ratio | 2004 / 2012 | Asphalt Mix Resurfacing |  | 26.06% |  |  | 56.57% | 217.1% | x | 0 | 1 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  | 1 | Macroeconomic conditions; Capacity of counterpart; Change of project scope
Indonesia | East Asia and Pacific | P074290 | C1 | S8 | P074290C1S8 | Ratio | 2004 / 2012 | Reconstruction |  | 49.09% |  |  | 94.05% | 191.6% | x | 0 | 1 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  | 1 | Macroeconomic conditions; Capacity of counterpart; Change of project scope
Nigeria | Sub-Saharan Africa | P074963 | C1 |  | P074963C1 | Ratio | 2002 / 2011 | Strengthening |  | 104.7% |  |  | 161.2% | 154% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; ;
Nigeria | Sub-Saharan Africa | P074963 | C1 | S1 | P074963C1S1 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 100% |  |  | 103.2% | 103.2% |  | 0 | 0 | 0 | 0
Nigeria | Sub-Saharan Africa | P074963 | C1 | S2 | P074963C1S2 | Ratio | 2002 / 2011 | Asphalt Mix Resurfacing |  | 133.1% |  |  | 128.4% | 96.48% |  | 0 | 0 | 0 | 0
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S1 | P075207C1S1 | Ratio | 2004 / 2013 | Reconstruction |  | 100% |  |  | 189.5% | 189.5% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Quality of estimates; Capacity of counterpart;
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S2 | P075207C1S2 | Ratio | 2004 / 2013 | Reconstruction |  | 100% |  |  | 180.5% | 180.5% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  | 1 |  | Quality of estimates; Capacity of counterpart;
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S3 | P075207C1S3 | Ratio | 2004 / 2013 | Reconstruction |  | 100% |  |  | 143.1% | 143.1% |  | 0 | 0 | 0 | 0
Yugoslavia, FR (Serbia/Montenegro) | Europe and Central Asia | P075207 | C1 | S4 | P075207C1S4 | Ratio | 2004 / 2013 | Reconstruction |  | 100% |  |  | 75% | 75% |  | 0 | 0 | 0 | 0
Samoa | East Asia and Pacific | P075523 | C1 | S1 | P075523C1S1 | Ratio | 2003 / 2014 | Surface Treatment Resurfacing | 126.7% | 93.75% |  |  | 363.6% | 387.8% | x | 0 | 0 | 1 | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  | Capacity of counterpart; Weather shocks; Quality of estimates
Samoa | East Asia and Pacific | P075523 | C1 | S2 | P075523C1S2 | Ratio | 2003 / 2014 | Widening | 100% | 100% |  |  | 440.7% | 440.7% | x | 0 | 0 | 1 | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  | Capacity of counterpart; Weather shocks; Quality of estimates
Samoa | East Asia and Pacific | P075523 | C1 | S3 | P075523C1S3 | Ratio | 2003 / 2014 | Upgrading | 33.33% | 100.8% |  |  | 386.7% | 383.7% | x | 0 | 0 | 1 | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  | Capacity of counterpart; Weather shocks; Quality of estimates
China | East Asia and Pacific | P075613 | C1 |  | P075613C1 | Ratio | 2007 / 2013 | New 4L Expressway |  | 100% |  |  | 195.4% | 195.4% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; ;
China | East Asia and Pacific | P075613 | C2 |  | P075613C2 | Ratio | 2007 / 2013 | Upgrading |  | 100% |  |  | 164.3% | 164.3% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; ;
India | South Asia | P077977 | C1 | S1 | P077977C1S1 | Ratio | 2004 / 2012 | Upgrading | 200% | 146.4% |  |  | 156.2% | 106.7% |  | 0 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
India | South Asia | P077977 | C1 | S2 | P077977C1S2 | Ratio | 2004 / 2012 | Upgrading | 150% | 96.92% |  |  | 85.71% | 88.43% |  | 0 | 0 | 0 | 0
India | South Asia | P077977 | C1 | S3 | P077977C1S3 | Ratio | 2004 / 2012 | Upgrading | 150% | 275.5% |  |  | 238.3% | 86.49% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
India | South Asia | P077977 | C1 | S4 | P077977C1S4 | Ratio | 2004 / 2012 | Upgrading | 150% | 152% |  |  | 166.4% | 109.5% | x | 1 | 0 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
Poland | Europe and Central Asia | P078170 | C2 |  | P078170C2 | Ratio | 2004 / 2009 | Concrete Pavement Restoration |  | 100% |  |  | 84.05% | 84.05% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P078284 | C1 |  | P078284C1 | Ratio | 2003 / 2008 | Strengthening |  | 99.48% |  |  | 140.9% | 141.7% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P078284 | C1 | S1 | P078284C1S1 | Ratio | 2003 / 2008 | Strengthening | 500% | 100% |  |  | 150% | 150% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P078284 | C1 | S2 | P078284C1S2 | Ratio | 2003 / 2008 | Strengthening | 157.1% | 98.95% |  |  | 124.7% | 126% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P078284 | C2 |  | P078284C2 | Ratio | 2003 / 2008 | Upgrading |  | 24.4% |  |  | 73.19% | 299.9% | x | 0 | 1 | 1 | 0 |  | 1 | [5 empty] | 1 |  | 1 | Political events; Competition; Change of project scope
Tanzania | Sub-Saharan Africa | P078387 | C1 | S1 | P078387C1S1 | Ratio | 2004 / 2010 | Upgrading |  | 104.9% |  |  | 98.71% | 94.09% |  | 0 | 0 | 0 | 0
Tanzania | Sub-Saharan Africa | P078387 | C1 | S2 | P078387C1S2 | Ratio | 2004 / 2010 | Upgrading | 200% | 98.25% |  |  | 113.8% | 115.9% |  | 0 | 0 | 0 | 0
Peru | Latin America and Caribbean | P078813 | C1 |  | P078813C1 | Ratio | 2005 / 2014 | Reconstruction |  | 104.1% |  |  | 101.9% | 97.85% |  | 0 | 0 | 0 | 0
Peru | Latin America and Caribbean | P078813 | C1 | S1 | P078813C1S1 | Ratio | 2005 / 2014 | Reconstruction |  | 71% |  |  | 93.05% | 131.1% |  | 0 | 0 | 0 | 0
Peru | Latin America and Caribbean | P078813 | C1 | S2 | P078813C1S2 | Ratio | 2005 / 2014 | Gravel Resurfacing |  | 131.1% |  |  | 149.3% | 113.8% |  | 0 | 0 | 0 | 0
Mali | Sub-Saharan Africa | P079351 | C1 |  | P079351C1 | Ratio | 2004 / 2010 | Asphalt Mix Resurfacing | 120% | 42.38% |  |  | 98.83% | 233.2% | x | 0 | 1 | 1 | 0 |  |  |  | 1 |  | 1 |  |  |  |  | Capacity of counterpart; Procurement system;
Indonesia | East Asia and Pacific | P079906 | C1 |  | P079906C1 | Ratio | 2006 / 2014 | Reconstruction |  | 56.89% |  |  | 79.66% | 140% |  | 0 | 0 | 0 | 0
Indonesia | East Asia and Pacific | P079906 | C1 | S1 | P079906C1S1 | Ratio | 2006 / 2014 | Strengthening |  | 75.04% |  |  | 84.15% | 112.2% |  | 0 | 0 | 0 | 0
Indonesia | East Asia and Pacific | P079906 | C1 | S2 | P079906C1S2 | Ratio | 2006 / 2014 | Widening |  | 82.73% |  |  | 94.98% | 114.8% |  | 0 | 0 | 0 | 0
Indonesia | East Asia and Pacific | P079906 | C1 | S3 | P079906C1S3 | Ratio | 2006 / 2014 | New 2L Highway |  | 79.27% |  |  | 81.56% | 102.9% |  | 0 | 0 | 0 | 0
Jordan | Middle East and North Africa | P081505 | C1 | S1 | P081505C1S1 | Ratio | 2004 / 2013 | New 4L Expressway |  | 100% |  |  | 266.3% | 266.3% | x | 0 | 0 | 1 | 0 |  | 1 | [5 empty] | 1 | 1 |  | Political events; Competition; Quality of estimates
Jordan | Middle East and North Africa | P081505 | C1 | S2 | P081505C1S2 | Ratio | 2004 / 2013 | New 4L Expressway |  | 100% |  |  | 225.4% | 225.4% | x | 0 | 0 | 1 | 0 |  | 1 | [6 empty] | 1 |  | Political events; Quality of estimates;
Jordan | Middle East and North Africa | P081505 | C1 | S3 | P081505C1S3 | Ratio | 2004 / 2013 | New 4L Expressway |  | 100% |  |  | 297.7% | 297.7% | x | 0 | 0 | 1 | 0 |  | 1 | [6 empty] | 1 |  | Political events; Quality of estimates;
Paraguay | Latin America and Caribbean | P082026 | C1 |  | P082026C1 | Ratio | 2006 / 2016 | Strengthening |  | 64.36% |  |  | 169.1% | 262.7% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 |  | Quality of estimates; ;
Paraguay | Latin America and Caribbean | P082026 | C1 | S1 | P082026C1S1 | Ratio | 2006 / 2016 | Strengthening | 100% | 100% |  |  | 118.9% | 118.9% |  | 0 | 0 | 0 | 0
Paraguay | Latin America and Caribbean | P082026 | C1 | S2 | P082026C1S2 | Ratio | 2006 / 2016 | Strengthening | 100% | 100% |  |  | 174.5% | 174.5% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 |  | Quality of estimates; ;
Paraguay | Latin America and Caribbean | P082026 | C1 | S3 | P082026C1S3 | Ratio | 2006 / 2016 | Strengthening | 172.8% | 100% |  |  | 394.6% | 394.6% | x | 0 | 0 | 1 | 0 | [8 empty] | 1 |  | Quality of estimates; ;
Paraguay | Latin America and Caribbean | P082026 | C2 |  | P082026C2 | Ratio | 2006 / 2016 | Reconstruction |  | 42.32% |  |  | 61.4% | 145.1% | x | 0 | 1 | 0 | 0 | [9 empty] | 1 | Change of project scope; ;
Paraguay | Latin America and Caribbean | P082026 | C2 | S1 | P082026C2S1 | Ratio | 2006 / 2016 | Reconstruction | 125% | 29.36% |  |  | 140.2% | 477.6% | x | 0 | 1 | 1 | 0 | [8 empty] | 1 | 1 | Change of project scope; Quality of estimates;
Paraguay | Latin America and Caribbean | P082026 | C2 | S2 | P082026C2S2 | Ratio | 2006 / 2016 | Reconstruction | 106.7% | 31.31% |  |  | 147.4% | 470.8% | x | 0 | 1 | 1 | 0 | [8 empty] | 1 | 1 | Quality of estimates; Change of project scope;
Paraguay | Latin America and Caribbean | P082026 | C2 | S3 | P082026C2S3 | Ratio | 2006 / 2016 | Reconstruction | 189.7% | 14.29% |  |  | 93.14% | 652% | x | 0 | 1 | 1 | 0 | [8 empty] | 1 | 1 | Change of project scope; Quality of estimates;
Afghanistan | South Asia | P082472 | C1 |  | P082472C1 | Ratio | 2008 / 2008 | Reconstruction |  | 75.83% |  |  | 110% | 145% |  | 0 | 0 | 0 | 0
Kenya | Sub-Saharan Africa | P082615 | C1 | S1 | P082615C1S1 | Ratio | 2004 / 2016 | Widening and Reconstruction |  | 100% |  |  | 331% | 331% | x | 0 | 0 | 1 | 0 | 1 | 1 | 1 | [7 empty] | Political events; Macroeconomic conditions; Weather shocks
Kenya | Sub-Saharan Africa | P082615 | C1 | S2 | P082615C1S2 | Ratio | 2004 / 2016 | Reconstruction |  | 60% |  |  | 233.7% | 389.5% | x | 0 | 0 | 1 | 0 | 1 | 1 | 1 | [7 empty] | Political events; Macroeconomic conditions; Weather shocks
Kenya | Sub-Saharan Africa | P082615 | C1 | S3 | P082615C1S3 | Ratio | 2004 / 2016 | Widening |  | 100% |  |  | 300.3% | 300.3% | x | 0 | 0 | 1 | 0 | 1 | 1 | 1 | [7 empty] | Political events; Macroeconomic conditions; Weather shocks
Kenya | Sub-Saharan Africa | P082615 | C1 | S4 | P082615C1S4 | Ratio | 2004 / 2016 | Reconstruction |  | 103.1% |  |  | 339.3% | 329.2% | x | 0 | 0 | 1 | 0 | 1 | 1 | 1 | [7 empty] | Political events; Macroeconomic conditions; Weather shocks
Kenya | Sub-Saharan Africa | P082615 | C1 | S5 | P082615C1S5 | Ratio | 2004 / 2016 | Reconstruction |  | 91.72% |  |  | 370.6% | 404% | x | 0 | 0 | 1 | 0 | 1 | 1 | 1 | [7 empty] | Political events; Macroeconomic conditions; Weather shocks
Georgia | Europe and Central Asia | P083110 | C1 |  | P083110C1 | Ratio | 2006 / 2013 | Widening and Reconstruction |  | 106.6% |  |  | 114.8% | 107.7% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 |  | P083543C1 | Ratio | 2004 / 2012 | Routine Maintenance | 126.3% | 68.35% |  |  | 182.6% | 267.1% | x | 0 | 0 | 1 | 0 |  | 1 | 1 | [7 empty] | Weather shocks; Political events;
Lao PDR | East Asia and Pacific | P083543 | C1 | S1 | P083543C1S1 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 100.8% | 100.8% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S10 | P083543C1S10 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 116.4% | 116.4% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S11 | P083543C1S11 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 82.41% | 82.41% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S12 | P083543C1S12 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 68.97% | 68.97% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S13 | P083543C1S13 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 76.89% | 76.89% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S14 | P083543C1S14 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 72.87% | 72.87% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S15 | P083543C1S15 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 114.3% | 114.3% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S16 | P083543C1S16 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 101.9% | 101.9% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S17 | P083543C1S17 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 83.36% | 83.36% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S18 | P083543C1S18 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 88.61% | 88.61% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S19 | P083543C1S19 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 158% | 158% | x | 0 | 0 | 1 | 0 |  | 1 | 1 | [7 empty] | Weather shocks; Political events;
Lao PDR | East Asia and Pacific | P083543 | C1 | S2 | P083543C1S2 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 109.4% | 109.4% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S20 | P083543C1S20 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 62.79% | 62.79% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S21 | P083543C1S21 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 59.09% | 59.09% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S22 | P083543C1S22 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 76.26% | 76.26% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S23 | P083543C1S23 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 82.22% | 82.22% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S24 | P083543C1S24 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 81.64% | 81.64% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S25 | P083543C1S25 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 53.62% | 53.62% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S26 | P083543C1S26 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 101.2% | 101.2% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S27 | P083543C1S27 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 114.3% | 114.3% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S28 | P083543C1S28 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 206.6% | 206.6% | x | 0 | 0 | 1 | 0 |  | 1 | 1 | [7 empty] | Weather shocks; Political events;
Lao PDR | East Asia and Pacific | P083543 | C1 | S29 | P083543C1S29 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 235.4% | 235.4% | x | 0 | 0 | 1 | 0 |  | 1 | 1 | [7 empty] | Weather shocks; Political events;
Lao PDR | East Asia and Pacific | P083543 | C1 | S3 | P083543C1S3 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 59% | 59% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S30 | P083543C1S30 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 81.47% | 81.47% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S31 | P083543C1S31 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 83.46% | 83.46% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S32 | P083543C1S32 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 118% | 118% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S33 | P083543C1S33 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 109.9% | 109.9% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S34 | P083543C1S34 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 159.5% | 159.5% | x | 0 | 0 | 1 | 0 |  | 1 | 1 | [7 empty] | Weather shocks; Political events;
Lao PDR | East Asia and Pacific | P083543 | C1 | S35 | P083543C1S35 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 114.9% | 114.9% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S36 | P083543C1S36 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 99.35% | 99.35% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S37 | P083543C1S37 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 100.8% | 100.8% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S38 | P083543C1S38 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 141.4% | 141.4% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S39 | P083543C1S39 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 127.6% | 127.6% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S4 | P083543C1S4 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 144.9% | 144.9% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S40 | P083543C1S40 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 131% | 131% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S5 | P083543C1S5 | Ratio | 2004 / 2011 | Surface Treatment Resurfacing | 100% | 100% |  |  | 104.2% | 104.2% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S6 | P083543C1S6 | Ratio | 2004 / 2011 | Asphalt Mix Resurfacing | 100% | 100% |  |  | 111.1% | 111.1% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S7 | P083543C1S7 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 75.43% | 75.43% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S8 | P083543C1S8 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 87.19% | 87.19% |  | 0 | 0 | 0 | 0
Lao PDR | East Asia and Pacific | P083543 | C1 | S9 | P083543C1S9 | Ratio | 2004 / 2011 | Gravel Resurfacing | 100% | 100% |  |  | 101.5% | 101.5% |  | 0 | 0 | 0 | 0
Georgia | Europe and Central Asia | P086277 | C1 |  | P086277C1 | Ratio | 2004 / 2013 | Strengthening | 128.1% | 168.4% |  |  | 632.6% | 375.7% | x | 1 | 0 | 1 | 0 | [9 empty] | 1 | Change of project scope; Change of project scope;
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S1 | P087004C1S1 | Ratio | 2005 / 2014 | Upgrading |  | 100% |  |  | 121% | 121% |  | 0 | 0 | 0 | 0
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S2 | P087004C1S2 | Ratio | 2005 / 2014 | Upgrading |  | 100% |  |  | 115.5% | 115.5% |  | 0 | 0 | 0 | 0
Cape Verde | Sub-Saharan Africa | P087004 | C1 | S3 | P087004C1S3 | Ratio | 2005 / 2014 | Upgrading |  | 100% |  |  | 148.3% | 148.3% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 |  | P087735C1 | Ratio | 2014 / 2014 | Strengthening |  | 43% |  |  | 81.31% | 189.1% | x | 0 | 1 | 1 | 0 |  | 1 |  |  |  | 1 |  |  |  | 1 | Capacity of Counterpart; Change of project scope; Political events
Iraq | Middle East and North Africa | P087735 | C1 | S1 | P087735C1S1 | Ratio | 2014 / 2014 | Strengthening | 133.3% | 100% |  |  | 96% | 96% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S10 | P087735C1S10 | Ratio | 2014 / 2014 | Reconstruction |  | 100% |  |  | 99.46% | 99.46% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S11 | P087735C1S11 | Ratio | 2014 / 2014 | Strengthening |  | 100% |  |  | 86.96% | 86.96% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S12 | P087735C1S12 | Ratio | 2014 / 2014 | Strengthening |  | 100% |  |  | 95% | 95% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S13 | P087735C1S13 | Ratio | 2014 / 2014 | Strengthening | 140% | 100% |  |  | 113.6% | 113.6% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S2 | P087735C1S2 | Ratio | 2014 / 2014 | Strengthening | 108.3% | 100% |  |  | 100% | 100% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S3 | P087735C1S3 | Ratio | 2014 / 2014 | Strengthening | 130.8% | 100% |  |  | 106.5% | 106.5% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S4 | P087735C1S4 | Ratio | 2014 / 2014 | Strengthening | 100% | 100% |  |  | 92.31% | 92.31% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S5 | P087735C1S5 | Ratio | 2014 / 2014 | Strengthening | 100% | 100% |  |  | 100% | 100% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S6 | P087735C1S6 | Ratio | 2014 / 2014 | Strengthening |  | 100% |  |  | 89.29% | 89.29% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S7 | P087735C1S7 | Ratio | 2014 / 2014 | Strengthening | 90% | 100% |  |  | 97.14% | 97.14% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S8 | P087735C1S8 | Ratio | 2014 / 2014 | Strengthening |  | 100% |  |  | 114.3% | 114.3% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C1 | S9 | P087735C1S9 | Ratio | 2014 / 2014 | Reconstruction |  | 100% |  |  | 99.46% | 99.46% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C2 |  | P087735C2 | Ratio | 2014 / 2014 | Widening |  | 105.8% |  |  | 117.4% | 110.9% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C2 | S1 | P087735C2S1 | Ratio | 2014 / 2014 | Widening |  | 100% |  |  | 116.6% | 116.6% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C2 | S2 | P087735C2S2 | Ratio | 2014 / 2014 | Reconstruction |  | 100% |  |  | 100% | 100% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C2 | S3 | P087735C2S3 | Ratio | 2014 / 2014 | Surface Treatment Resurfacing |  | 100% |  |  | 100% | 100% |  | 0 | 0 | 0 | 0
Iraq | Middle East and North Africa | P087735 | C2 | S4 | P087735C2S4 | Ratio | 2014 / 2014 | Surface Treatment Resurfacing |  | 100% |  |  | 95.65% | 95.65% |  | 0 | 0 | 0 | 0
Argentina | Latin America and Caribbean | P088153 | C1 |  | P088153C1 | Ratio | 2004 / 2011 | Strengthening |  | 60.18% |  |  | 263.6% | 438% | x | 0 | 0 | 1 | 0 | 1 | [6 empty] | 1 | 1 |  | Macroeconomic conditions; Competition; Quality of estimates
Ethiopia | Sub-Saharan Africa | P091077 | C1 |  | P091077C1 | Ratio | 2007 / 2015 | Upgrading |  | 98.16% |  |  | 149.9% | 152.7% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  |  |  | 1 |  |  | Capacity of contractor; Procurement system; Competition
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S1 | P091077C1S1 | Ratio | 2007 / 2015 | Upgrading | 172.4% | 100% |  |  | 161.5% | 161.5% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  |  |  | 1 |  |  | Capacity of contractor; Procurement system; Competition
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S2 | P091077C1S2 | Ratio | 2007 / 2015 | Reconstruction | 203.3% | 100% |  |  | 148.3% | 148.3% |  | 0 | 0 | 0 | 0
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S3 | P091077C1S3 | Ratio | 2007 / 2015 | Reconstruction | 118.5% | 100% |  |  | 123.4% | 123.4% |  | 0 | 0 | 0 | 0
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S4 | P091077C1S4 | Ratio | 2007 / 2015 | Upgrading | 92.15% | 100% |  |  | 168.4% | 168.4% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  |  |  | 1 |  |  | Capacity of contractor; Procurement system; Competition
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S5 | P091077C1S5 | Ratio | 2007 / 2015 | Upgrading | 155.3% | 100% |  |  | 151.8% | 151.8% | x | 0 | 0 | 1 | 0 |  |  |  | 1 |  |  |  | 1 |  |  | Capacity of contractor; Procurement system; Competition
Ethiopia | Sub-Saharan Africa | P091077 | C1 | S6 | P091077C1S6 | Ratio | 2007 / 2015 | Upgrading | 167% | 100% |  |  | 99.04% | 99.04% |  | 0 | 0 | 0 | 0
Mauritius | Sub-Saharan Africa | P091828 | C1 | S1 | P091828C1S1 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction |  | 100% |  |  | 156.9% | 156.9% | x | 0 | 0 | 1 | 0 | 1 | [7 empty] | 1 |  | Macroeconomic conditions; Quality of estimates;
Mauritius | Sub-Saharan Africa | P091828 | C1 | S2 | P091828C1S2 | Ratio | 2009 / 2015 | Reconstruction |  | 100% |  |  | 80.86% | 80.86% |  | 0 | 0 | 0 | 0
Mauritius | Sub-Saharan Africa | P091828 | C1 | S3 | P091828C1S3 | Ratio | 2009 / 2015 | Reconstruction |  | 100% |  |  | 191.7% | 191.7% | x | 0 | 0 | 1 | 0 | 1 | [8 empty] | 1 | Macroeconomic conditions; Change of project scope;
Mauritius | Sub-Saharan Africa | P091828 | C1 | S4 | P091828C1S4 | Ratio | 2009 / 2015 | Reconstruction |  | 100% |  |  | 91.82% | 91.82% |  | 0 | 0 | 0 | 0
Romania | Europe and Central Asia | P093812 | C1 |  | P093812C1 | Ratio | 2006 / 2010 | Surface Treatment Resurfacing |  | 75.52% |  |  | 111.5% | 147.6% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P093906 | C1 |  | P093906C1 | Ratio | 2006 / 2011 | New 4L Expressway |  | 100% |  |  | 114% | 114% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P093906 | C2 |  | P093906C2 | Ratio | 2006 / 2011 | Upgrading |  | 46.82% |  |  | 22.57% | 48.2% | x | 0 | 1 | 0 | 1 |  | 1 |  | 1 | [5 empty] | 1 | Change of project scope; Political events; Procurement system
Georgia | Europe and Central Asia | P094044 | C1 | S1 | P094044C1S1 | Ratio | 2007 / 2012 | Widening | 140% | 100% |  |  | 165% | 165% | x | 0 | 0 | 1 | 0 |  | 1 | 1 | [5 empty] | 1 |  | Political events; Quality of estimates; Weather shocks
Azerbaijan | Europe and Central Asia | P094488 | C1 | S1 | P094488C1S1 | Ratio | 2005 / 2005 | Widening |  | 38.75% |  |  | 69.52% | 179.4% | x | 0 | 1 | 1 | 0 | 1 |  |  |  | 1 |  |  | 1 |  |  | Administrative processes; Macroeconomic conditions; Competition
Azerbaijan | Europe and Central Asia | P094488 | C1 | S2 | P094488C1S2 | Ratio | 2005 / 2005 | Reconstruction |  | 100% |  |  | 178.1% | 178.1% | x | 0 | 0 | 1 | 0 | 1 |  |  |  | 1 |  |  | 1 |  |  | Administrative processes; Macroeconomic conditions; Competition
Angola | Sub-Saharan Africa | P095229 | C1 | S1 | P095229C1S1 | Ratio | 2014 / 2014 | Reconstruction |  | 33.33% |  |  | 153.8% | 461.5% | x | 0 | 1 | 1 | 0 |  | 1 |  |  | 1 | [5 empty] | Political events; Administrative processes;
Haiti | Latin America and Caribbean | P095523 | C1 | S1 | P095523C1S1 | Ratio | 2006 / 2014 | Upgrading |  | 20.62% |  |  | 118.8% | 576.3% | x | 0 | 1 | 1 | 0 |  |  | 1 |  |  | 1 |  |  |  |  | Capacity of Counterpart; Weather shocks;
Haiti | Latin America and Caribbean | P095523 | C1 | S2 | P095523C1S2 | Ratio | 2006 / 2014 | Upgrading |  | 63.49% |  |  | 340.4% | 536.2% | x | 0 | 0 | 1 | 0 |  |  | 1 |  |  | 1 |  |  |  |  | Capacity of Counterpart; Weather shocks;
Argentina | Latin America and Caribbean | P095569 | C1 |  | P095569C1 | Ratio | 2007 / 2014 | Asphalt Mix Resurfacing |  | 101.1% |  |  | 101.4% | 100.3% |  | 0 | 0 | 0 | 0
Peru | Latin America and Caribbean | P095570 | C1 |  | P095570C1 | Ratio | 2006 / 2014 | Gravel Resurfacing |  | 79.76% |  |  | 130.3% | 163.4% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; ;
Peru | Latin America and Caribbean | P095570 | C1 | S1 | P095570C1S1 | Ratio | 2006 / 2014 | Reconstruction |  | 109.2% |  |  | 170.6% | 156.2% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; ;
Peru | Latin America and Caribbean | P095570 | C1 | S2 | P095570C1S2 | Ratio | 2006 / 2014 | Gravel Resurfacing |  | 69.7% |  |  | 127.4% | 182.8% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | Macroeconomic conditions; ;
Peru | Latin America and Caribbean | P095570 | C1 | S3 | P095570C1S3 | Ratio | 2006 / 2014 | Reconstruction |  | 88.91% |  |  | 128% | 144% |  | 0 | 0 | 0 | 0
India | South Asia | P096023 | C1 | S1 | P096023C1S1 | Ratio | 2008 / 2017 | Partial Widening and Reconstruction |  | 100% |  |  | 85.42% | 85.42% |  | 0 | 0 | 0 | 0
India | South Asia | P096023 | C1 | S2 | P096023C1S2 | Ratio | 2008 / 2017 | Partial Widening and Reconstruction |  | 95.12% |  |  | 104.5% | 109.8% |  | 0 | 0 | 0 | 0
Sudan | Sub-Saharan Africa | P098837 | C1 |  | P098837C1 | Ratio | 2011 / 2013 | Upgrading |  | 43.96% |  |  | 114.2% | 259.7% | x | 0 | 1 | 1 | 0 |  | 1 |  |  |  | 1 |  |  |  | 1 | Change of project scope; Political events; Capacity of Counterpart
Bulgaria | Europe and Central Asia | P099894 | C1 |  | P099894C1 | Ratio | 2007 / 2013 | Strengthening |  | 68.22% |  |  | 67.99% | 99.66% |  | 0 | 0 | 0 | 0
Bulgaria | Europe and Central Asia | P099894 | C1 | S1 | P099894C1S1 | Ratio | 2007 / 2013 | Strengthening |  | 98.55% |  |  | 118.2% | 120% |  | 0 | 0 | 0 | 0
Bulgaria | Europe and Central Asia | P099894 | C1 | S2 | P099894C1S2 | Ratio | 2007 / 2013 | Strengthening |  | 106.3% |  |  | 88.96% | 83.69% |  | 0 | 0 | 0 | 0
Bulgaria | Europe and Central Asia | P099894 | C1 | S3 | P099894C1S3 | Ratio | 2007 / 2013 | Strengthening |  | 75.57% |  |  | 70.32% | 93.04% |  | 0 | 0 | 0 | 0
Bulgaria | Europe and Central Asia | P099894 | C1 | S4 | P099894C1S4 | Ratio | 2007 / 2013 | Strengthening |  | 99.11% |  |  | 58.76% | 59.29% |  | 0 | 0 | 0 | 0
Bulgaria | Europe and Central Asia | P099894 | C1 | S5 | P099894C1S5 | Ratio | 2007 / 2013 | Strengthening |  | 96.77% |  |  | 90.73% | 93.76% |  | 0 | 0 | 0 | 0
Bulgaria | Europe and Central Asia | P099894 | C1 | S6 | P099894C1S6 | Ratio | 2007 / 2013 | Strengthening |  | 95.08% |  |  | 65.26% | 68.64% |  | 0 | 0 | 0 | 0
Bhutan | South Asia | P100332 | C1 |  | P100332C1 | Ratio | 2007 / 2013 | New 1L Road |  | 101.1% |  |  | 124.6% | 123.2% |  | 0 | 0 | 0 | 0
Bhutan | South Asia | P100332 | C1 | S1 | P100332C1S1 | Ratio | 2007 / 2013 | New 1L Road |  | 86.35% |  |  | 83% | 96.12% |  | 0 | 0 | 0 | 0
Bhutan | South Asia | P100332 | C1 | S2 | P100332C1S2 | Ratio | 2007 / 2013 | New 1L Road |  | 118.6% |  |  | 127.6% | 107.6% |  | 0 | 0 | 0 | 0
Bhutan | South Asia | P100332 | C1 | S3 | P100332C1S3 | Ratio | 2007 / 2013 | New 1L Road |  | 100% |  |  | 122.4% | 122.4% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | P101258 | C1 |  | P101258C1 | Ratio | 2009 / 2016 | New 4L Expressway |  | 100% |  |  | 118.5% | 118.5% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P107101 | C1 | S1 | P107101C1S1 | Ratio | 2010 / 2012 | Strengthening | 825% | 100% |  |  | 99.79% | 99.79% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P107101 | C1 | S2 | P107101C1S2 | Ratio | 2010 / 2012 | Strengthening | 825% | 100% |  |  | 98.6% | 98.6% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P107101 | C1 | S3 | P107101C1S3 | Ratio | 2010 / 2012 | Strengthening | 750% | 100% |  |  | 74.13% | 74.13% |  | 0 | 0 | 0 | 0
Afghanistan | South Asia | P107101 | C1 | S4 | P107101C1S4 | Ratio | 2010 / 2012 | Strengthening | 750% | 100% |  |  | 66.28% | 66.28% |  | 0 | 0 | 0 | 0
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S1 | P107840C1S1 | Ratio | 2008 / 2016 | Reconstruction |  | 125.7% |  |  | 120% | 95.52% |  | 0 | 0 | 0 | 0 | [5 empty] | 1 |  |  |  |  | Capacity of Counterpart; ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S10 | P107840C1S10 | Ratio | 2008 / 2016 | Reconstruction |  | 72.93% |  |  | 88.37% | 121.2% |  | 0 | 0 | 0 | 0 | [8 empty] | 1 |  | ; Quality of estimates;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S11 | P107840C1S11 | Ratio | 2008 / 2016 | Reconstruction |  | 86.83% |  |  | 78.55% | 90.47% |  | 0 | 0 | 0 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of Counterpart; Quality of estimates;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S2 | P107840C1S2 | Ratio | 2008 / 2016 | Reconstruction |  | 93.16% |  |  | 70.23% | 75.39% |  | 0 | 0 | 0 | 0 | [5 empty] | 1 |  |  |  |  | Capacity of Counterpart; ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S3 | P107840C1S3 | Ratio | 2008 / 2016 | Reconstruction |  | 123.2% |  |  | 122.9% | 99.7% |  | 0 | 0 | 0 | 0 | [8 empty] | 1 |  | ; Quality of estimates;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S4 | P107840C1S4 | Ratio | 2008 / 2016 | Reconstruction |  | 124.3% |  |  | 72.74% | 58.5% |  | 0 | 0 | 0 | 0 | [5 empty] | 1 |  |  | 1 |  | Capacity of Counterpart; Quality of estimates;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S5 | P107840C1S5 | Ratio | 2008 / 2016 | Reconstruction |  | 100.8% |  |  | 128.5% | 127.5% |  | 0 | 0 | 0 | 0 | [5 empty] | 1 |  |  |  |  | Capacity of Counterpart; ;
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S6 | P107840C1S6 | Ratio | 2008 / 2016 | Reconstruction |  | 110% |  |  | 220.7% | 200.6% | x | 0 | 0 | 1 | 0 |  |  | 1 |  |  | 1 |  |  | 1 |  | Capacity of Counterpart; Quality of estimates; Weather shocks
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S7 | P107840C1S7 | Ratio | 2008 / 2016 | Reconstruction |  | 137.4% |  |  | 109.4% | 79.58% |  | 0 | 0 | 0 | 0
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S8 | P107840C1S8 | Ratio | 2008 / 2016 | Reconstruction |  | 102.8% |  |  | 116.7% | 113.6% |  | 0 | 0 | 0 | 0
Macedonia, FYR | Europe and Central Asia | P107840 | C1 | S9 | P107840C1S9 | Ratio | 2008 / 2016 | Reconstruction |  | 72.87% |  |  | 45% | 61.76% |  | 0 | 0 | 0 | 0
Sri Lanka | South Asia | P107847 | C1 | S1 | P107847C1S1 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction | 98.33% | 78.19% |  |  | 141.6% | 181.1% | x | 0 | 0 | 1 | 0 | 1 |  | 1 | [5 empty] | 1 |  | Quality of estimates; Macroeconomic conditions; Weather shocks
Sri Lanka | South Asia | P107847 | C1 | S2 | P107847C1S2 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction | 98.33% | 59.15% |  |  | 142.9% | 241.5% | x | 0 | 0 | 1 | 0 | 1 |  |  |  |  | 1 |  |  |  |  | Macroeconomic conditions; Capacity of counterpart;
Sri Lanka | South Asia | P107847 | C1 | S3 | P107847C1S3 | Ratio | 2009 / 2015 | Partial Widening and Reconstruction | 98.33% | 55.72% |  |  | 142.9% | 256.4% | x | 0 | 0 | 1 | 0 | 1 | [5 empty] | 1 |  |  |  | Macroeconomic conditions; Capacity of contractors;
Honduras | Latin America and Caribbean | P109058 | C1 | S1 | P109058C1S1 | Ratio | 2008 / 2015 | Upgrading |  | 100% |  |  | 108.5% | 108.5% |  | 0 | 0 | 0 | 0
Honduras | Latin America and Caribbean | P109058 | C1 | S2 | P109058C1S2 | Ratio | 2008 / 2015 | Upgrading |  | 100% |  |  | 129.5% | 129.5% |  | 0 | 0 | 0 | 0
Honduras | Latin America and Caribbean | P109058 | C1 | S3 | P109058C1S3 | Ratio | 2008 / 2015 | Upgrading |  | 36.36% |  |  | 114.3% | 314.2% | x | 0 | 1 | 1 | 0 |  | 1 | 1 | [7 empty] | Weather shocks; Political events;
Belarus | Europe and Central Asia | P118375 | C1 | S1 | P118375C1S1 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% |  |  | 83.85% | 83.85% |  | 0 | 0 | 0 | 0
Belarus | Europe and Central Asia | P118375 | C1 | S2 | P118375C1S2 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% |  |  | 132.9% | 132.9% |  | 0 | 0 | 0 | 0
Belarus | Europe and Central Asia | P118375 | C1 | S3 | P118375C1S3 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% |  |  | 81.22% | 81.22% |  | 0 | 0 | 0 | 0
Belarus | Europe and Central Asia | P118375 | C1 | S4 | P118375C1S4 | Ratio | 2010 / 2016 | Widening and Reconstruction | 77.42% | 100% |  |  | 147.4% | 147.4% |  | 0 | 0 | 0 | 0
South Sudan | Sub-Saharan Africa | P118579 | C1 | S1 | P118579C1S1 | Ratio | 2010 / 2013 | Routine Maintenance |  | 84.85% |  |  | 98.41% | 116% |  | 0 | 0 | 0 | 0
South Sudan | Sub-Saharan Africa | P118579 | C1 | S2 | P118579C1S2 | Ratio | 2010 / 2013 | Routine Maintenance |  | 70.62% |  |  | 101.4% | 143.6% |  | 0 | 0 | 0 | 0
South Sudan | Sub-Saharan Africa | P118579 | C1 | S3 | P118579C1S3 | Ratio | 2010 / 2013 | Routine Maintenance |  | 79.47% |  |  | 111.8% | 140.6% |  | 0 | 0 | 0 | 0
South Sudan | Sub-Saharan Africa | P118579 | C1 | S4 | P118579C1S4 | Ratio | 2010 / 2013 | Routine Maintenance |  | 95.1% |  |  | 95.8% | 100.7% |  | 0 | 0 | 0 | 0
South Sudan | Sub-Saharan Africa | P118579 | C1 | S5 | P118579C1S5 | Ratio | 2010 / 2013 | Routine Maintenance |  | 44.79% |  |  | 76.48% | 170.7% | x | 0 | 1 | 1 | 0 |  | 1 |  |  |  | 1 |  |  |  |  | Capacity of counterpart; Political events;
South Sudan | Sub-Saharan Africa | P118579 | C1 | S6 | P118579C1S6 | Ratio | 2010 / 2013 | Routine Maintenance |  | 100% |  |  | 95.41% | 95.41% |  | 0 | 0 | 0 | 0
South Sudan | Sub-Saharan Africa | P118579 | C1 | S7 | P118579C1S7 | Ratio | 2010 / 2013 | Routine Maintenance |  | 93.33% |  |  | 114.9% | 123.1% |  | 0 | 0 | 0 | 0
South Sudan | Sub-Saharan Africa | P118579 | C1 | S8 | P118579C1S8 | Ratio | 2010 / 2013 | Routine Maintenance |  | 49.62% |  |  | 114.2% | 230.2% | x | 0 | 1 | 1 | 0 |  | 1 |  |  |  | 1 |  |  | 1 |  | Quality of estimates; Capacity of counterpart; Political events
Pakistan | South Asia | P125584 | C1 | S1 | P125584C1S1 | Ratio | 2011 / 2016 | Partial Widening and Reconstruction | 100% | 147.6% |  |  | 144% | 97.53% |  | 0 | 0 | 0 | 0
Pakistan | South Asia | P128966 | C1 |  | P128966C1 | Ratio | 2012 / 2016 | Upgrading |  | 100% |  |  | 99.56% | 99.56% |  | 0 | 0 | 0 | 0
Chad | Sub-Saharan Africa | AfDB project - P-TD-DB0-008 | C1 |  | AfDB project - P-TD-DB0-008C1 | Ratio | 2009 / 2017 | Asphalt Mix Resurfacing | 100% | 100% | 168.3% |  | 174.5% | 174.5% | x | 0 | 0 | 1 | 0 | [9 empty] | 1 | ; ; Change of project scope
Swaziland | Sub-Saharan Africa | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6 | C1 |  | Loan numbers: ADB loan: B/SWA/ROD/89/15 and ADF loan: F/SWA/ROD/89/6C1 | Ratio | 1988 / 1994 | Strengthening | 100% | 100% | 604.3% |  | 386.9% | 386.9% | x | 0 | 0 | 1 | 0 | [5 empty] | 1 |  |  |  | 1 | ; ; Change of project scope; Capacity of Counterpart
Niger | Sub-Saharan Africa | 0 | C1 |  | 0C1 | Ratio | 1989 / 1999 | Partial Widening |  | 89.11% | 225.5% |  | 85.59% | 131.1% |  | 0 | 0 | 0 | 0
Zambia | Sub-Saharan Africa | AfDB project - P –Z1-DB0 -063 | C1 |  | AfDB project - P –Z1-DB0 -063 C1 | Ratio | 2010 / 2017 | Reconstruction | 108.3% | 100% | 93.93% |  | 93.93% | 93.93% |  | 0 | 0 | 0 | 0
Kenya | Sub-Saharan Africa | AfDB project P-KE-DB0-019 | C1 |  | AfDB project P-KE-DB0-019C1 | Ratio | 2010 / 2017 | Reconstruction | 141.7% | 100% | 130.5% |  | 100% | 100% |  | 0 | 0 | 0 | 0
Guinea | Sub-Saharan Africa | AfDB P-GN-AB0-005 | C1 |  | AfDB P-GN-AB0-005 C1 | Ratio | 2012 / 2011 | Asphalt Mix Resurfacing |  | 25.74% | 40.07% |  | 39.31% | 152.7% | x | 0 | 1 | 1 | 0 |  |  |  | 1 |  |  | 1 |  |  |  | ; Procurement system; Capacity of contractors
Benin | Sub-Saharan Africa | AfDB-P-BJ-DB0-010 | C1 |  | AfDB-P-BJ-DB0-010 C1 | Ratio | 2002 / 2011 | New 2L Highway |  | 100% | 105.6% |  | 156% | 156% | x | 0 | 0 | 1 | 0 | 1 | [8 empty] | 1 | macroeconomic conditions; macroeconomic conditions; change of project scope
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 | S1 | AfDB loan number: B/CAM/RTE/89/16C1S1 | Ratio | 1988 / 1998 | Upgrading | 200% | 100% | 102.1% |  | 51.53% | 51.53% |  | 0 | 0 | 0 | 0
Cameroon | Sub-Saharan Africa | AfDB loan number: B/CAM/RTE/89/16 | C1 | S2 | AfDB loan number: B/CAM/RTE/89/16C1S2 | Ratio | 1988 / 1998 | Strengthening | 200% | 99.6% | 94.18% |  | 47.55% | 47.74% | x | 0 | 0 | 0 | 1 | [9 empty] | 1 | ; ; change of project scope
Burkina Faso | Sub-Saharan Africa | AfDB loan number: F/BUF/RTE/92/19 | C1 |  | AfDB loan number: F/BUF/RTE/92/19C1 | Ratio | 1990 / 1999 | Upgrading | 220% | 175.9% | 120% |  | 53.07% | 30.17% | x | 1 | 0 | 0 | 1 | [8 empty] | 1 |  | Quality of estimates ;
Lesotho | Sub-Saharan Africa | AfDB loan number: CS/LES/TR/86/18 | C1 |  | AfDB loan number: CS/LES/TR/86/18 C1 | Ratio | 1985 / 1991 | Upgrading | 145.8% | 100% | 230.3% |  | 185.8% | 185.8% | x | 0 | 0 | 1 | 0
Morocco | Middle East and North Africa | AfDB loan number B/MRC/RTE/90/35 | C1 |  | AfDB loan number B/MRC/RTE/90/35C1 | Ratio | 1989 / 1998 | Strengthening |  | 137% | 97.05% |  | 85.77% | 62.61% |  | 0 | 0 | 0 | 0
Namibia | Sub-Saharan Africa | AfDB loan number: F/NAM/ROD/92/1 | C1 |  | AfDB loan number: F/NAM/ROD/92/1 C1 | Ratio | 1991 / 1995 | Upgrading |  | 100% | 150.5% |  | 114.6% | 114.6% |  | 0 | 0 | 0 | 0
Lesotho | Sub-Saharan Africa | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 | C1 |  | AfDB loan numbers: F/LES/TRA-ROD/87/20 & F/LES/ROD/93/SUP/8 C1 | Ratio | 1987 / 1997 | Upgrading | 350% | 100% | 585.8% |  | 258.9% | 258.9% | x | 0 | 0 | 1 | 0 | [9 empty] | 1 | ; ; change of project scope
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C1 |  | AfDB loan number: F/BEN/ROD/92/27 C1 | Ratio | 1992 / 1999 | New 2L Highway |  | 100% | 131.6% |  | 100% | 56.56% |  | 0 | 0 | 0 | 0
Benin | Sub-Saharan Africa | AfDB loan number: F/BEN/ROD/92/27 | C2 |  | AfDB loan number: F/BEN/ROD/92/27 C2 | Ratio | 1992 / 1999 | Partial Widening and Reconstruction |  | 100% | 281.2% |  | 120.9% | 120.9% |  | 0 | 0 | 0 | 0
Malawi | Sub-Saharan Africa | AfDB loan F/MLW/AGR(RD)/87/15 | C1 |  | AfDB loan F/MLW/AGR(RD)/87/15C1 | Ratio | 1987 / 1999 | Upgrading |  | 104.8% | 186.6% |  | 9.313% | 8.883% | x | 0 | 0 | 0 | 1 | 1 | [9 empty] | ; ; Macroeconomic conditions
Burkina Faso | Sub-Saharan Africa | AfDB P-BF-DB0-012 | C1 |  | AfDB P-BF-DB0-012C1 | Ratio | 2004 / 2011 | Strengthening |  | 94.26% | 92.98% |  | 104.1% | 110.4% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | Project number: 42017-013 | C1 | S1 | Project number: 42017-013C1S1 | Ratio | 2010 / 2016 | New 4L Expressway |  | 100% | 121.8% |  | 124.2% | 124.2% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | Project number: 42017-013 | C1 | S2 | Project number: 42017-013C1S2 | Ratio | 2010 / 2016 | Upgrading |  | 100% | 114.8% |  | 117.1% | 117.1% |  | 0 | 0 | 0 | 0
China | East Asia and Pacific | Project number: 42017-013 | C1 | S3 | Project number: 42017-013C1S3 | Ratio | 2010 / 2016 | New 2L Highway |  | 100% | 125.6% |  | 128.1% | 128.1% |  | 0 | 0 | 0 | 0
Kazakhstan | Europe and Central Asia | Project numbers 29568 & 32463 | C1 |  | Project numbers 29568 & 32463 C1 | Ratio | 2000 / 2007 | Surface Treatment Resurfacing |  | 90.2% | 151.5% |  | 175.7% | 194.7% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | ; ; macroeconomic conditions
Cambodia | East Asia and Pacific | Project Number: 42358-013 | C1 |  | Project Number: 42358-013C1 | Ratio | 2009 / 2014 | upgrading |  | 100% | 151.1% |  | 157.1% | 157.1% | x | 0 | 0 | 1 | 0 | 1 | [9 empty] | ; ; macroeconomic conditions
Kazakhstan | Europe and Central Asia | Project Number: 43439-023 | C1 |  | Project Number: 43439-023 C1 | Ratio | 2010 / 2016 | Asphalt Mix Resurfacing |  | 100% | 60.25% |  | 60.25% | 60.25% |  | 0 | 0 | 0 | 0

## Ratios_estimate_vs_actual
Tab: Ratios_estimate vs_outliers Here we look at the actual (a) length and (b) unit cost (both converted into USD) of project components vis-à-vis the original estimates. To do this we compare the actual projects (ex-post) to the original estimates (ex-ante). > Example from figure 1: the actual unit costs of project components in MENA end up 32% higher, on average, compared to the initial forecasts
Row Labels | Ratio length (km) | Ratio unit cost | Figure 1
East Asia and Pacific | 1.0851 | 1.3826
Europe and Central Asia | 1.0144 | 1.1647
Latin America and Caribbean | 0.9742 | 1.8139
Middle East and North Africa | 0.99002 | 1.3167
South Asia | 1.0272 | 1.4068
Sub-Saharan Africa | 0.95038 | 1.8287
Grand Total | 1.0177 | 1.5048
Row Labels | Ratio unit cost | Ratio length
Sub-Saharan Africa | 82.87% | -5.874%
Latin America and Caribbean | 81.39% | -2.58%
South Asia | 40.68% | 2.719%
East Asia and Pacific | 38.26% | 8.719%
Middle East and North Africa | 31.67% | -2.024%
Europe and Central Asia | 16.47% | 1.605%

## Ratios_outliers_per_region
Tab: Ratios_region_outliers_per_region Here we look at the share (%) of project components that go significantly overboard (ratio of x 1.50 or more) or underboard (ratio of x 0.50 or less) when comparing the actual projects (ex post) vs the original estimates (ex-ante). The criteria used are (a) length and (b) the unit cost. Below are examples on how to interpret results: > Example from figure 2: 8% of the project components in South Asia end up with significantly more road (+50%) than what was initialy planned/forecasted. > Example from figure 3: 49% of project components in Sub-Saharan African go significantly overboard in terms of unit costs compared to the initial estimates/forecasts.
a. Length |  |  | Figure 2
Row Labels | Average of Length_outlier_over | Average of Length_outlier_under
East Asia and Pacific | 10% | 5.882%
Europe and Central Asia | 2.532% | 3.797%
Latin America and Caribbean | 5.051% | 9.091%
Middle East and North Africa | 0% | 2.632%
South Asia | 7.792% | 3.896%
Sub-Saharan Africa | 3.061% | 10.2%
Grand Total | 5.882% | 6.417%
b. Unit cost ($ per km built) |  |  | Figure 3
Row Labels | Average of cost_outlier_over | Average of cost_outlier_under
East Asia and Pacific | 26.47% | 2.353%
Europe and Central Asia | 16.46% | 1.266%
Latin America and Caribbean | 42.42% | 5.051%
Middle East and North Africa | 21.05% | 0%
South Asia | 24.68% | 2.597%
Sub-Saharan Africa | 46.94% | 5.102%
Grand Total | 30.84% | 3.03%

## Outliers_by_type
Tab:Outliers_by_type Here we only look at project components that go significantly overboard (ratio of x 1.50 or more) or underboard (ratio of x 0.50 or less) when comparing the actual projects (ex post) vs the original estimates (ex-ante). The criteria used are (a) length and (b) unit costs. We then look at the reason provided by the ICR (implementation completion report) as to why the estimates were significantly off. ICRs provide 10 explanation categories (e.g. 'competition', 'weather shocks', 'political events', etc) which we use here. (note: several categories may be identified in an ICR). > Example from figure (a): For 33 project components where the lenght of the road ended significantly higher than initially forecasted, 'change of the project scope' was identified as a cause for the overrun in 79% of cases. > Example from figure (d): For 173 project components where where unit costs ended up significantly higher than initially forecasted, 'quality of estimates' wase identified as a leading cause for the overrun in 50% of cases.
a. Project components with length completed at +50% over original estimate | [11 empty] | b. Project components with length completed at 50% under original estimate
| Length_outlier_over | 1 | [10 empty] | Length_outlier_under | 1
| Sum of Political events | Sum of Macroeconomic conditions | Sum of Weather shocks | Sum of Procurement system | Sum of Administrative processes | Sum of Capacity of counterpart | Sum of Capacity of contractors | Sum of Competition | Sum of Quality of estimates | Sum of Change of project scope | Count of Project ID |  | Sum of Political events | Sum of Macroeconomic conditions | Sum of Weather shocks | Sum of Procurement system | Sum of Administrative processes | Sum of Capacity of counterpart | Sum of Capacity of contractors | Sum of Competition | Sum of Quality of estimates | Sum of Change of project scope | Count of Project ID
| 1 | 5 | 2 | 2 | 0 | 5 | 1 | 0 | 8 | 26 | 33 |  | 10 | 15 | 6 | 7 | 2 | 16 | 1 | 2 | 11 | 22 | 36
|  | number | share | [10 empty] | number | share
Change of project scope |  | 26 | 78.79% | [8 empty] | Change of project scope |  | 22 | 61.11%
Quality of estimates |  | 8 | 24.24% | [8 empty] | Capacity of counterpart |  | 16 | 44.44%
Macroeconomic conditions |  | 5 | 15.15% | [8 empty] | Macroeconomic conditions |  | 15 | 41.67%
Capacity of counterpart |  | 5 | 15.15% | [8 empty] | Quality of estimates |  | 11 | 30.56%
Weather shocks |  | 2 | 6.061% | [8 empty] | Political events |  | 10 | 27.78%
Procurement system |  | 2 | 6.061% | [8 empty] | Procurement system |  | 7 | 19.44%
Capacity of contractors |  | 1 | 3.03% | [8 empty] | Weather shocks |  | 6 | 16.67%
Political events |  | 1 | 3.03% | [8 empty] | Administrative processes |  | 2 | 5.556%
Competition |  | 0 | 0% | [8 empty] | Competition |  | 2 | 5.556%
Administrative processes |  | 0 | 0% | [8 empty] | Capacity of contractors |  | 1 | 2.778%
c. Project components with unit costs at 50% under original estimate | [11 empty] | d. Project components with unit costs at +50% over original estimate
| cost_outlier_under | 1 | [10 empty] | cost_outlier_over | 1
| Sum of Political events | Sum of Macroeconomic conditions | Sum of Weather shocks | Sum of Procurement system | Sum of Administrative processes | Sum of Capacity of counterpart | Sum of Capacity of contractors | Sum of Competition | Sum of Quality of estimates | Sum of Change of project scope | Count of Project ID |  | Sum of Political events | Sum of Macroeconomic conditions | Sum of Weather shocks | Sum of Procurement system | Sum of Administrative processes | Sum of Capacity of counterpart | Sum of Capacity of contractors | Sum of Competition | Sum of Quality of estimates | Sum of Change of project scope | Count of Project ID
| 1 | 3 | 1 | 2 | 0 | 2 | 0 | 0 | 7 | 10 | 17 |  | 33 | 75 | 41 | 20 | 3 | 59 | 5 | 11 | 86 | 46 | 173
|  | number | share | [10 empty] | number | share
Change of project scope |  | 10 | 58.82% | [8 empty] | Quality of estimates |  | 86 | 49.71%
Quality of estimates |  | 7 | 41.18% | [8 empty] | Macroeconomic conditions |  | 75 | 43.35%
Macroeconomic conditions |  | 3 | 17.65% | [8 empty] | Capacity of counterpart |  | 59 | 34.1%
Capacity of counterpart |  | 2 | 11.76% | [8 empty] | Change of project scope |  | 46 | 26.59%
Procurement system |  | 2 | 11.76% | [8 empty] | Weather shocks |  | 41 | 23.7%
Political events |  | 1 | 5.882% | [8 empty] | Political events |  | 33 | 19.08%
Weather shocks |  | 1 | 5.882% | [8 empty] | Procurement system |  | 20 | 11.56%
Administrative processes |  | 0 | 0% | [8 empty] | Competition |  | 11 | 6.358%
Capacity of contractors |  | 0 | 0% | [8 empty] | Capacity of contractors |  | 5 | 2.89%
Competition |  | 0 | 0% | [8 empty] | Administrative processes |  | 3 | 1.734%

## Unit_costs_per_region
Tab Unit_costs_per_region Here we are trying to get the average unit costs (USD per km) for project components across regions. However, there are different project types that are more or less costly (e.g. new 6l expressway vs.gravel resurfacing). So to compare apples to apples we must control for work types. We do this by focusing on the work types with the largest sample: (a) asphalt mix resurfacing; (b) reconstruction; and (c) upgrading. We also showcase the average project length as it is possible that larger projects are able to leverage economies of scale > Example from figure a: Sub-saharan african has the largest unit cost for actual 'asphalt mix resurfacing' projects, which stand at 0.22M per km.
Check_cost_over | (All)
Figure a. 'Asphalt Mix Resurfacing' work type: 76 project components
Row Labels | Count of Cost Type | Count of Unit costs | Average of Length (km) | Average of Unit costs | Average of Cost | Row Labels | Estimated unit costs (M/km) | Actual avrg unit costs (M/km) | Average of Length (km) | Sample
Asphalt Mix Resurfacing | 152 | 152 | 310.2809 | 0.10914 | 30.1957 | Europe and Central Asia | 0.19867 | 0.24713 | 166.39 | 10
East Asia and Pacific | 34 | 34 | 283.3618 | 0.063136 | 22.3375 | Sub-Saharan Africa | 0.22784 | 0.20807 | 182.1692 | 13
Actual | 17 | 17 | 237.8471 | 0.070584 | 21.8468 | South Asia | 0.059837 | 0.10015 | 1609 | 4
Estimate | 17 | 17 | 328.8765 | 0.055687 | 22.8281 | East Asia and Pacific | 0.055687 | 0.070584 | 237.8471 | 17
Europe and Central Asia | 20 | 20 | 163.21 | 0.2229 | 43.5123 | Latin America and Caribbean | 0.046219 | 0.070574 | 212.229 | 31
Actual | 10 | 10 | 166.39 | 0.19867 | 39.1707 | Middle East and North Africa | 0.023256 | 0.033523 | 88 | 1
Estimate | 10 | 10 | 160.03 | 0.24713 | 47.854
Latin America and Caribbean | 62 | 62 | 252.3226 | 0.058397 | 22.5826
Actual | 31 | 31 | 212.229 | 0.070574 | 22.8561
Estimate | 31 | 31 | 292.4161 | 0.046219 | 22.309
Middle East and North Africa | 2 | 2 | 87 | 0.028389 | 2.475
Actual | 1 | 1 | 88 | 0.033523 | 2.95 | Figure b. 'Reconstruction' work type: 128 projects
Estimate | 1 | 1 | 86 | 0.023256 | 2 | Row Labels | Estimated unit costs | Actual avrg unit costs | Average of Length (km) | Sample
South Asia | 8 | 8 | 1594.75 | 0.079993 | 126.3136 | Sub-Saharan Africa | 0.4385 | 0.84595 | 368.4688 | 16
Actual | 4 | 4 | 1609 | 0.10015 | 150.2646 | East Asia and Pacific | 0.24699 | 0.4015 | 334.5618 | 17
Estimate | 4 | 4 | 1580.5 | 0.059837 | 102.3625 | Europe and Central Asia | 0.27574 | 0.25961 | 47.8344 | 32
Sub-Saharan Africa | 26 | 26 | 218.7769 | 0.21796 | 20.9404 | Latin America and Caribbean | 0.1202 | 0.17214 | 619.2425 | 40
Actual | 13 | 13 | 182.1692 | 0.20807 | 23.7819 | South Asia | 0.17879 | 0.17204 | 516.2833 | 6
Estimate | 13 | 13 | 255.3846 | 0.22784 | 18.0989 | Middle East and North Africa | 0.11883 | 0.14108 | 52.7235 | 17
Bituminous Pavement Preventive Treatment | 20 | 20 | 247.4 | 0.043635 | 6.1095
Concrete Pavement Restoration | 2 | 2 | 917 | 0.15916 | 145.95
Gravel Resurfacing | 72 | 72 | 1151.0444 | 0.014256 | 12.8545
New 1L Road | 12 | 12 | 64.9825 | 0.13584 | 9.1183
New 2L Highway | 17 | 17 | 58.9565 | 1.3475 | 27.2983
New 4L Expressway | 45 | 45 | 81.1628 | 5.2552 | 352.7217
New 6L Expressway | 4 | 4 | 21.425 | 13.7383 | 224.005
Partial Widening | 2 | 2 | 1107.5 | 0.097599 | 108.0694 | Figure c. 'Upgrading' work type: 99 projects
Partial Widening and Reconstruction | 20 | 20 | 66.563 | 0.72104 | 25.2412 | Row Labels | Estimated unit costs | Actual avrg unit costs | Average of Length (km) | Sample
Reconstruction | 256 | 256 | 349.0336 | 0.26142 | 30.4857 | Europe and Central Asia | 0.7965 | 0.77711 | 25.05 | 46
East Asia and Pacific | 34 | 34 | 378.9262 | 0.32424 | 47.7733 | Sub-Saharan Africa | 0.30113 | 0.59775 | 128.7271 | 31
Actual | 17 | 17 | 334.5618 | 0.4015 | 53.5019 | Latin America and Caribbean | 0.28078 | 0.49914 | 60.8333 | 9
Estimate | 17 | 17 | 423.2906 | 0.24699 | 42.0447 | East Asia and Pacific | 0.16504 | 0.18137 | 162.3985 | 46
Europe and Central Asia | 64 | 64 | 40.8125 | 0.26767 | 17.1259 | South Asia | 0.091788 | 0.12836 | 1179.4455 | 11
Actual | 32 | 32 | 47.8344 | 0.25961 | 18.7015
Estimate | 32 | 32 | 33.7906 | 0.27574 | 15.5503
Latin America and Caribbean | 80 | 80 | 574.4975 | 0.14617 | 33.4804
Actual | 40 | 40 | 619.2425 | 0.17214 | 41.2078
Estimate | 40 | 40 | 529.7525 | 0.1202 | 25.7531
Middle East and North Africa | 34 | 34 | 56.0853 | 0.12995 | 6.6772
Actual | 17 | 17 | 52.7235 | 0.14108 | 7.2211
Estimate | 17 | 17 | 59.4471 | 0.11883 | 6.1333
South Asia | 12 | 12 | 612.8667 | 0.17542 | 33.9813
Actual | 6 | 6 | 516.2833 | 0.17204 | 33.3492
Estimate | 6 | 6 | 709.45 | 0.17879 | 34.6134
Sub-Saharan Africa | 32 | 32 | 582.375 | 0.64222 | 55.3358
Actual | 16 | 16 | 368.4688 | 0.84595 | 67.7434
Estimate | 16 | 16 | 796.2812 | 0.4385 | 42.9282
Routine Maintenance | 43 | 43 | 4241.986 | 0.021096 | 12.7395
Strengthening | 126 | 126 | 662.1485 | 0.27279 | 64.7918
Surface Treatment Resurfacing | 47 | 47 | 410.5128 | 0.057298 | 21.1615
Upgrading | 198 | 198 | 228.548 | 0.28479 | 33.7461
East Asia and Pacific | 92 | 92 | 154.9701 | 0.1732 | 22.7409
Actual | 46 | 46 | 162.3985 | 0.18137 | 24.1531
Estimate | 46 | 46 | 147.5417 | 0.16504 | 21.3287
Europe and Central Asia | 4 | 4 | 24.525 | 0.78681 | 19.3975
Actual | 2 | 2 | 25.05 | 0.77711 | 19.3
Estimate | 2 | 2 | 24 | 0.7965 | 19.495
Latin America and Caribbean | 18 | 18 | 66.6778 | 0.38996 | 15.0533
Actual | 9 | 9 | 60.8333 | 0.49914 | 16.3211
Estimate | 9 | 9 | 72.5222 | 0.28078 | 13.7856
South Asia | 22 | 22 | 951.3591 | 0.11008 | 58.5782
Actual | 11 | 11 | 1179.4455 | 0.12836 | 64.3155
Estimate | 11 | 11 | 723.2727 | 0.091788 | 52.8408
Sub-Saharan Africa | 62 | 62 | 141.404 | 0.44944 | 47.6177
Actual | 31 | 31 | 128.7271 | 0.59775 | 59.6195
Estimate | 31 | 31 | 154.081 | 0.30113 | 35.616
Widening | 28 | 28 | 150.8439 | 1.6653 | 172.0039
Widening and Reconstruction | 78 | 78 | 151.4465 | 0.95098 | 84.7467
Grand Total | 1122 | 1122 | 518.4118 | 0.56282 | 53.1291

## Project_type_outliers
Tab Project_type_outliers Here we look at the project types that were the most likely to be "major overruns" in terms of unit costs (USD per km). An overrun is when actual unit costs in terms of USD per KM (ex-ante) end up 50% higher compared to original estimate (ex-post). For the figure below, we are only illustrating the project types for which we have a sample size of over 10 project components. > Example: 50% of all "New 4L Expressway" project types end up as major overuns
cost_outlier_over | (All)
Row Labels | Sum of cost_outlier_over | Count of Project ID | Share |  | Figure: share of project type that end up as overruns on unit-costs (USD per km)
Asphalt Mix Resurfacing | 30 | 78 | 38.46%
Bituminous Pavement Preventive Treatment | 0 | 9 | 0%
Concrete Pavement Restoration | 0 | 1 | 0%
Gravel Resurfacing | 8 | 36 | 22.22%
New 1L Road | 0 | 6 | 0%
New 2L Highway | 3 | 7 | 42.86%
New 4L Expressway | 8 | 24 | 33.33%
New 6L Expressway | 1 | 2 | 50%
Partial Widening | 0 | 2 | 50%
Partial Widening and Reconstruction | 4 | 10 | 0%
Reconstruction | 42 | 127 | 40%
Routine Maintenance | 9 | 23 | 33.07%
Strengthening | 15 | 63 | 39.13%
Surface Treatment Resurfacing | 5 | 21 | 23.81%
Upgrading | 30 | 99 | 23.81%
Widening | 6 | 14 | 30.3%
Widening and Reconstruction | 12 | 39 | 42.86%
Grand Total | 173 | 561 | 30.84%
ADD average cost
ADD average cost
| Share of major cost overruns | Average unit cost
Widening and Reconstruction | 42.86% | 1.0146
Reconstruction | 40% | 0.30457
Strengthening | 39.13% | 0.28382
Asphalt Mix Resurfacing | 38.46% | 0.11202
New 4L Expressway | 33.33% | 5.593
Routine Maintenance | 33.07% | 0.027219
Upgrading | 23.81% | 0.34679
Surface Treatment Resurfacing | 23.81% | 0.052917
Gravel Resurfacing | 22.22% | 0.010722
Cost Type | Actual
Row Labels | Count of Cost Type | Count of Unit costs | Average of Length (km) | Average of Unit costs | Average of Cost
Asphalt Mix Resurfacing | 76 | 76 | 278.6658 | 0.11202 | 31.3792
Bituminous Pavement Preventive Treatment | 9 | 9 | 353.4444 | 0.045334 | 7.7889
Concrete Pavement Restoration | 1 | 1 | 917 | 0.14537 | 133.3
Gravel Resurfacing | 36 | 36 | 1034.4611 | 0.010722 | 12.9534
New 1L Road | 6 | 6 | 64.115 | 0.13607 | 8.6267
New 2L Highway | 7 | 7 | 69.04 | 1.1694 | 37.1441
New 4L Expressway | 24 | 24 | 76.615 | 5.593 | 374.0922
New 6L Expressway | 2 | 2 | 21.425 | 17.5249 | 271.325
Partial Widening | 1 | 1 | 1115 | 0.094743 | 105.6389
Partial Widening and Reconstruction | 10 | 10 | 60.716 | 0.82556 | 27.8657
Reconstruction | 128 | 128 | 327.1676 | 0.30457 | 35.6487
Routine Maintenance | 23 | 23 | 4255.4957 | 0.027219 | 13.7862
Strengthening | 63 | 63 | 684.6863 | 0.28382 | 87.3331
Surface Treatment Resurfacing | 23 | 23 | 401.2609 | 0.071441 | 26.1026
Upgrading | 99 | 99 | 252.8522 | 0.34679 | 38.9112
Widening | 14 | 14 | 143.7521 | 1.9868 | 185.1264
Widening and Reconstruction | 39 | 39 | 138.1059 | 1.0146 | 87.2401
Grand Total | 561 | 561 | 519.6757 | 0.63625 | 60.7848